## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA | Jaypur | Bankura Division | Mahaldanga Piped Water Supply Scheme | SM/18318 | New | Material Requisition To Resource Division |  |  | RTOR000060/2022-2023 | 79BQA | 06/01/2023 | 06/01/2023 | Resource Division | 240.6 | 0 | 0 | 0
2 | BANKURA | Jaypur | Bankura Mechanical | Mahaldanga Piped Water Supply Scheme | SM/18318 | New | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for newly sunk TW No-I, TW No-II & T/W No-III of Mahaldanga piped water supply scheme under Bankura Mechanical Division, PHE Dte Block : Joypur, Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000166/2023-2024 | 878/BMD | 04/05/2023 | 31/10/2023 | UNIVERSAL ENTERPRISE | 53.32 | 0 | 0 | 32
3 | BANKURA | Jaypur | Bankura Division | Mahaldanga Piped Water Supply Scheme | SM/18318 | New | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR MAHALDANGA PIPED WATER SUPPLY SCHEME, BLOCK- JOYPUR, DIST- BANKURA UNDER JJM INCLUDING TRIAL RUN FOR 3 MONTHS AND O&M FOR A PERIOD OF 3 YEARS UNDER BANKURA DIVISION,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000472/2023-2024 | 2327/BQA | 14/08/2023 | 01/04/2026 | M/S TARUN KUMAR PATRA | 904.78 | 0 | 0 | 65
4 | BANKURA | Jaypur | Bankura Mechanical | Mahaldanga Piped Water Supply Scheme | SM/18318 | New | Mahaldanga T/W-II |  |  | BILL/00854/2023-2024 | BP-2023-24-40 | 18/12/2023 | 18/12/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.29 | 0 | 0 | 0
5 | BANKURA | Jaypur | Bankura Mechanical | Mahaldanga Piped Water Supply Scheme | SM/18318 | New | Mahaldanga T/W-III |  |  | BILL/00853/2023-2024 | BP-2023-24-39 | 18/12/2023 | 18/12/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.28 | 0 | 0 | 0
Total | [13 empty] | 1205.27 | 0 | 0