## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA | Patrasayer | Bankura Mechanical | Rampur Piped Water Supply Scheme | SM/18349 | New | New Service connection for P/H II of Rampur water supply scheme at Patrasayer Block (SM/18349) |  |  | BILL/01138/2024-2025 | BP-2024-25-276 | 21/11/2024 | 21/11/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.58 | 0 | 0 | 0
2 | BANKURA | Patrasayer | Bankura Mechanical | Rampur Piped Water Supply Scheme | SM/18349 | New | New Service connection for T/W III of Rampur water supply scheme at Patrasayer Block under BMD PHE Dte. |  |  | BILL/01137/2024-2025 | BP-2024-25-275 | 21/11/2024 | 21/11/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.91 | 0 | 0 | 0
3 | BANKURA | Patrasayer | Bankura Mechanical | Rampur Piped Water Supply Scheme | SM/18349 | New | New service connection for P/H no I of Rampur Water supply scheme at Patrasayer Block under BMD PHE Dte. |  |  | BILL/01139/2024-2025 | BP-2024-25-277 | 21/11/2024 | 21/11/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 8.11 | 0 | 0 | 0
4 | BANKURA | Patrasayer | Bankura Division | Rampur Piped Water Supply Scheme | SM/18349 | New | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR RAMPUR PIPED WATER SUPPLY SCHEME, BLOCK- PATRASAYER, DIST- BANKURA UNDER JJM INCLUDING TRIAL RUN FOR 3 MONTHS AND O&M FOR A PERIOD OF 3 YEARS UNDER BANKURA DIVISION,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000473/2023-2024 | 2328/BQA | 14/08/2023 | 01/04/2026 | M/S TARUN KUMAR PATRA | 835.53 | 134.53 | 16.1 | 80
5 | BANKURA | Patrasayer | Bankura Mechanical | Rampur Piped Water Supply Scheme | SM/18349 | New | Acceptance cum Formal work order for the work of Providing and installation of Electromagnetic flowmeter with motorized Sluice Valve for respective OHR for at Rampur Piped Water Supply Scheme under BMD PHE Dte Dist-Bankura. | Assistant Engineer | Junior Engineer | ORD/000039/2025-2026 | 243/BMD | 14/05/2025 | 12/08/2025 | CHAKRABORTY MINING & ENGINEERING. | 12.22 | 0 | 0 | 0
6 | BANKURA | Patrasayer | Bankura Division | Rampur Piped Water Supply Scheme | SM/18349 | New | Jack Pushing under different place over Irrigation Canal & Bodai Nadi for Rampur Piped Water Supply Scheme under Patrasyer Block under Bishnupur Sub-Division of Bankura Division, P.H.E. Dte. (SM/18349). | Assistant Engineer | Junior Engineer | ORD/001959/2024-2025 | 694/BQA | 12/03/2025 | 10/06/2025 | M/S TARUN KUMAR PATRA | 123.94 | 0 | 0 | 80
7 | BANKURA | Patrasayer | Bankura Division | Rampur Piped Water Supply Scheme | SM/18349 | New | Construction of Approach Road for (Head Work Site & 2nd Tubewell site), Guard wall at OHR side, HDD Boring in connection with Jal Jeevan Mission (JJM) Rampur Piped water Supply Scheme within Patrasayer Block under Bishnupur Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000255/2025-2026 | 1496/BQA | 07/07/2025 | 05/10/2025 | M/S TARUN KUMAR PATRA | 36.2 | 0 | 0 | 30
8 | BANKURA | Patrasayer | Bankura Mechanical | Rampur Piped Water Supply Scheme | SM/18349 | New | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for newly sunk TW No-I, TW No-II & TW No-III of Rampur Piped water supply scheme Block : Patrasayar under Bankura Mechanical Division, PHE Dte. Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000249/2023-2024 | 1169/BMD | 01/06/2023 | 16/05/2026 | ORIENTAL ENGINEERING CO. | 68.63 | 23.1 | 33.66 | 33
Total | [13 empty] | 1094.12 | 157.63 | 14.41