## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Laying rising main, distribution system, collecting line from RBTW to CWR, construction of CWR, Pump House, Sub-Station, Chlorine Room, OHR and boundary wall including provision of FHTC under balance work of Improvement of Sonagara Water Supply Scheme u | SM/18390 | Augmentation | Construction of 400 m³ Capacity R.C.C OHR (based on Departmental Design) with 20 mtr. staging height including foundation, pipeline connection and Providing FHTC for Zone- IB of Improvement of Sonagara Piped Water Supply Scheme under (BRGF Ph-I) under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000738/2023-2024 | 2737/BQA | 04/10/2023 | 30/06/2024 | MD. AAMIR KHAN | 302.89 | 0 | 0 | 0
2 | BANKURA |  | Bankura Division | Laying rising main, distribution system, collecting line from RBTW to CWR, construction of CWR, Pump House, Sub-Station, Chlorine Room, OHR and boundary wall including provision of FHTC under balance work of Improvement of Sonagara Water Supply Scheme u | SM/18390 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000055/2023-2024 | 2470/BQA | 29/08/2023 | 29/08/2023 | Resource Division | 227.39 | 0 | 0 | 0
3 | BANKURA |  | Bankura Division | Laying rising main, distribution system, collecting line from RBTW to CWR, construction of CWR, Pump House, Sub-Station, Chlorine Room, OHR and boundary wall including provision of FHTC under balance work of Improvement of Sonagara Water Supply Scheme u | SM/18390 | Augmentation | Construction of Boundary wall, Approach road, Land Development with other allied works for Improvement of Sonagara Piped Water Supply Scheme under (BRGF Ph-I) under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (For OHR site) |  | Junior Engineer | ORD/000001/2023-2024 | 754/BQA | 04/04/2023 | 19/05/2023 | ASEK ALI KHAN | 14.57 | 0 | 0 | 0
4 | BANKURA |  | Bankura Division | Laying rising main, distribution system, collecting line from RBTW to CWR, construction of CWR, Pump House, Sub-Station, Chlorine Room, OHR and boundary wall including provision of FHTC under balance work of Improvement of Sonagara Water Supply Scheme u | SM/18390 | Augmentation | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Kalyansaer (1), Kalapathar (2), Bera (3), Kese (4), Lachankunda (5), Bhagra (6), Lalbazar (7), Digarkanali (8), Karamara (9), Damdi (10), Baburamhir (11), Raidihi (12), Bankanali (13), Indrajhor (14), Khatanga (61), Jaljura (62), Gumkihata (63), Barakharanga (64), Madhupur (65), Khalpara (66), Pairaguri (67), Siarbeda (68), Chirugora (69), Karrasol (70), Chaturi Nutandihi (72), Chaturi (73), Lachhipur (74), Manhara (75), Bishanpur (76), Rautkhana (77), Pirra (78), Rangasol (79), Birudi (80), Dundar (81) & Khejurbedia (82) mouzas for Zone- IA of Improvement of Sonagara Water Supply Scheme under BRGF (Phase - I) at Block- Raipur, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000478/2023-2024 | 2333/BQA | 14/08/2023 | 02/04/2026 | MUNMUN UPADHYAY | 208.25 | 0 | 0 | 40
5 | BANKURA |  | Bankura Division | Laying rising main, distribution system, collecting line from RBTW to CWR, construction of CWR, Pump House, Sub-Station, Chlorine Room, OHR and boundary wall including provision of FHTC under balance work of Improvement of Sonagara Water Supply Scheme u | SM/18390 | Augmentation | Soil Investigation work for the proposed construction of RCC Over Head Reservoir under Bankura Sadar Sub- Division & Khatra Sub- Division of Bankura Division, P.H.E. Dte. (2nd Call) | Assistant Engineer | Junior Engineer | ORD/000861/2023-2024 | 2953/BQA | 31/10/2023 | 30/12/2023 | K S GROUP | 5.18 | 0 | 0 | 70
6 | BANKURA |  | Bankura Division | Laying rising main, distribution system, collecting line from RBTW to CWR, construction of CWR, Pump House, Sub-Station, Chlorine Room, OHR and boundary wall including provision of FHTC under balance work of Improvement of Sonagara Water Supply Scheme u | SM/18390 | Augmentation | Supplying, laying, fitting, fixing and jointing of MS Delivery main Connecting river bed tube well to Common Manifold incuding supply and erecting of guard piling etc. including cost of clamp, bracket, 'U' bolt etc. all complete with other allied works for Improvement of Sonagara Piped Water Supply Scheme under (BRGF Ph-I) under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000469/2023-2024 | 2324/BQA | 14/08/2023 | 12/11/2023 | EARTH MOVING (INDIA) | 129.16 | 128.44 | 99.44 | 94
7 | BANKURA |  | Bankura Division | Laying rising main, distribution system, collecting line from RBTW to CWR, construction of CWR, Pump House, Sub-Station, Chlorine Room, OHR and boundary wall including provision of FHTC under balance work of Improvement of Sonagara Water Supply Scheme u | SM/18390 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000297/2023-2024 | 885/BQA | 12/03/2024 | 12/03/2024 | Resource Division | 143.02 | 0 | 0 | 0
8 | BANKURA |  | Bankura Division | Laying rising main, distribution system, collecting line from RBTW to CWR, construction of CWR, Pump House, Sub-Station, Chlorine Room, OHR and boundary wall including provision of FHTC under balance work of Improvement of Sonagara Water Supply Scheme u | SM/18390 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000159/2023-2024 | 116/BQA | 10/01/2024 | 10/01/2024 | Resource Division | 39.55 | 0 | 0 | 0
9 | BANKURA |  | Bankura Mechanical | Laying rising main, distribution system, collecting line from RBTW to CWR, construction of CWR, Pump House, Sub-Station, Chlorine Room, OHR and boundary wall including provision of FHTC under balance work of Improvement of Sonagara Water Supply Scheme u | SM/18390 | Augmentation | Laying rising main, distribution system, collecting line from RBTW to CWR, construction of CWR, Pump House, Sub-Station, Chlorine Room, OHR and boundary wall including provision of FHTC under balance work of Improvement of Sonagara Water Supply Scheme under BRGF (Phase - I) under Jal Jeevan Mission Programme |  |  | BILL/01519/2023-2024 | BP-2023-24-119 | 21/02/2024 | 21/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.05 | 0 | 0 | 0
10 | BANKURA |  | Bankura Mechanical | Laying rising main, distribution system, collecting line from RBTW to CWR, construction of CWR, Pump House, Sub-Station, Chlorine Room, OHR and boundary wall including provision of FHTC under balance work of Improvement of Sonagara Water Supply Scheme u | SM/18390 | Augmentation | Service connection charge for SONAGARA water supply scheme (scheme code: SM/18390) |  |  | BILL/00350/2024-2025 | BP-2024-25-82 | 10/06/2024 | 10/06/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 36.61 | 0 | 0 | 0
11 | BANKURA |  | Bankura Division | Laying rising main, distribution system, collecting line from RBTW to CWR, construction of CWR, Pump House, Sub-Station, Chlorine Room, OHR and boundary wall including provision of FHTC under balance work of Improvement of Sonagara Water Supply Scheme u | SM/18390 | Augmentation | Construction of Boundary wall, Approach road, Land Development with other allied works for Improvement of Sonagara Piped Water Supply Scheme under (BRGF Ph-I) under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (For Head Work site) | Assistant Engineer | Junior Engineer | ORD/000383/2023-2024 | 2382/BQA | 14/08/2023 | 02/12/2025 | GANGADHAR MONDAL | 29.04 | 11.6 | 39.96 | 80
12 | BANKURA |  | Bankura Mechanical | Laying rising main, distribution system, collecting line from RBTW to CWR, construction of CWR, Pump House, Sub-Station, Chlorine Room, OHR and boundary wall including provision of FHTC under balance work of Improvement of Sonagara Water Supply Scheme u | SM/18390 | Augmentation | Acceptance cum Formal work order for the work of Providing of pumping machineries, Sub-Station equipment¿s and other Electro-mechanical accessories For the scheme of Laying rising main distribution system collecting line from RBTW to CWR Pump House, Sub-Station, Chlorine Room, OHR and boundary wall including providing of FHTC under balance work of improvement of Sanagara water supply scheme under BRGF( Phase-I) under Jal Jeevan Mission Programme Block - Raipur , Dist - Bankura | Assistant Engineer,Driller-in-Charge | Junior Engineer | ORD/000613/2023-2024 | 2068/BMD | 12/09/2023 | 29/11/2025 | WEST BENGAL ENGINEERING CO. | 409.3 | 200.9 | 49.08 | 56
13 | BANKURA |  | Bankura Division | Laying rising main, distribution system, collecting line from RBTW to CWR, construction of CWR, Pump House, Sub-Station, Chlorine Room, OHR and boundary wall including provision of FHTC under balance work of Improvement of Sonagara Water Supply Scheme u | SM/18390 | Augmentation | Construction of High lift Pump House with all allied works for balance work of Improvement of Sonagara Water Supply Scheme under BRGF (Phase - I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001085/2023-2024 | 3531/BQA | 29/12/2023 | 02/04/2025 | ASOKE KUMAR SAHU | 63.51 | 30.96 | 48.74 | 81
14 | BANKURA |  | Bankura Mechanical | Laying rising main, distribution system, collecting line from RBTW to CWR, construction of CWR, Pump House, Sub-Station, Chlorine Room, OHR and boundary wall including provision of FHTC under balance work of Improvement of Sonagara Water Supply Scheme u | SM/18390 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of submersible pumping machineries & gaseous chlorination system and other electromechanical accessories and Making an arrangement for proper material management and handling at Ailakandi PHE Mechanical office campus for Augmentation of Sonagara and its adjoining mouzas water supply scheme under Jal Jeeven mission Progremme under Bankura Mechanical Division, P.H.E. Dte | Driller-in-Charge | Junior Engineer | ORD/000144/2024-2025 | 487/BMD | 09/07/2024 | 03/08/2025 | WEST BENGAL ENGINEERING CO. | 83.28 | 0 | 0 | 30
15 | BANKURA |  | Bankura Division | Laying rising main, distribution system, collecting line from RBTW to CWR, construction of CWR, Pump House, Sub-Station, Chlorine Room, OHR and boundary wall including provision of FHTC under balance work of Improvement of Sonagara Water Supply Scheme u | SM/18390 | Augmentation | Repairing and painting of Over Head Reservoir (Capacity 550 Cum., staging height 20 Mtr.), Boundary Wall and construction of Chlorination Room, Guard Room at OHR sites with all allied works under balance work of Improvement of Sonagara Water Supply Scheme under BRGF (Phase - I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000123/2025-2026 | 1285/BQA | 17/06/2025 | 15/09/2025 | SUBHANKAR BANERJEE | 54.07 | 0 | 0 | 0
16 | BANKURA |  | Bankura Mechanical | Laying rising main, distribution system, collecting line from RBTW to CWR, construction of CWR, Pump House, Sub-Station, Chlorine Room, OHR and boundary wall including provision of FHTC under balance work of Improvement of Sonagara Water Supply Scheme u | SM/18390 | Augmentation | Acceptance cum Formal work order for the work of Providing internal & external illumination arrangement for CWR Pump House, Sub-Station, Chlorine Room of Sanagara water supply scheme under Bankura Mechanical Division,PHE. Dte. in the Block - Raipur , Dist ¿ Bankura. | Driller-in-Charge | Junior Engineer | ORD/000013/2025-2026 | 148/BMD | 30/04/2025 | 29/07/2025 | WEST BENGAL ENGINEERING CO. | 12.85 | 0 | 0 | 0
17 | BANKURA |  | Bankura Division | Laying rising main, distribution system, collecting line from RBTW to CWR, construction of CWR, Pump House, Sub-Station, Chlorine Room, OHR and boundary wall including provision of FHTC under balance work of Improvement of Sonagara Water Supply Scheme u | SM/18390 | Augmentation | Balance work of Rising main, Construction of Chlorine Room and Construction of Operator Room for Improvement of Sonagara Water Supply Scheme under BRGF (Phase - I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (For Sonagara Zone-IIB site) | Assistant Engineer | Junior Engineer | ORD/000120/2025-2026 | 1282/BQA | 17/06/2025 | 15/09/2025 | SIBSANKAR CHOWDHURY | 45.08 | 0 | 0 | 0
18 | BANKURA |  | Bankura Division | Laying rising main, distribution system, collecting line from RBTW to CWR, construction of CWR, Pump House, Sub-Station, Chlorine Room, OHR and boundary wall including provision of FHTC under balance work of Improvement of Sonagara Water Supply Scheme u | SM/18390 | Augmentation | Laying additional HDPE pipeline, Supply of Sluice valve, construction of valve chamber with all allied works under Improvement of Sonagara Water Supply Scheme (Zone-IA) under BRGF (Phase - I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000171/2025-2026 | 1307/BQA | 17/06/2025 | 02/01/2026 | TARINI CHARAN UPADHYAY | 19.48 | 0 | 0 | 0
Total | [13 empty] | 1823.28 | 371.9 | 20.4