## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Augmentation works for 86 Nos. Mouzas of Saltora Block 07 nos Zone (06 nos OHR & Direct Zone- 1) under Saltora- Chhatna Water Supply Scheme (BRGF ph - I project). | SM/18423 | Augmentation | Creation of Balance FHTC (Functional House Hold Tap Connection), construction of platform with allied works for Augmentation of Monipur (Zone - D) under Saltora- Chhatna Block W/S Scheme (BRGF Ph - I project) under Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000488/2023-2024 | 2340/BQA | 14/08/2023 | 10/05/2024 | PARTHA PRATIM CHHATAIT | 142.05 | 0 | 0 | 0
2 | BANKURA |  | Bankura Division | Augmentation works for 86 Nos. Mouzas of Saltora Block 07 nos Zone (06 nos OHR & Direct Zone- 1) under Saltora- Chhatna Water Supply Scheme (BRGF ph - I project). | SM/18423 | Augmentation | Creation of Balance FHTC (Functional House Hold Tap Connection), construction of platform with allied works for Augmentation of Tilabaid (Zone - F) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000487/2023-2024 | 2339/BQA | 14/08/2023 | 10/05/2024 | PARTHA PRATIM CHHATAIT | 213.98 | 0 | 0 | 0
3 | BANKURA |  | Bankura Division | Augmentation works for 86 Nos. Mouzas of Saltora Block 07 nos Zone (06 nos OHR & Direct Zone- 1) under Saltora- Chhatna Water Supply Scheme (BRGF ph - I project). | SM/18423 | Augmentation | Support service for detail surveying, cross checking of abailable LOP and taking level at the interval of 50 mtr. by using Survey Instrument like DGPS / Drone and detailed design of pipe line by using Watergems Software on the basis of population density for Augmentation works for Chinabari (Zone-H) under Saltora- Chhatna water Supply Scheme (BRGF Ph-I project) of Bankura Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000851/2023-2024 | 2977/BQA | 31/10/2023 | 30/11/2023 | GEO SOLUTION | 2.09 | 0 | 0 | 0
4 | BANKURA |  | Bankura Mechanical | Augmentation works for 86 Nos. Mouzas of Saltora Block 07 nos Zone (06 nos OHR & Direct Zone- 1) under Saltora- Chhatna Water Supply Scheme (BRGF ph - I project). | SM/18423 | Augmentation | Acceptance cum Formal work order for the work of Supply delivery and fitting fixing of Pump spares of VT pumps at Intake pumping station at Kukrakuri under Chhatna, Saltora Block Sub-Surface Water Based Piped Water Supply Scheme (BRGF Phase-I) under Bankura Mechanical Division, P.H.E. Dte. Block: Saltora, Dist- Bankura. | Assistant Engineer | Junior Engineer | ORD/000310/2023-2024 | 1409/BMD | 18/07/2023 | 16/09/2023 | ORIENTAL ENGINEERING CO. | 110.62 | 105.21 | 95.11 | 95
5 | BANKURA |  | Bankura Division | Augmentation works for 86 Nos. Mouzas of Saltora Block 07 nos Zone (06 nos OHR & Direct Zone- 1) under Saltora- Chhatna Water Supply Scheme (BRGF ph - I project). | SM/18423 | Augmentation | Creation of Balance FHTC (Functional House Hold Tap Connection), construction of platform with allied works for Augmentation of Udaypur (Zone - B) & Routora (Zone - A) under Saltora- Chhatna Block W/S Scheme (BRGF Ph - I project) under Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000489/2023-2024 | 2341/BQA | 14/08/2023 | 10/05/2024 | PARTHA PRATIM CHHATAIT | 164.04 | 35.08 | 21.38 | 22
6 | BANKURA |  | Bankura Division | Augmentation works for 86 Nos. Mouzas of Saltora Block 07 nos Zone (06 nos OHR & Direct Zone- 1) under Saltora- Chhatna Water Supply Scheme (BRGF ph - I project). | SM/18423 | Augmentation | Support service for detail surveying, cross checking of abailable LOP and taking level at the interval of 50 mtr. by using Survey Instrument like DGPS / Drone and detailed design of pipe line by using Watergems Software on the basis of population density for Augmentation works for Manipur (Zone-D) under Saltora- Chhatna water Supply Scheme (BRGF Ph-I project) of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000850/2023-2024 | 2976/BQA | 31/10/2023 | 30/11/2023 | MEASURE LAND | 2.09 | 1.84 | 88.16 | 100
7 | BANKURA |  | Bankura Division | Augmentation works for 86 Nos. Mouzas of Saltora Block 07 nos Zone (06 nos OHR & Direct Zone- 1) under Saltora- Chhatna Water Supply Scheme (BRGF ph - I project). | SM/18423 | Augmentation | Design Making & Erection of Disply board using Logo and tag line of Jal Jeevan Mission to the place at different work sites at Ranagora (147), Kanki (150), Bandayagal (156), Bindajam (157) & Khudrabanagram (159) of Swajal Gram/Har Ghar Jal Villages for awarness generation among the pepole of Bankura Sadar Sub- Division under Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001057/2023-2024 | 1173/BSD | 22/11/2023 | 07/12/2023 | TAPAS DEY | 0.69 | 0.68 | 97.77 | 100
8 | BANKURA |  | Bankura Mechanical | Augmentation works for 86 Nos. Mouzas of Saltora Block 07 nos Zone (06 nos OHR & Direct Zone- 1) under Saltora- Chhatna Water Supply Scheme (BRGF ph - I project). | SM/18423 | Augmentation | Acceptance cum Formal work order for the work of Supply delivery and fitting fixing of Pump spares of HSC pumps at clear water pumping station at Kukrakuri under Chhatna, Saltora Block Sub-Surface Water Based Piped Water Supply Scheme (BRGF Phase-I) under Bankura Mechanical Division, P.H.E. Dte. Block: Saltora, Dist- Bankura | Assistant Engineer | Junior Engineer | ORD/000307/2023-2024 | 1408/BMD | 18/07/2023 | 10/09/2024 | ORIENTAL ENGINEERING CO. | 216.67 | 206.36 | 95.24 | 95
9 | BANKURA |  | Bankura Division | Augmentation works for 86 Nos. Mouzas of Saltora Block 07 nos Zone (06 nos OHR & Direct Zone- 1) under Saltora- Chhatna Water Supply Scheme (BRGF ph - I project). | SM/18423 | Augmentation | Support service for detail surveying, cross checking of abailable LOP and taking level at the interval of 50 mtr. by using Survey Instrument like DGPS / Drone and detailed design of pipe line by using Watergems Software on the basis of population density for Udaypur (Zone- B) of Augmentation works for 86 Nos. Mouzas of Saltora Block 07 nos Zone (06 nos OHR & Direct Zone- 1) under Saltora- Chhatna Water Supply Scheme (BRGF ph - I project) of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000075/2024-2025 | 1496/BQA | 18/06/2024 | 18/07/2024 | MESAURE LAND | 2.52 | 0 | 0 | 80
10 | BANKURA |  | Bankura Division | Augmentation works for 86 Nos. Mouzas of Saltora Block 07 nos Zone (06 nos OHR & Direct Zone- 1) under Saltora- Chhatna Water Supply Scheme (BRGF ph - I project). | SM/18423 | Augmentation | Crossing PWD Road by different dia MS pipe by trench less Technologies i.e Jack Pushing method with MS Carrier pipe and all alled works at Chandra More of HORAKA (Zone - G) under Augmentation works for 86 Nos. Mouzas of Saltora Block 07 nos Zone (06 nos OHR & Direct Zone- 1) under Saltora- Chhatna Water Supply Scheme (BRGF ph - I project) under Bankura Division, PHE Dte. | Assistant Engineer |  | ORD/001395/2024-2025 | 42/BQA | 02/01/2025 | 16/02/2025 | PARAMESWAR CHOWDHURY | 4.65 | 0 | 0 | 0
11 | BANKURA |  | Bankura Mechanical | Augmentation works for 86 Nos. Mouzas of Saltora Block 07 nos Zone (06 nos OHR & Direct Zone- 1) under Saltora- Chhatna Water Supply Scheme (BRGF ph - I project). | SM/18423 | Augmentation | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Pabra piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block : Saltora , Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000018/2025-2026 | 153/BMD | 30/04/2025 | 29/07/2025 | M/S DAS AND SARKAR ENTERPRISE | 9.72 | 0 | 0 | 0
12 | BANKURA |  | Bankura Division | Augmentation works for 86 Nos. Mouzas of Saltora Block 07 nos Zone (06 nos OHR & Direct Zone- 1) under Saltora- Chhatna Water Supply Scheme (BRGF ph - I project). | SM/18423 | Augmentation | Creation of Balance FHTC (Functional House Hold Tap Connection) & Laying of balance distribution system of pipeline with allied works for Augmentation of Ranjitpur (Zone - C) under Saltora- Chhatna Block W/S Scheme (BRGF Ph - I project) under Jal Jeevan Mission under Bankura Division, P.H.E. Dte. Block - Saltora, Name of OHR - Ranjitpur, Total House Hold - 150 nos | Assistant Engineer |  | ORD/000160/2025-2026 | 1301/BQA | 17/06/2025 | 01/08/2025 | GOURANGA NANDI | 28.74 | 0 | 0 | 0
Total | [13 empty] | 897.87 | 349.17 | 38.89