## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Augmentation works for Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas under Jal Jeevan Mission Programme | SM/18424 | Augmentation | Work Order for Repairing of Collecting line with other allied works of Lakshmisagar Water Supply Scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000453/2023-2024 | 261/KSD | 24/08/2023 | 31/08/2023 | S.S. CONSTRUCTION | 0.97 | 0 | 0 | 0
2 | BANKURA |  | Bankura Division | Augmentation works for Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas under Jal Jeevan Mission Programme | SM/18424 | Augmentation | Sinking of 4 (Four) Nos. 200 mm dia. X 4.50 Mtr. depth horizontal river bed tube well, using MS "T" and Laying, fitting & fixing 100 mm dia M.S collecting line from river bed tube well to CWR with allied works for in connection with Augmentation of Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001155/2023-2024 | 359/BQA | 06/02/2024 | 07/03/2024 | SIBSANKAR CHOWDHURY | 50.22 | 33.75 | 67.21 | 45
3 | BANKURA |  | Bankura Division | Augmentation works for Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas under Jal Jeevan Mission Programme | SM/18424 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000184/2023-2024 | 116/BQA | 10/01/2024 | 10/01/2024 | Resource Division | 2.03 | 0 | 0 | 0
4 | BANKURA |  | Bankura Mechanical | Augmentation works for Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas under Jal Jeevan Mission Programme | SM/18424 | Augmentation | Augmentation works for Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas under Jal Jeevan Mission Programme |  |  | BILL/01661/2023-2024 | BP-2023-24-175 | 22/03/2024 | 22/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 6.19 | 0 | 0 | 0
5 | BANKURA |  | Bankura Division | Augmentation works for Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas under Jal Jeevan Mission Programme | SM/18424 | Augmentation | Sinking of 1 No. 200mm X 165 mm dia.X 240 mtr. deep Rig Bore Tube Well (by DTH Rig machine) and Construction & commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in different mouzas in connection with Augmentation of Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer (Contractual) | ORD/000516/2023-2024 | 2453/BQA | 28/08/2023 | 02/04/2026 | GOUTAM BHOWMIK | 93.63 | 35.43 | 37.84 | 20
6 | BANKURA |  | Bankura Mechanical | Augmentation works for Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas under Jal Jeevan Mission Programme | SM/18424 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of pumping machineries and other electromechanical accessories for Augmentation works for Augmentation of piped water supply scheme for Lakshmisagar and its adjoining mouzas under Jal Jeevan mission programe under Bankura Mechanical Division, P.H.E. Dte | Driller-in-Charge | Junior Engineer | ORD/000618/2023-2024 | 2090/BMD | 12/09/2023 | 10/01/2024 | MAHADEV ENTERPRISE | 86.97 | 0 | 0 | 13
7 | BANKURA |  | Bankura Mechanical | Augmentation works for Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas under Jal Jeevan Mission Programme | SM/18424 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of pumping machineries and other electromechanical accessories in boosting site and HWS site for Augmentation works for Piped Water Supply Scheme for Lakshmisagar and Its Adjoining Mouzas under Jal Jeevan Mission Programme under under Bankura Mechanical Division, P.H.E. Dte | Driller-in-Charge | Junior Engineer | ORD/000145/2024-2025 | 488/BMD | 09/07/2024 | 06/11/2024 | MAHADEV ENTERPRISE | 54.94 | 0 | 0 | 23
8 | BANKURA |  | Bankura Division | Augmentation works for Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas under Jal Jeevan Mission Programme | SM/18424 | Augmentation | Sinking of 3 Nos. 300 mm X 200 mm X 200 m deep Tubewell by Rig boring method including interconnection with 100 mm dia. G.I. Pipe and Construction of 3 Nos. Pump Houses with ancillary works, Laying of HDPE pipeline and Construction of Valve Chamber with all allied works in connection with Augmentation of Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas under Jal Jeevan Mission under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000062/2024-2025 | 1485/BQA | 18/06/2024 | 02/08/2024 | S B ASSOCIATES | 96.61 | 0 | 0 | 80
9 | BANKURA |  | Bankura Division | Augmentation works for Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas under Jal Jeevan Mission Programme | SM/18424 | Augmentation | Repairing and painting of 2 Nos. Over Head Reservoir (Capacity 450 Cum. & 350 Cum., staging height 20 Mtr.) including by pass arrangement, construction of boundary wall (OHR site Zone- I & II, Intake site), repairing of CWR, pump house, WBSEDCL room, guard room with all other allied woorks for Augmentation of Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas (Zone-I & II) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer |  | ORD/001770/2024-2025 | 493/BQA | 25/02/2025 | 26/04/2025 | BEAUTY CHATTERJEE | 39.16 | 0 | 0 | 0
10 | BANKURA |  | Bankura Division | Augmentation works for Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas under Jal Jeevan Mission Programme | SM/18424 | Augmentation | Laying additional pipeline in connection with Augmentation works for Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000186/2025-2026 | 1324/BQA | 17/06/2025 | 01/08/2025 | GOUTAM BHOWMIK | 18.24 | 0 | 0 | 0
Total | [13 empty] | 448.97 | 69.18 | 15.41