## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐III/B WATER SUPPLY SCHEME | SM/18495 | Augmentation | Work Order for Preparation of Detailed Project Report for Agumentation of Mukutmanipur-Khatra-Ranibandh Water Supply Scheme, Block : Khatra, District : Bankura Under Jal Swapna Project under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Zone-3B) (Sl. No. 06) | Assistant Engineer |  | ORD/001164/2022-2023 | 184\KSD | 24/05/2022 | 08/06/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.62 | 3.62 | 100 | 100
2 | BANKURA |  | Bankura Division | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐III/B WATER SUPPLY SCHEME | SM/18495 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000043/2022-2023 | 79BQA | 06/01/2023 | 06/01/2023 | Resource Division | 49.27 | 0 | 0 | 0
3 | BANKURA |  | Bankura Division | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐III/B WATER SUPPLY SCHEME | SM/18495 | Augmentation | Construction of Chlorine Room at OHR Site for Mukutmanipur, Khatra & Ranibandh (Zone- III/B) Water Supply Scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000189/2024-2025 | 1860/BQA | 12/07/2024 | 10/10/2024 | TAPAS DEY | 4.62 | 0 | 0 | 0
4 | BANKURA |  | Bankura Division | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐III/B WATER SUPPLY SCHEME | SM/18495 | Augmentation | SOIL INVESTIGATION FOR PIPED WATER SUPPLY SCHEME OF DIFERENT PLACES UNDER JJM WITH IN KHATRA SUB DIVITION OF BANKURA DISTRICT UNDER BANKURA DIVISION, PHE DTE. | Assistant Engineer | Junior Engineer | ORD/000403/2022-2023 | 643/BQA | 24/03/2023 | 23/04/2023 | P. K. TEWARY DRILLING CO | 8.41 | 0.84 | 10 | 99
5 | BANKURA |  | Bankura Division | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐III/B WATER SUPPLY SCHEME | SM/18495 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000204/2023-2024 | 116/BQA | 10/01/2024 | 10/01/2024 | Resource Division | 24.58 | 0 | 0 | 0
6 | BANKURA |  | Bankura Division | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐III/B WATER SUPPLY SCHEME | SM/18495 | Augmentation | Supplying, laying, fitting, fixing and jointing of HDPE pipeline of distribution system with allied works, providing ¿FHTC (Functional House Hold Tap Connection)¿ and Construction of 500 m³ capacity R.C.C OHR (based on Departmental Design) with 20 mtr staging height including foundation, pipeline connection and cost of pipes, specials etc. with allied worksfor Mukutmanipur, Khatra & Ranibundh (Zone- III/B) Water Supply Scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000492/2023-2024 | 2344/BQA | 14/08/2023 | 02/01/2026 | GOPAL CHANDRA CHOWDHURY | 659.32 | 0 | 0 | 30
7 | BANKURA |  | Bankura Division | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐III/B WATER SUPPLY SCHEME | SM/18495 | Augmentation | Laying additional HDPE pipeline, supply of sluice valve, construction of valve chamber under Augmentation of Mukutmanipur, Khatra & Ranibundh Water Supply Scheme (Zone-III/B) under Jal Jeevan Mission programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000173/2025-2026 | 1309/BQA | 17/06/2025 | 18/10/2025 | GOPAL CHANDRA CHOWDHURY | 64.96 | 0 | 0 | 0
8 | BANKURA |  | Bankura Division | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐III/B WATER SUPPLY SCHEME | SM/18495 | Augmentation | "Crossing of Road at different location by Jack pushing method (600 mm dia RCC Hume pipes for casing pipe) for Distribution Main for Mukutmanipur, Khatra & Ranibundh (Zone- III/B) Water Supply Scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Location of site: (1) At Karali More, (2) Near Dedua Bridge & (3) Near SDO Office More" | Assistant Engineer | Junior Engineer | ORD/001966/2024-2025 | 686/BQA | 12/03/2025 | 02/01/2026 | GOPAL CHANDRA CHOWDHURY | 23.62 | 0 | 0 | 0
Total | [13 empty] | 838.4 | 4.46 | 0.53