## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA | Patrasayer | Bankura Division | Ghora Danga Piped Water Supply Scheme | SM/18611 | New | Material Requisition To Resource Division |  |  | RTOR000019/2023-2024 | 1120/BQA | 12/05/2023 | 12/05/2023 | Resource Division | 155.44 | 0 | 0 | 0
2 | BANKURA | Patrasayer | Bankura Division | Ghora Danga Piped Water Supply Scheme | SM/18611 | New | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR GHORA DANGA PIPED WATER SUPPLY SCHEME, BLOCK- PATRASAYER, DIST- BANKURA UNDER JJM INCLUDING TRIAL RUN FOR 3 MONTHS AND O&M FOR A PERIOD OF 3 YEARS UNDER BANKURA DIVISION,PHE DTE. | Assistant Engineer | Junior Engineer | ORD/000479/2023-2024 | 2334/BQA | 14/08/2023 | 01/10/2025 | BAJRANG ROAD CONSTRUCTION PRIVATE LIMITED | 648.29 | 120.46 | 18.58 | 60
3 | BANKURA | Patrasayer | Bankura Division | Ghora Danga Piped Water Supply Scheme | SM/18611 | New | Instalation of scheme information board for 2 nos. sites of Ghora Danga Piped Water Supply Scheme (SM/18611), 2 nos. of Mukundapur Piped Water Supply Scheme (SM/14006) & 2 nos. of Jamkuri Piped Water Supply Scheme (SM/14007) within Patrasayer Block under Bishnupur Sub-Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001888/2024-2025 | 566/VSD | 27/09/2024 | 12/10/2024 | PARTHA ROY | 0.9 | 0 | 0 | 0
4 | BANKURA | Patrasayer | Bankura Mechanical | Ghora Danga Piped Water Supply Scheme | SM/18611 | New | New service connection for Ghoradanga (T/W-II) water supply scheme under BMD PHE Dte.(SM/18611) |  |  | BILL/01464/2024-2025 | BP-2024-25-360 | 07/02/2025 | 07/02/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.96 | 0 | 0 | 0
5 | BANKURA | Patrasayer | Bankura Mechanical | Ghora Danga Piped Water Supply Scheme | SM/18611 | New | New service connection for ghoradanga(T/W-I) water supply scheme under BMD PHE Dte.(SM/18611) |  |  | BILL/01356/2024-2025 | BP-2024-25-327 | 13/01/2025 | 13/01/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.75 | 0 | 0 | 0
6 | BANKURA | Patrasayer | Bankura Division | Ghora Danga Piped Water Supply Scheme | SM/18611 | New | Restoration work of MRL09- Ranpur to Belut under Patrasayer Block, PACKAGE NO.-WB-03-844 under PMGSY-III of Length 1,685.00 Mtr. due to laying of pipeline of Ghoradanga PWSS [SM/18611] by Bankura Division. PHE Dte. |  |  | BILL/01417/2025-2026 |  | 09/09/2025 | 09/09/2025 | EXECUTIVE ENGINEER & HPIU WBSRDA BISHNUPUR DIVISION | 9.64 | 0 | 0 | 0
7 | BANKURA | Patrasayer | Bankura Mechanical | Ghora Danga Piped Water Supply Scheme | SM/18611 | New | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro mechanical accessories for newly sunk TW No I, TW No II of Ghora danga Piped water supply scheme Block Patrashayar under Bankura Mechanical Division, PHE Dte. Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000114/2024-2025 | 425/BMD | 27/06/2024 | 17/02/2026 | RAJIB COMPANY | 50.06 | 0 | 0 | 30
Total | [13 empty] | 873.06 | 120.46 | 13.8