## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Augmentation of Intake, WTP & Rising main for Surface Water based Piped Water Supply Scheme for Mukutmanipur, Khatra & Ranibundh | SM/18612 | Augmentation | Surveying, Planning, Designing, Delivery, Erection, Construction, Commissioning and Completion in all respect of all Civil , Mechanical and Electrical works ( excluding Supply and Installation of Raw Water Pumps, Clear Water High Lift Pumps , Motors, Panels, Electrical Substation and allied works, Chlorination arrangement, SCADA and Yard Lighting including related works ) including all allied , related and enabling works of Fixed type Intake Jetty with pump house, Access Bridge, Laying of Raw Water Rising Main, Bank Protection, Construction of Sub-station Building, Clear Water Pump House and 5 MLD capacity Water Treatment (WTP) based on conventional technologies with 20% overloading on EPC/ Turnkey basis in a single package for Augmentation of Mukutmanipur, Khatra & Ranibandh Piped Water Supply Scheme under Bankura Division, PHE Dte. , Dist - Bankura with impounded surface water of Kangsabati Dam at Mukutmanipur as source of water followed by 03(Three) months of Trial Run and subsequent Operation & Maintenance for 03(Three) years. | Assistant Engineer |  | ORD/000964/2023-2024 | 3479/BQA | 21/12/2023 | 13/06/2025 | CONCORD ENGINEERING | 3377.5 | 0 | 0 | 0
2 | BANKURA |  | Bankura Division | Augmentation of Intake, WTP & Rising main for Surface Water based Piped Water Supply Scheme for Mukutmanipur, Khatra & Ranibundh | SM/18612 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000155/2023-2024 | 112/BQA | 10/01/2024 | 10/01/2024 | Resource Division | 1295.36 | 0 | 0 | 0
3 | BANKURA |  | Bankura Division | Augmentation of Intake, WTP & Rising main for Surface Water based Piped Water Supply Scheme for Mukutmanipur, Khatra & Ranibundh | SM/18612 | Augmentation | Laying Rising Main using different dia D.I - K9 pipes from WTP to Existing ESRs & Proposed OHRs at Mukutmanipur, Khatra & Ranibundh under Augmentation of Surface Water Based Piped Water Supply Scheme for Mukutmanipur, Khatra & Ranibandh under Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000737/2023-2024 | 2741/BQA | 04/10/2023 | 02/04/2025 | SWAPAN KUMAR UPADHYAY | 217.09 | 11.72 | 5.4 | 20
4 | BANKURA |  | Bankura Mechanical | Augmentation of Intake, WTP & Rising main for Surface Water based Piped Water Supply Scheme for Mukutmanipur, Khatra & Ranibundh | SM/18612 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of pumping machineries and other electro-mechanical accessories for at new intake for Augmentation of Intake WTP & rising main for surface water based piped water supply scheme Mukutmanipur, Khatra, & Ranibandh under Bankura Mechanical Division, P.H.E Dte. Dist: Bankura | Driller-in-Charge | Estimator | ORD/000634/2024-2025 | 1475/BMD | 10/01/2025 | 10/05/2025 | DEBJYOTI BASU | 107.35 | 0 | 0 | 0
5 | BANKURA |  | Bankura Mechanical | Augmentation of Intake, WTP & Rising main for Surface Water based Piped Water Supply Scheme for Mukutmanipur, Khatra & Ranibundh | SM/18612 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of pumping machineries and other electromechanical accessories for new WTP for Augmentation of Intake WTP and rising main for surface water based piped water supply scheme Mukutmanipur, Khatra, and Ranibandh under Bankura Mechanical Division, P.H.E Dte. Dist Bankura | Driller-in-Charge | Estimator | ORD/000001/2025-2026 | 95/BMD | 23/04/2025 | 21/08/2025 | M/S P.P ELECTRICALS | 314.08 | 0 | 0 | 0
6 | BANKURA |  | Bankura Mechanical | Augmentation of Intake, WTP & Rising main for Surface Water based Piped Water Supply Scheme for Mukutmanipur, Khatra & Ranibundh | SM/18612 | Augmentation | Acceptance cum Formal work order for the work of Providing Yard lighting arrangement at new WTP site for Augmentation of Intake WTP and rising main for surface water based piped water supply scheme Mukutmanipur, Khatra, and Ranibandh under Bankura Mechanical Division, P.H.E Dte. Dist Bankura (2nd Call) | Driller-in-Charge | Estimator | ORD/000872/2024-2025 | 2035/BMD | 07/03/2025 | 02/11/2025 | UNITED TRADERS | 14 | 0 | 0 | 60
Total | [13 empty] | 5325.38 | 11.72 | 0.22