## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA | Patrasayer | Bankura Division | Biur Piped Water Supply Scheme | SM/18754 | New | Material Requisition To Resource Division |  |  | RTOR000023/2023-2024 | 1120/BQA | 12/05/2023 | 12/05/2023 | Resource Division | 101.52 | 0 | 0 | 0
2 | BANKURA | Patrasayer | Bankura Mechanical | Biur Piped Water Supply Scheme | SM/18754 | New | Biur Piped Water Supply Scheme |  |  | BILL/01672/2023-2024 | BP-2023-24-174 | 22/03/2024 | 22/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.28 | 0 | 0 | 0
3 | BANKURA | Patrasayer | Bankura Division | Biur Piped Water Supply Scheme | SM/18754 | New | Supply, delivery, construction, commissioning and completion of all civil works including all allied, related and enabling works for Biur piped water supply scheme, Block- Patrasayer, Dist- Bankura under JJM including trial run for 3 months and O&M for a period of 3 years under Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000819/2023-2024 | 2928/BQA | 26/10/2023 | 27/05/2025 | DEBAKI RANJAN SARKAR | 793.67 | 0 | 0 | 50
4 | BANKURA | Patrasayer | Bankura Mechanical | Biur Piped Water Supply Scheme | SM/18754 | New | Acceptance cum Formal work order for the work of Providing, installation of Pumping machinery with other electro mechanical accessories for newly sunk at TW No I and T.W No II of Biur piped water supply scheme Block Patrashayar under Bankura Mechanical Division, PHE Dte. Dist Bankura | Assistant Engineer | Junior Engineer | ORD/000113/2024-2025 | 424/BMD | 27/06/2024 | 22/06/2025 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 49.86 | 0 | 0 | 33
Total | [13 empty] | 948.33 | 0 | 0