## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA | Kotulpur | Bankura Division | Baragaria Piped Water Supply Scheme | SM/18789 | New | Material Requisition To Resource Division |  |  | RTOR000028/2023-2024 | 1120/BQA | 12/05/2023 | 12/05/2023 | Resource Division | 139.21 | 0 | 0 | 0
2 | BANKURA | Kotulpur | Bankura Mechanical | Baragaria Piped Water Supply Scheme | SM/18789 | New | New service connection at P/H-I of Barageria W/S scheme |  |  | BILL/00422/2024-2025 | BP-2024-25-99 | 21/06/2024 | 21/06/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.36 | 0 | 0 | 0
3 | BANKURA | Kotulpur | Bankura Mechanical | Baragaria Piped Water Supply Scheme | SM/18789 | New | New service connection charge at P/H-II of Bargeria W/S scheme |  |  | BILL/00530/2024-2025 | BP-2024-25-139 | 25/07/2024 | 25/07/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 6.79 | 0 | 0 | 0
4 | BANKURA | Kotulpur | Bankura Division | Baragaria Piped Water Supply Scheme | SM/18789 | New | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR BARAGARIA PIPED WATER SUPPLY SCHEME, BLOCK- KOTULPUR, DIST- BANKURA UNDER JJM INCLUDING TRIAL RUN FOR 3 MONTHS AND O&M FOR A PERIOD OF 3 YEARS UNDER BANKURA DIVISION,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000755/2023-2024 | 2743/BQA | 04/10/2023 | 27/03/2025 | GOPAL CHANDRA CHOWDHURY | 962.3 | 301.37 | 31.32 | 65
5 | BANKURA | Kotulpur | Bankura Division | Baragaria Piped Water Supply Scheme | SM/18789 | New | Restoration of work (for temporary & final closer) of a ghogh over the left Bank of the Kotulpur Branch Canal Below the PHE pipe line in between ch. 600.00 to 615.00 in Mouza-Hariharchak, G.P- Mirjapur, P.S & Block;- Kotulpur, dist:- Bankura under the Executive Engineer of Bankura Division, Public Health Engineering Directorate and of Kangsabati Canals Division No.-III, Bishnupur in connection with the Work ¿Supply, Delivery, Construction,Commissioning and Completion of all civil works including all allied, related and enabling works for Baragaria piped water supply scheme, Block- Kotulpur, Dist Bankura under JJM including trial run for 3 months and O&M for a period of 3 years under Bankura Division, PHE Dte.'' | Assistant Engineer | Junior Engineer | ORD/000131/2025-2026 | 1292/BQA | 17/06/2025 | 12/07/2025 | SOUMEN KHAN | 11.77 | 0 | 0 | 90
6 | BANKURA | Kotulpur | Bankura Mechanical | Baragaria Piped Water Supply Scheme | SM/18789 | New | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for newly sunk TW No-I, TW No-II & TW No-III of Baragaria Piped water supply scheme Block : Kotulpur under Bankura Mechanical Division, PHE Dte. Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000105/2023-2024 | 2066/BMD | 11/09/2023 | 26/08/2026 | M/S SOMA ENTERPRISES | 68.06 | 34.69 | 50.98 | 37
7 | BANKURA | Kotulpur | Bankura Division | Baragaria Piped Water Supply Scheme | SM/18789 | New | Balanced ancillary works for Barageria Water Supply Scheme under Joypur Block under Bishnupur Sub-Division of Bankura Division, P.H.E. Dte. (SM/18789) | Assistant Engineer | Junior Engineer | ORD/001960/2024-2025 | 695/BQA | 12/03/2025 | 01/04/2026 | GOPAL CHANDRA CHOWDHURY | 231.66 | 0 | 0 | 80
Total | [13 empty] | 1424.14 | 336.06 | 23.6