## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA | Kotulpur | Bankura Division | Panahar Piped Water Supply Scheme | SM/18790 | New | Material Requisition To Resource Division |  |  | RTOR000024/2023-2024 | 1120/BQA | 12/05/2023 | 12/05/2023 | Resource Division | 111.45 | 0 | 0 | 0
2 | BANKURA | Kotulpur | Bankura Mechanical | Panahar Piped Water Supply Scheme | SM/18790 | New | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for newly sunk TW No-I, TW No-II & TW No-III of Panahar piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block : Kotulpur , Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000167/2023-2024 | 2065/BMD | 11/09/2023 | 09/03/2024 | PROGRESSIVE ENGINEERS CO-OPERATIVE SOCIETY LIMITED | 59.03 | 27.3 | 46.25 | 46
3 | BANKURA | Kotulpur | Bankura Mechanical | Panahar Piped Water Supply Scheme | SM/18790 | New | New service connection connection at P/H no-I of panahar W/S scheme. |  |  | BILL/00528/2024-2025 | BP-2024-25-137 | 25/07/2024 | 25/07/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.8 | 0 | 0 | 0
4 | BANKURA | Kotulpur | Bankura Mechanical | Panahar Piped Water Supply Scheme | SM/18790 | New | New service connection at P/H-III of Panahar W/S scheme |  |  | BILL/00529/2024-2025 | BP-2024-25-138 | 25/07/2024 | 25/07/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 7.99 | 0 | 0 | 0
5 | BANKURA | Kotulpur | Bankura Mechanical | Panahar Piped Water Supply Scheme | SM/18790 | New | New service connection at P/H-III of Panahar W/S scheme |  |  | BILL/00527/2024-2025 | BP-2024-25-136 | 25/07/2024 | 25/07/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 8.18 | 0 | 0 | 0
6 | BANKURA | Kotulpur | Bankura Division | Panahar Piped Water Supply Scheme | SM/18790 | New | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR PANHAR PIPED WATER SUPPLY SCHEME, BLOCK- KOTULPUR, DIST- BANKURA UNDER JJM INCLUDING TRIAL RUN FOR 3 MONTHS AND O&M FOR A PERIOD OF 3 YEARS UNDER BANKURA DIVISION,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000754/2023-2024 | 2742/BQA | 04/10/2023 | 01/01/2026 | GOPAL CHANDRA CHOWDHURY | 806.18 | 277.51 | 34.42 | 85
7 | BANKURA | Kotulpur | Bankura Division | Panahar Piped Water Supply Scheme | SM/18790 | New | Balanced ancillary works for Panahar Water Supply Scheme under Kotulpur Block under Bishnupur Sub-Division of Bankura Division, P.H.E. Dte. (SM/18790) | Assistant Engineer | Junior Engineer | ORD/001946/2024-2025 | 692/BQA | 12/03/2025 | 01/01/2026 | GOPAL CHANDRA CHOWDHURY | 151.31 | 0 | 0 | 85
Total | [13 empty] | 1147.93 | 304.81 | 26.55