## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Mechanical | Water Supply arrangement at Eklavya Model Residential school (EMRS) at Mukutmanipur, Khatra Sub- Division by creating source, Laying Rising Main & Distribution pipeline and Constructing CWR & Pump House | SM/18862 | School | Acceptance cum Formal work order for the work of Providing and installation of pumping machineries installed at CWR of Eklavya Model Residental School (ERMS) at Mukutmanipur, Khatra Sub Division under Bankura in the District of Bankura. | Driller-in-Charge | Estimator | ORD/001054/2023-2024 | 2983/BMD | 01/03/2024 | 30/05/2024 | M/S DAS & SARKAR ENTERPRISE | 4.68 | 4.52 | 96.48 | 100
2 | BANKURA |  | Bankura Division | Water Supply arrangement at Eklavya Model Residential school (EMRS) at Mukutmanipur, Khatra Sub- Division by creating source, Laying Rising Main & Distribution pipeline and Constructing CWR & Pump House | SM/18862 | School | Construction and commissioning of Water Supply arrangement at Eklavya Model Residential school (EMRS) at Mukutmanipur, Khatra Sub- Division by Laying Pumping Main & Distribution pipeline and Constructing CWR & Pump House etc. | Assistant Engineer | Junior Engineer | ORD/000602/2022-2023 | 555./BQA | 17/03/2023 | 02/02/2025 | D. S. ENTERPRISE | 34.27 | 14.93 | 43.55 | 50
Total | [13 empty] | 38.95 | 19.44 | 49.92