## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Mechanical | Augmentation of Water Supply Scheme for Pathardoba, Zone-B and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme | SM/18892 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of pumping machineries and other electromechanical accessories for Augmentation for Pathardoba Zone-B and adjoining mouzas under Simlapal water supply scheme (BRGF Ph-I) under Jal Jeevan Mission progremme under Bankura Mechanical Division PHE Dte, Dist :Bankura. | Driller-in-Charge | Junior Engineer | ORD/000994/2023-2024 | 2854/BMD | 09/02/2024 | 07/08/2025 | PROGRESSIVE ENGINEERS CO-OPERATIVE SOCIETY LIMITED | 134.65 | 89.23 | 66.27 | 65
2 | BANKURA |  | Bankura Division | Augmentation of Water Supply Scheme for Pathardoba, Zone-B and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme | SM/18892 | Augmentation | Support service for detail surveying, cross checking of abailable LOP and taking level at the interval of 50 mtr. by using Survey Instrument like DGPS / Drone and detailed design of pipe line by using Watergems Software on the basis of population density for Augmentation of Water Supply Scheme for Pathardoba, Zone-B and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000832/2023-2024 | 2958/BQA | 31/10/2023 | 30/11/2023 | GEO SOLUTION | 3.54 | 3.53 | 99.65 | 96
3 | BANKURA |  | Bankura Mechanical | Augmentation of Water Supply Scheme for Pathardoba, Zone-B and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme | SM/18892 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of illumination arrangement and installation od new charger panel and other allied works for Augmentation for PATHARDOBA ZONE -B water supply scheme under Simlapal water supply scheme (BRGF Ph-I) under Jal Jeevan Mission progremme under Bankura Mechanical Division PHE Dte, Dist :Bankura. | Driller-in-Charge | Junior Engineer | ORD/000274/2024-2025 | 779/BMD | 20/08/2024 | 26/08/2025 | M/S BIPUL BANERJEE | 18.58 | 0 | 0 | 55
4 | BANKURA |  | Bankura Division | Augmentation of Water Supply Scheme for Pathardoba, Zone-B and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme | SM/18892 | Augmentation | Repairing and painting of Over Head Reservoir (Capacity 350 Cum., staging height 20 Mtr.), Chlorination Room, Guard Room, Boundary Wall and laying distribution pipeline for providing FHTC, Sinking of 4 (Four) Nos. 200 mm dia. X 4.50 Mtr. depth horizontal river bed tube well (Replacement Tubewell), using MS "T" and Laying, Fitting & fixing 100 mm G.I. collecting line from river bed tube well to CWR with all allied works of Augmentation works for Pathardoba, Zone-B water Supply Scheme under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000256/2025-2026 | 1505/BQA | 08/07/2025 | 09/01/2026 | APEX ENTERPRISE | 156.89 | 0 | 0 | 0
5 | BANKURA |  | Bankura Division | Augmentation of Water Supply Scheme for Pathardoba, Zone-B and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme | SM/18892 | Augmentation | Sinking of 2 (Two) Nos. 200 mm dia. X 4.50 Mtr. depth horizontal river bed tube well (Replacement Tubewell), using MS "T" and Laying, Fitting & fixing 100 mm MS collecting line from river bed tube well to CWR with allied works and Construction & commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in different mouzas for Augmentation of Water Supply Scheme for Pathardoba, Zone-B and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer |  | ORD/001611/2024-2025 | 311/BQA | 28/01/2025 | 26/08/2025 | M/S PARAMESWAR CHOWDHURY | 104.47 | 0 | 0 | 0
6 | BANKURA |  | Bankura Mechanical | Augmentation of Water Supply Scheme for Pathardoba, Zone-B and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme | SM/18892 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of Neutralization System other work at Pathardoba Zone -A water supply scheme under BMD PHE Dte | Driller-in-Charge | Junior Engineer | ORD/000192/2025-2026 | 637/BMD | 11/07/2025 | 09/10/2025 | GOPAL CHANDRA CHOWDHURY | 15.72 | 0 | 0 | 0
7 | BANKURA |  | Bankura Division | Augmentation of Water Supply Scheme for Pathardoba, Zone-B and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme | SM/18892 | Augmentation | Repair and Maintenance work of the Road from T02-Banskopa to Jugda under Taldangra Block in the District of Bankura ,Vide Package No- WB-03-435, Road Length-11.49 Km.( Augmentation of water supply scheme for Pathardoba (Zone-B) under Simlapal water supply scheme (BRGF Ph-I) |  |  | BILL/01459/2024-2025 | BP/483/2024-25 | 22/03/2025 | 22/03/2025 | EXECUTIVE ENGINEER & HPIU WBSRDA BISHNUPUR DIVISION | 2.2 | 0 | 0 | 0
8 | BANKURA |  | Bankura Division | Augmentation of Water Supply Scheme for Pathardoba, Zone-B and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme | SM/18892 | Augmentation | Repair and maintenance work of the road from T03-Bagakhnila under Simlapal Block in the district of Bankura vide package No. WB-03-193, Road length - 2.64 Km. (Augmentation of Water Supply Scheme of Pathardoba Zone-B under Simlapal Water Supply Scheme BRGF Phase-I) |  |  | BILL/01468/2024-2025 | BP/483/2024-25 | 22/03/2025 | 22/03/2025 | EXECUTIVE ENGINEER & HPIU WBSRDA BISHNUPUR DIVISION | 1.89 | 0 | 0 | 0
9 | BANKURA |  | Bankura Division | Augmentation of Water Supply Scheme for Pathardoba, Zone-B and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme | SM/18892 | Augmentation | Repair and Maintenance work of the Road from Balarampur - Ramboni under Simlapal Block in the District of Bankura ,Vide Package No- WB-03-188, Road Length-5.702 Km. ( Augmentation of water supply scheme for Pathardoba (Zone-B) under Simlapal water supply scheme (BRGF Ph-l) |  |  | BILL/01467/2024-2025 | BP/483/2024-25 | 22/03/2025 | 22/03/2025 | EXECUTIVE ENGINEER & HPIU WBSRDA BISHNUPUR DIVISION | 0.47 | 0 | 0 | 0
Total | [13 empty] | 438.42 | 92.76 | 21.16