## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Augmentation of Water Supply Scheme for Parsola, Zone-B and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme | SM/18893 | Augmentation | Support service for detail surveying, cross checking of abailable LOP and taking level at the interval of 50 mtr. by using Survey Instrument like DGPS / Drone and detailed design of pipe line by using Watergems Software on the basis of population density for Augmentation of Water Supply Scheme for Parsola Zone - B and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000060/2024-2025 | 1490/BQA | 18/06/2024 | 18/07/2024 | MESAURE LAND | 1.26 | 1.21 | 96.08 | 90
2 | BANKURA |  | Bankura Mechanical | Augmentation of Water Supply Scheme for Parsola, Zone-B and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme | SM/18893 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of pumping machineries and other electromechanical accessories for Augmentation of water supply scheme for Parsola Zone-B and its adjoining mouzas under simlapal water (BRGF Ph-I) under Jal Jeevan Mission progremme under Bankura Mechanical Division PHE Dte, Dist :Bankura | Driller-in-Charge | Junior Engineer | ORD/000991/2023-2024 | 2851/BMD | 09/02/2024 | 11/07/2025 | QUAZI NOZRUL ISLAM | 102.52 | 0 | 0 | 40
3 | BANKURA |  | Bankura Division | Augmentation of Water Supply Scheme for Parsola, Zone-B and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme | SM/18893 | Augmentation | Sinking of 2 (Two) Nos. 200 mm dia. X 4.50 Mtr. depth horizontal river bed tube well, using MS "T" and Laying, Fitting & fixing 100 mm G.I. collecting line from river bed tube well to CWR with allied works and Construction & commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in different mouzas for Augmentation of Water Supply Scheme for Parsola, Zone-B and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001619/2024-2025 | 242/BQA | 21/01/2025 | 01/05/2026 | NAYAN BARDHAN | 133.96 | 0 | 0 | 15
4 | BANKURA |  | Bankura Division | Augmentation of Water Supply Scheme for Parsola, Zone-B and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme | SM/18893 | Augmentation | Sinking of 4 (Four) Nos. 200 mm dia. X 4.50 Mtr. depth horizontal river bed tube well, using MS "T" and Laying, Fitting & fixing 100 mm MS collecting line from river bed tube well to CWR and road crossing of distribution pipeline at different location by trenchless technologies with other allied works of Augmentation of Water Supply Scheme for Parsola, Zone-B and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000179/2025-2026 | 1315/BQA | 17/06/2025 | 18/12/2025 | APEX ENTERPRISE | 42.63 | 0 | 0 | 0
5 | BANKURA |  | Bankura Division | Augmentation of Water Supply Scheme for Parsola, Zone-B and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme | SM/18893 | Augmentation | Repairing and painting of Over Head Reservoir (Capacity 200 Cum., staging height 20 Mtr.), Chlorination Room, Guard Room and Boundary Wall with all allied works of Augmentation works for Parsola, Zone-B water Supply Scheme under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001971/2024-2025 | 667/BQA | 12/03/2025 | 02/12/2025 | PRADIP PATRA | 11.21 | 0 | 0 | 70
Total | [13 empty] | 291.58 | 1.21 | 0.42