## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Mechanical | Augmentation of Water Supply Scheme for Pathardoba, Zone-A and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme | SM/18895 | Augmentation | Augmentation of Water Supply Scheme for Pathardoba, Zone-A and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme |  |  | BILL/01656/2023-2024 | BP-2023-24-172 | 22/03/2024 | 22/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.44 | 0 | 0 | 0
2 | BANKURA |  | Bankura Division | Augmentation of Water Supply Scheme for Pathardoba, Zone-A and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme | SM/18895 | Augmentation | Sinking of 2 (Two) Nos. 200 mm dia. X 4.50 Mtr. depth horizontal river bed tube well (Replacement Tubewell), using MS "T" and Laying, Fitting & fixing 100 mm MS collecting line from river bed tube well to CWR with allied works and Construction & commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in different mouzas for Augmentation of Water Supply Scheme for Pathardoba, Zone-A and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001614/2024-2025 | 233/BQA | 20/01/2025 | 02/04/2026 | GOPAL CHANDRA CHOWDHURY | 244.27 | 0 | 0 | 40
3 | BANKURA |  | Bankura Division | Augmentation of Water Supply Scheme for Pathardoba, Zone-A and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme | SM/18895 | Augmentation | Repairing and painting of Over Head Reservoir (Capacity 500 Cum., staging height 20 Mtr.), High lift Pump House, Operator Room, Clear Water Reservoir, WBSEDCL Room, Chlorination Room, Guard Room and Boundary Wall with all allied works of Augmentation works for Pathardoba, Zone-A water Supply Scheme under Simlapal water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000125/2025-2026 | 1287/BQA | 17/06/2025 | 15/09/2025 | PARESH CHANDRA LAYEK | 18.76 | 0 | 0 | 0
4 | BANKURA |  | Bankura Mechanical | Augmentation of Water Supply Scheme for Pathardoba, Zone-A and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme | SM/18895 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of pumping machineries and other electromechanical accessories for Augmentation for Pathardoba Zone-A and adjoining mouzas under Simlapal water supply scheme (BRGF Ph-I) under Jal Jeevan Mission progremme under Bankura Mechanical Division PHE Dte, Dist :Bankura. | Driller-in-Charge | Junior Engineer | ORD/000993/2023-2024 | 2853/BMD | 09/02/2024 | 29/01/2026 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 135.08 | 114.91 | 85.07 | 70
5 | BANKURA |  | Bankura Division | Augmentation of Water Supply Scheme for Pathardoba, Zone-A and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme | SM/18895 | Augmentation | Support service for detail surveying, cross checking of abailable LOP and taking level at the interval of 50 mtr. by using Survey Instrument like DGPS / Drone and detailed design of pipe line by using Watergems Software on the basis of population density for Augmentation of Water Supply Scheme for Pathardoba Zone - A and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000384/2024-2025 | 2434/BQA | 25/09/2024 | 25/10/2024 | CARTO | 2.53 | 2.48 | 98.31 | 90
Total | [13 empty] | 404.07 | 117.39 | 29.05