## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Drinking water sample collection & testing through Field Test Kits (FTKs Phase-ll)& uploading charges for the samerelated toWater Quality Monitoring & SurveillanceProgrammeUnder Jal Jeevan Mission | SM/19084 | Support-WQMSP | Sample collection, testing by Field Test Kit (FTKs) & data uploadig charges of test results in State Water Quality Dashboard through mobile application as a part of SWACHHA JAL SE SURAKSHA (SJSS) campaign in High School, Primary School, Uper Primary & Sisu Siksha Kendra & Anganwari Centers of 22 blocks within Bankura District under BankuraDivision PHE Dte . | Assistant Engineer |  | ORD/001152/2023-2024 | 362/BQA | 06/02/2024 | 07/03/2024 | TAPAS DEY | 8.28 | 8.28 | 100 | 98
2 | BANKURA |  | Bankura Division | Drinking water sample collection & testing through Field Test Kits (FTKs Phase-ll)& uploading charges for the samerelated toWater Quality Monitoring & SurveillanceProgrammeUnder Jal Jeevan Mission | SM/19084 | Support-WQMSP | Work order for collection of drinking Water samples & uploading charges of field data related to Water Quality Monitoring & Surveillance from where facilitator are not available or inactive under Bankura Sadar Sub Division under Jal Jeevan Mission. (sl. no.-03) | Assistant Engineer | Junior Engineer | ORD/001532/2024-2025 | 277/BK | 27/12/2024 | 27/06/2025 | SONU SINGH | 0.93 | 0 | 0 | 0
3 | BANKURA |  | Bankura Division | Drinking water sample collection & testing through Field Test Kits (FTKs Phase-ll)& uploading charges for the samerelated toWater Quality Monitoring & SurveillanceProgrammeUnder Jal Jeevan Mission | SM/19084 | Support-WQMSP | Work order for collection of drinking Water samples & uploading charges of field data related to Water Quality Monitoring & Surveillance from where facilitator are not available or inactive under Bishnupur Sub Division under Jal Jeevan Mission.(Sl.No.-01) | Assistant Engineer | Junior Engineer | ORD/001530/2024-2025 | 275/BK | 27/12/2024 | 27/06/2025 | TAPAS DEY | 0.93 | 0 | 0 | 45
4 | BANKURA |  | Bankura Division | Drinking water sample collection & testing through Field Test Kits (FTKs Phase-ll)& uploading charges for the samerelated toWater Quality Monitoring & SurveillanceProgrammeUnder Jal Jeevan Mission | SM/19084 | Support-WQMSP | Work order for collection of drinking Water samples & uploading charges of field data related to Water Quality Monitoring & Surveillance from where facilitator are not available or inactive under Khatra Sub Division under Jal Jeevan Mission(sl no-02) | Assistant Engineer | Junior Engineer | ORD/001531/2024-2025 | 276/BK | 27/12/2024 | 27/06/2025 | ABHIRUP MALLA | 0.7 | 0 | 0 | 30
Total | [13 empty] | 10.85 | 8.28 | 76.36