## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA | Sonamukhi | Bankura Division | Nanda Mohanpur Piped Water Supply Scheme | SM/19178 | New | Material Requisition To Resource Division |  |  | RTOR000066/2022-2023 | 79BQA | 06/01/2023 | 06/01/2023 | Resource Division | 250.24 | 0 | 0 | 0
2 | BANKURA | Sonamukhi | Bankura Mechanical | Nanda Mohanpur Piped Water Supply Scheme | SM/19178 | New | Acceptance cum Formal work order for the work of Providing and installation of Electromagnetic flowmeter with motorized Sluice Valve for respective OHR for at Nandamohonpur Piped Water Supply Scheme under BMD PHE Dte Dist-Bankura. | Assistant Engineer | Junior Engineer | ORD/000179/2025-2026 | 452/BMD | 10/06/2025 | 08/09/2025 | M/S BIPUL BANERJEE | 12.36 | 0 | 0 | 0
Total | [13 empty] | 262.59 | 0 | 0