## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Procurement of Chemicals & Consumables, glassware etc. required for smooth running of the different laboratories under Bankura Division, PHE Dte. | SM/19269 | Support-WQMSP | Contuinuation Work Order for Supply of different Chemicals, Reagent, Membrane Filter etc. for 16 nos Water Testing Laboratories of RWS Bankura Sub -Division under Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000304/2024-2025 | 2192/BQA | 14/08/2024 | 24/08/2024 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 10.02 | 0 | 0 | 95
2 | BANKURA |  | Bankura Division | Procurement of Chemicals & Consumables, glassware etc. required for smooth running of the different laboratories under Bankura Division, PHE Dte. | SM/19269 | Support-WQMSP | Supply of different Chemicals, Reagent, Membrane Filter etc. for 16 nos Water Testing Laboratories of RWS Bankura Sub -Division under Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001606/2024-2025 | 350/BQA | 04/02/2025 | 04/02/2026 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 51.55 | 0 | 0 | 90
Total | [13 empty] | 61.57 | 0 | 0