## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Mechanical | Construction of Grid- connection solar photo-voltaic system for Kanaipur pumping station of Panchal PWS scheme,Dist: Bankura. | SM/10271 | IOT | Acceptance cum Formal work order for the work Construction of Grid-connected Solar Photo-voltaic System for Kanaipur Pumping Station of Panchal PWS Scheme, Dist: Bankura. | Assistant Engineer |  | ORD/000075/2022-2023 | 637/BMD | 28/04/2022 | 12/06/2022 | M/S NABIN GOPAL SENGUPTA | 16.5 | 9.23 | 55.93 | 98
Total | [13 empty] | 16.5 | 9.23 | 55.93