## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Mechanical | Construction of Grid-Connected solar photo -voltaic system for Beliatore PWSS scheme, Dist- Bankura | SM/15311 | Solarisation | Application fee ie earnest money for Net meter for Grid-connected solar pv system for Beliatore PWS scheme under BMD ,PHE Dte. (SM/15311) |  |  | BILL/00349/2024-2025 | 1 | 19/09/2024 | 19/09/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.01 | 0 | 0 | 0
2 | BANKURA |  | Bankura Mechanical | Construction of Grid-Connected solar photo -voltaic system for Beliatore PWSS scheme, Dist- Bankura | SM/15311 | Solarisation | NET BILLING Meter quotation bill for Grid connected Solar PV system for Beliator PWS scheme BMD,PHE Dte, to Beliatore CCC, CL.kw30 (SM/15311) |  |  | BILL/01100/2024-2025 | BP-2024-25-248 | 25/10/2024 | 25/10/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.22 | 0 | 0 | 0
3 | BANKURA |  | Bankura Mechanical | Construction of Grid-Connected solar photo -voltaic system for Beliatore PWSS scheme, Dist- Bankura | SM/15311 | Solarisation | Acceptance cum Formal work order for the work of Construction of Grid-connected Solar Photo-voltaic System for Beliatore PWS Scheme under Bankura Mechanical Division PHE Dte. Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000472/2022-2023 | 479/BMD | 23/03/2023 | 02/08/2025 | KINGKINI TRADERS | 15.6 | 0 | 0 | 100
Total | [13 empty] | 15.83 | 0 | 0