## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Mechanical | Construction of Grid-Connected solar photo -voltaic system for Ekteswar PWSS scheme Dist Bankura | SM/15312 | Solarisation | Acceptance cum Formal work order for the work of Construction of Grid-connected Solar Photo-voltaic System for Ekteswar PWS Scheme under Bankura Mechanical Division PHE Dte. Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000473/2022-2023 | 480/BMD | 23/03/2023 | 22/05/2023 | GOENKA ENTERPRISE | 25.01 | 0 | 0 | 88
2 | BANKURA |  | Bankura Mechanical | Construction of Grid-Connected solar photo -voltaic system for Ekteswar PWSS scheme Dist Bankura | SM/15312 | Solarisation | New NET meter connection for on grid solar system at EKTESHWAR water supply scheme at mouza-Sankarhati under BMD PHE Dte. |  |  | BILL/00300/2024-2025 | BP-2024-25-67 | 24/07/2024 | 24/07/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.6 | 0 | 0 | 0
3 | BANKURA |  | Bankura Mechanical | Construction of Grid-Connected solar photo -voltaic system for Ekteswar PWSS scheme Dist Bankura | SM/15312 | Solarisation | New Service connection at Sanbandha of Ekteshwar water supply scheme under BMD PHE Dte. |  |  | BILL/00948/2024-2025 | BP-2024-25-234 | 27/09/2024 | 27/09/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.04 | 0 | 0 | 0
Total | [13 empty] | 25.65 | 0 | 0