## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Mechanical | Construction of Grid-Connected solar photo -voltaic system for Radhanagar PWSS scheme Dist Bankura | SM/15314 | Solarisation | Acceptance cum Formal work order for the work of Construction of Grid-connected Solar Photo-voltaic System for Radhanagar PWS Scheme under Bankura Mechanical Division PHE Dte. Dist: Bankura | Assistant Engineer |  | ORD/000478/2022-2023 | 485/BMD | 23/03/2023 | 22/05/2023 | ABHIJIT MUKHERJEE | 22.25 | 16.4 | 73.71 | 75
2 | BANKURA |  | Bankura Mechanical | Construction of Grid-Connected solar photo -voltaic system for Radhanagar PWSS scheme Dist Bankura | SM/15314 | Solarisation | WBSEDCL Solar Quotation for net Billing of 40 kw solar plant at CWR site Radhanagar W/S scheme |  |  | BILL/00293/2024-2025 | BP-2024-25-66 | 24/07/2024 | 24/07/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.36 | 0 | 0 | 0
Total | [13 empty] | 22.62 | 16.4 | 72.53