## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Mechanical | Construction of Grid-Connected solar photo -voltaic system for Laxmisagar PWSS scheme Dist Bankura | SM/15315 | Solarisation | Acceptance cum Formal work order for the work of Construction of Grid-connected Solar Photo-voltaic System for Laxmisagar PWS Scheme under Bankura Mechanical Division PHE Dte. Dist: Bankura. | Driller-in-Charge | Junior Engineer | ORD/000474/2022-2023 | 481/BMD | 23/03/2023 | 28/05/2023 | M/S DE ENGINEERING CONCERN | 4.73 | 4.34 | 91.75 | 80
2 | BANKURA |  | Bankura Mechanical | Construction of Grid-Connected solar photo -voltaic system for Laxmisagar PWSS scheme Dist Bankura | SM/15315 | Solarisation | Processing charge of the WBSEDCL Application fee of 8kw solar grid-Connected Solar Photo Voltic System for Laxmisagar PWSS Scheme Dist-Bankura |  |  | BILL/00525/2024-2025 | BP-2024-25-148 | 25/07/2024 | 25/07/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.01 | 0 | 0 | 0
3 | BANKURA |  | Bankura Mechanical | Construction of Grid-Connected solar photo -voltaic system for Laxmisagar PWSS scheme Dist Bankura | SM/15315 | Solarisation | Service connection Charges for Net metering installation of 8 KWp solar grid at laxmisagar ws scheme under BMD PHE Dte. |  |  | BILL/01481/2024-2025 | BP-2024-25-372 | 07/02/2025 | 07/02/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.29 | 0 | 0 | 0
Total | [13 empty] | 5.03 | 4.34 | 86.39