## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Mechanical | Construction of Grid-Connected solar photo -voltaic system for Nabakishor PWSS scheme Dist Bankura | SM/15316 | Solarisation | Acceptance cum Formal work order for the work of Construction of Grid-connected Solar Photo-voltaic System for P/H No-I of Nabakishore PWS Scheme under Bankura Mechanical Division PHE Dte. Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000476/2022-2023 | 483/BMD | 23/03/2023 | 22/05/2023 | UNICON | 7.8 | 0 | 0 | 55
Total | [13 empty] | 7.8 | 0 | 0