## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Mechanical | Construction of Grid-Connected solar photo -voltaic system for Sarenga PWSS scheme Dist Bankura | SM/15317 | Solarisation | Acceptance cum Formal work order for the work of Construction of Grid-connected Solar Photo-voltaic System for Sarenga PWS Scheme under Bankura Mechanical Division PHE Dte. Dist: Bankura. | Assistant Engineer,Driller-in-Charge | Junior Engineer | ORD/000022/2023-2024 | 653/BMD | 17/04/2023 | 16/06/2023 | M/S S.S. ENTERPRISE(MURSHIDABAD) | 30.51 | 15.26 | 50.01 | 50
Total | [13 empty] | 30.51 | 15.26 | 50.01