## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Mechanical | Construction of Grid-Connected solar photo -voltaic system for Sanabandh PWSS scheme Dist Bankura | SM/15318 | Solarisation | Acceptance cum Formal work order for the work of Construction of Grid-Connected solar photo -voltaic system for Sonabundh PWS scheme (at new P/H) Dist Bankura | Assistant Engineer | Junior Engineer | ORD/000021/2023-2024 | 652/BMD | 17/04/2023 | 16/06/2023 | ABHIJIT MUKHERJEE | 25.01 | 24.56 | 98.2 | 98
2 | BANKURA |  | Bankura Mechanical | Construction of Grid-Connected solar photo -voltaic system for Sanabandh PWSS scheme Dist Bankura | SM/15318 | Solarisation | Submission Quotation for 45 kwp solar net metering at CWR site of Sanabandh W/S scheme. |  |  | BILL/00286/2024-2025 | BP-2024-25-64 | 24/07/2024 | 24/07/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.13 | 0 | 0 | 0
3 | BANKURA |  | Bankura Mechanical | Construction of Grid-Connected solar photo -voltaic system for Sanabandh PWSS scheme Dist Bankura | SM/15318 | Solarisation | Quotation payment for application of Solar Plant of 14 KWp at NABAKISHORE PH-I water supply scheme under BMD PHE Dte |  |  | BILL/00301/2024-2025 |  | 10/05/2024 | 10/05/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.01 | 0 | 0 | 0
Total | [13 empty] | 25.15 | 24.56 | 97.66