## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Mechanical | Construction of Grid-connected Solar Photo-Voltaic system for Kukrakuri intake pumping station of Chhatna-Saltora PWSS scheme,Dist: Bankura | SM/15330 | Solarisation | Acceptance cum Formal work order for the work of Construction of Grid-connected Solar Photo-Voltaic system for Kukrakuri intake pumping station of Chhatna-Saltora PWSS scheme,Dist Bankura | Assistant Engineer | Junior Engineer | ORD/000527/2023-2024 | 1891/BMD | 17/08/2023 | 04/12/2025 | GOENKA ENTERPRISE | 87.36 | 69.26 | 79.28 | 95
2 | BANKURA |  | Bankura Mechanical | Construction of Grid-connected Solar Photo-Voltaic system for Kukrakuri intake pumping station of Chhatna-Saltora PWSS scheme,Dist: Bankura | SM/15330 | Solarisation | Quotation for Net Billing at 160 kwp Solar Plant at Kukrakuri. Con ID 950012901 |  |  | BILL/00440/2024-2025 | BP-2024-25-110 | 03/07/2024 | 03/07/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.02 | 0 | 0 | 0
3 | BANKURA |  | Bankura Mechanical | Construction of Grid-connected Solar Photo-Voltaic system for Kukrakuri intake pumping station of Chhatna-Saltora PWSS scheme,Dist: Bankura | SM/15330 | Solarisation | Submission of quotation for Net Billing Generation Meter at Kukrakuri Intake .SM /15330 |  |  | BILL/01487/2024-2025 | BP-2024-25-376 | 07/02/2025 | 07/02/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.27 | 0 | 0 | 0
Total | [13 empty] | 87.66 | 69.26 | 79.01