## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Mechanical | Construction of Grid-connected Solar Photo-Voltaic system for Rampur pump house-I of Rampur PWSS scheme,Dist: Bankura | SM/16965 | Solarisation | Acceptance cum Formal work order for the work of Construction of Grid-connected Solar Photo-voltaic System for Rampur Pumping Station P/H No-I of Rampur PWS Scheme under Bankura Mechanical Division PHE Dte. Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000009/2023-2024 | 648/BMD | 17/04/2023 | 16/06/2023 | M/S BIPUL BANERJEE | 4.81 | 3.48 | 72.32 | 72
Total | [13 empty] | 4.81 | 3.48 | 72.32