## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Mechanical | Construction of Grid-connected Solar Photo-voltaic System for Mukutmonipur Pumping Station of Mukutmonipur PWS Scheme, Dist: Bankura. | SM/17238 | Solarisation | Acceptance cum Formal work order for the work of Construction of Grid-connected Solar Photo-voltaic System for Mukutmanipur PWS Scheme under Bankura Mechanical Division PHE Dte. Dist: Bankura. | Assistant Engineer | Estimator | ORD/000016/2023-2024 | 650/BMD | 17/04/2023 | 16/06/2023 | UNITED TRADERS | 49.25 | 0 | 0 | 80
2 | BANKURA |  | Bankura Mechanical | Construction of Grid-connected Solar Photo-voltaic System for Mukutmonipur Pumping Station of Mukutmonipur PWS Scheme, Dist: Bankura. | SM/17238 | Solarisation | Application for Solar Power Plant of 90KWp Solar Power Plant at Mukutmanipur old WTP site [Consumer Id No-942311700 ] under Bankura Mechanical Division P.H.E Dte |  |  | BILL/00436/2024-2025 | BP-2024-25-110 | 21/06/2024 | 21/06/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.02 | 0 | 0 | 0
3 | BANKURA |  | Bankura Mechanical | Construction of Grid-connected Solar Photo-voltaic System for Mukutmonipur Pumping Station of Mukutmonipur PWS Scheme, Dist: Bankura. | SM/17238 | Solarisation | Acceptance cum Formal work order for the work of Construction of Grid-connected Solar Photo-voltaic System for Mukutmanipur PWS Scheme at new WTP site under Bankura Mechanical Division PHE Dte. Dist: Bankura | Driller-in-Charge | Estimator | ORD/001092/2023-2024 | 3067/BMD | 12/03/2024 | 07/03/2025 | M/S INSILICA | 71.69 | 0 | 0 | 100
4 | BANKURA |  | Bankura Mechanical | Construction of Grid-connected Solar Photo-voltaic System for Mukutmonipur Pumping Station of Mukutmonipur PWS Scheme, Dist: Bankura. | SM/17238 | Solarisation | Acceptance cum Formal work order for the work of Provide installation of Zero Export Device with other accessories for Construction of Grid connected Solar Photo voltaic System for Mukutmanipur PWS Scheme under Bankura Mechanical Division PHE Dte. Dist: Bankura | Driller-in-Charge | Estimator | ORD/001083/2023-2024 | 3061/BMD | 12/03/2024 | 10/06/2025 | UNITED TRADERS | 5.5 | 0 | 0 | 100
Total | [13 empty] | 126.46 | 0 | 0