## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Resource | Engagement of Implementation Support Agency (ISA) for implementation of community mobilization and capacity building activities under JJM , Support Activities at Purulia , Bankura , Paschim Midnapore and Jhargram Districts for 6 months . | SM/18998 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Purulia District. | Assistant Engineer | Junior Engineer | ORD/000095/2023-2024 | 2701/RS | 31/08/2023 | 29/02/2024 | KULTIKARI MOTHER TERESA SOCIAL WELFARE SOCIETY | 233.97 | 233.97 | 100 | 99
2 | JHARGRAM |  | Resource | Engagement of Implementation Support Agency (ISA) for implementation of community mobilization and capacity building activities under JJM , Support Activities at Purulia , Bankura , Paschim Midnapore and Jhargram Districts for 6 months . | SM/18998 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Purulia District. | Assistant Engineer | Junior Engineer | ORD/000095/2023-2024 | 2701/RS | 31/08/2023 | 29/02/2024 | KULTIKARI MOTHER TERESA SOCIAL WELFARE SOCIETY | 233.97 | 233.97 | 100 | 99
3 | PASCHIM MEDINIPUR |  | Resource | Engagement of Implementation Support Agency (ISA) for implementation of community mobilization and capacity building activities under JJM , Support Activities at Purulia , Bankura , Paschim Midnapore and Jhargram Districts for 6 months . | SM/18998 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Purulia District. | Assistant Engineer | Junior Engineer | ORD/000095/2023-2024 | 2701/RS | 31/08/2023 | 29/02/2024 | KULTIKARI MOTHER TERESA SOCIAL WELFARE SOCIETY | 233.97 | 233.97 | 100 | 99
4 | PURULIA |  | Resource | Engagement of Implementation Support Agency (ISA) for implementation of community mobilization and capacity building activities under JJM , Support Activities at Purulia , Bankura , Paschim Midnapore and Jhargram Districts for 6 months . | SM/18998 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Purulia District. | Assistant Engineer | Junior Engineer | ORD/000095/2023-2024 | 2701/RS | 31/08/2023 | 29/02/2024 | KULTIKARI MOTHER TERESA SOCIAL WELFARE SOCIETY | 233.97 | 233.97 | 100 | 99
5 | BANKURA |  | Resource | Engagement of Implementation Support Agency (ISA) for implementation of community mobilization and capacity building activities under JJM , Support Activities at Purulia , Bankura , Paschim Midnapore and Jhargram Districts for 6 months . | SM/18998 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM in the districts of the Bankura. | Assistant Engineer | Junior Engineer | ORD/000158/2023-2024 | 3074/RS | 06/10/2023 | 03/04/2024 | KARNAJORA AGNIBINA SEVA SAMITY | 211.88 | 211.88 | 100 | 50
6 | JHARGRAM |  | Resource | Engagement of Implementation Support Agency (ISA) for implementation of community mobilization and capacity building activities under JJM , Support Activities at Purulia , Bankura , Paschim Midnapore and Jhargram Districts for 6 months . | SM/18998 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM in the districts of the Bankura. | Assistant Engineer | Junior Engineer | ORD/000158/2023-2024 | 3074/RS | 06/10/2023 | 03/04/2024 | KARNAJORA AGNIBINA SEVA SAMITY | 211.88 | 211.88 | 100 | 50
7 | PASCHIM MEDINIPUR |  | Resource | Engagement of Implementation Support Agency (ISA) for implementation of community mobilization and capacity building activities under JJM , Support Activities at Purulia , Bankura , Paschim Midnapore and Jhargram Districts for 6 months . | SM/18998 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM in the districts of the Bankura. | Assistant Engineer | Junior Engineer | ORD/000158/2023-2024 | 3074/RS | 06/10/2023 | 03/04/2024 | KARNAJORA AGNIBINA SEVA SAMITY | 211.88 | 211.88 | 100 | 50
8 | PURULIA |  | Resource | Engagement of Implementation Support Agency (ISA) for implementation of community mobilization and capacity building activities under JJM , Support Activities at Purulia , Bankura , Paschim Midnapore and Jhargram Districts for 6 months . | SM/18998 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM in the districts of the Bankura. | Assistant Engineer | Junior Engineer | ORD/000158/2023-2024 | 3074/RS | 06/10/2023 | 03/04/2024 | KARNAJORA AGNIBINA SEVA SAMITY | 211.88 | 211.88 | 100 | 50
9 | BANKURA |  | Resource | Engagement of Implementation Support Agency (ISA) for implementation of community mobilization and capacity building activities under JJM , Support Activities at Purulia , Bankura , Paschim Midnapore and Jhargram Districts for 6 months . | SM/18998 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Jhargram District for the period of 6(Six) months from 01/12/2023 to 31/05/2024. | Assistant Engineer | Junior Engineer | ORD/000197/2023-2024 | 3539/RS | 28/11/2023 | 29/05/2024 | KARNAJORA AGNIBINA SEVA SAMITY | 96.09 | 88.76 | 92.37 | 50
10 | JHARGRAM |  | Resource | Engagement of Implementation Support Agency (ISA) for implementation of community mobilization and capacity building activities under JJM , Support Activities at Purulia , Bankura , Paschim Midnapore and Jhargram Districts for 6 months . | SM/18998 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Jhargram District for the period of 6(Six) months from 01/12/2023 to 31/05/2024. | Assistant Engineer | Junior Engineer | ORD/000197/2023-2024 | 3539/RS | 28/11/2023 | 29/05/2024 | KARNAJORA AGNIBINA SEVA SAMITY | 96.09 | 88.76 | 92.37 | 50
11 | PASCHIM MEDINIPUR |  | Resource | Engagement of Implementation Support Agency (ISA) for implementation of community mobilization and capacity building activities under JJM , Support Activities at Purulia , Bankura , Paschim Midnapore and Jhargram Districts for 6 months . | SM/18998 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Jhargram District for the period of 6(Six) months from 01/12/2023 to 31/05/2024. | Assistant Engineer | Junior Engineer | ORD/000197/2023-2024 | 3539/RS | 28/11/2023 | 29/05/2024 | KARNAJORA AGNIBINA SEVA SAMITY | 96.09 | 88.76 | 92.37 | 50
12 | PURULIA |  | Resource | Engagement of Implementation Support Agency (ISA) for implementation of community mobilization and capacity building activities under JJM , Support Activities at Purulia , Bankura , Paschim Midnapore and Jhargram Districts for 6 months . | SM/18998 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Jhargram District for the period of 6(Six) months from 01/12/2023 to 31/05/2024. | Assistant Engineer | Junior Engineer | ORD/000197/2023-2024 | 3539/RS | 28/11/2023 | 29/05/2024 | KARNAJORA AGNIBINA SEVA SAMITY | 96.09 | 88.76 | 92.37 | 50
13 | BANKURA |  | Resource | Engagement of Implementation Support Agency (ISA) for implementation of community mobilization and capacity building activities under JJM , Support Activities at Purulia , Bankura , Paschim Midnapore and Jhargram Districts for 6 months . | SM/18998 |  | Engagement of Implementation Support Agency (ISA) for Implementation of commudity mobilization & capacity building activities related to House Hold tap connection (FHTC) in Paschim Midnapur district Under Jal Jeevan Mission (JJM) Support Activities. | Assistant Engineer | Junior Engineer | ORD/000221/2023-2024 | 3540/RS | 28/11/2023 | 29/05/2024 | TUBGRAM GRAMMYAK UNNAYAN SAMITY | 250.41 | 250.41 | 100 | 50
14 | JHARGRAM |  | Resource | Engagement of Implementation Support Agency (ISA) for implementation of community mobilization and capacity building activities under JJM , Support Activities at Purulia , Bankura , Paschim Midnapore and Jhargram Districts for 6 months . | SM/18998 |  | Engagement of Implementation Support Agency (ISA) for Implementation of commudity mobilization & capacity building activities related to House Hold tap connection (FHTC) in Paschim Midnapur district Under Jal Jeevan Mission (JJM) Support Activities. | Assistant Engineer | Junior Engineer | ORD/000221/2023-2024 | 3540/RS | 28/11/2023 | 29/05/2024 | TUBGRAM GRAMMYAK UNNAYAN SAMITY | 250.41 | 250.41 | 100 | 50
15 | PASCHIM MEDINIPUR |  | Resource | Engagement of Implementation Support Agency (ISA) for implementation of community mobilization and capacity building activities under JJM , Support Activities at Purulia , Bankura , Paschim Midnapore and Jhargram Districts for 6 months . | SM/18998 |  | Engagement of Implementation Support Agency (ISA) for Implementation of commudity mobilization & capacity building activities related to House Hold tap connection (FHTC) in Paschim Midnapur district Under Jal Jeevan Mission (JJM) Support Activities. | Assistant Engineer | Junior Engineer | ORD/000221/2023-2024 | 3540/RS | 28/11/2023 | 29/05/2024 | TUBGRAM GRAMMYAK UNNAYAN SAMITY | 250.41 | 250.41 | 100 | 50
16 | PURULIA |  | Resource | Engagement of Implementation Support Agency (ISA) for implementation of community mobilization and capacity building activities under JJM , Support Activities at Purulia , Bankura , Paschim Midnapore and Jhargram Districts for 6 months . | SM/18998 |  | Engagement of Implementation Support Agency (ISA) for Implementation of commudity mobilization & capacity building activities related to House Hold tap connection (FHTC) in Paschim Midnapur district Under Jal Jeevan Mission (JJM) Support Activities. | Assistant Engineer | Junior Engineer | ORD/000221/2023-2024 | 3540/RS | 28/11/2023 | 29/05/2024 | TUBGRAM GRAMMYAK UNNAYAN SAMITY | 250.41 | 250.41 | 100 | 50
Total | [13 empty] | 3169.42 | 3140.11 | 99.08