## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Purulia and Bankura districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19232 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM in the districts of the Bankura. | Assistant Engineer | Junior Engineer | ORD/000209/2024-2025 | 3199/RS | 31/12/2024 | 31/03/2025 | KARNAJORA AGNIBINA SEVA SAMITY | 108.74 | 19.05 | 17.52 | 99
2 | PURULIA |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Purulia and Bankura districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19232 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM in the districts of the Bankura. | Assistant Engineer | Junior Engineer | ORD/000209/2024-2025 | 3199/RS | 31/12/2024 | 31/03/2025 | KARNAJORA AGNIBINA SEVA SAMITY | 108.74 | 19.05 | 17.52 | 99
3 | BANKURA |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Purulia and Bankura districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19232 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Purulia District. | Assistant Engineer | Junior Engineer | ORD/000213/2024-2025 | 3189/RS | 30/12/2024 | 30/03/2025 | KULTIKARI MOTHER TERESA SOCIAL WELFARE SOCIETY | 115.02 | 11.47 | 9.98 | 99
4 | PURULIA |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Purulia and Bankura districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19232 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Purulia District. | Assistant Engineer | Junior Engineer | ORD/000213/2024-2025 | 3189/RS | 30/12/2024 | 30/03/2025 | KULTIKARI MOTHER TERESA SOCIAL WELFARE SOCIETY | 115.02 | 11.47 | 9.98 | 99
5 | BANKURA |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Purulia and Bankura districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19232 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Purulia District. | Assistant Engineer | Junior Engineer | ORD/000326/2023-2024 | 737/RS | 04/03/2024 | 04/01/2025 | KULTIKARI MOTHER TERESA SOCIAL WELFARE SOCIETY | 364.96 | 305.18 | 83.62 | 50
6 | PURULIA |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Purulia and Bankura districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19232 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Purulia District. | Assistant Engineer | Junior Engineer | ORD/000326/2023-2024 | 737/RS | 04/03/2024 | 04/01/2025 | KULTIKARI MOTHER TERESA SOCIAL WELFARE SOCIETY | 364.96 | 305.18 | 83.62 | 50
7 | BANKURA |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Purulia and Bankura districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19232 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM in the districts of the Bankura. | Assistant Engineer | Junior Engineer | ORD/000360/2023-2024 | 794/RS | 11/03/2024 | 05/12/2024 | KARNAJORA AGNIBINA SEVA SAMITY | 314.89 | 261 | 82.89 | 50
8 | PURULIA |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at Purulia and Bankura districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19232 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM in the districts of the Bankura. | Assistant Engineer | Junior Engineer | ORD/000360/2023-2024 | 794/RS | 11/03/2024 | 05/12/2024 | KARNAJORA AGNIBINA SEVA SAMITY | 314.89 | 261 | 82.89 | 50
Total | [13 empty] | 1807.22 | 1193.4 | 66.03