## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Resource | Setting up of District Project Management Unit (DPMU) at Purulia, Bankura, Purba & Paschim Medinipur, Jhargram, Howrah, Hooghly, South & North 24 Parganas and nadia districts under Jal Jeevan Mission | SM/19239 |  | Engagement of one consulting agency for Setting up of District Project Management Unit (DPMU) at Howrah, Hooghly, South 24 Parganas, North 24 Parganas andNadiadistricts under Jal Jeevan Mission/ Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000357/2023-2024 | 701/RS | 29/02/2024 | 31/12/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 255.26 | 214.18 | 83.91 | 10
2 | HOOGHLY |  | Resource | Setting up of District Project Management Unit (DPMU) at Purulia, Bankura, Purba & Paschim Medinipur, Jhargram, Howrah, Hooghly, South & North 24 Parganas and nadia districts under Jal Jeevan Mission | SM/19239 |  | Engagement of one consulting agency for Setting up of District Project Management Unit (DPMU) at Howrah, Hooghly, South 24 Parganas, North 24 Parganas andNadiadistricts under Jal Jeevan Mission/ Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000357/2023-2024 | 701/RS | 29/02/2024 | 31/12/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 255.26 | 214.18 | 83.91 | 10
3 | HOWRAH |  | Resource | Setting up of District Project Management Unit (DPMU) at Purulia, Bankura, Purba & Paschim Medinipur, Jhargram, Howrah, Hooghly, South & North 24 Parganas and nadia districts under Jal Jeevan Mission | SM/19239 |  | Engagement of one consulting agency for Setting up of District Project Management Unit (DPMU) at Howrah, Hooghly, South 24 Parganas, North 24 Parganas andNadiadistricts under Jal Jeevan Mission/ Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000357/2023-2024 | 701/RS | 29/02/2024 | 31/12/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 255.26 | 214.18 | 83.91 | 10
4 | JHARGRAM |  | Resource | Setting up of District Project Management Unit (DPMU) at Purulia, Bankura, Purba & Paschim Medinipur, Jhargram, Howrah, Hooghly, South & North 24 Parganas and nadia districts under Jal Jeevan Mission | SM/19239 |  | Engagement of one consulting agency for Setting up of District Project Management Unit (DPMU) at Howrah, Hooghly, South 24 Parganas, North 24 Parganas andNadiadistricts under Jal Jeevan Mission/ Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000357/2023-2024 | 701/RS | 29/02/2024 | 31/12/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 255.26 | 214.18 | 83.91 | 10
5 | NADIA |  | Resource | Setting up of District Project Management Unit (DPMU) at Purulia, Bankura, Purba & Paschim Medinipur, Jhargram, Howrah, Hooghly, South & North 24 Parganas and nadia districts under Jal Jeevan Mission | SM/19239 |  | Engagement of one consulting agency for Setting up of District Project Management Unit (DPMU) at Howrah, Hooghly, South 24 Parganas, North 24 Parganas andNadiadistricts under Jal Jeevan Mission/ Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000357/2023-2024 | 701/RS | 29/02/2024 | 31/12/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 255.26 | 214.18 | 83.91 | 10
6 | NORTH 24 PARGANAS |  | Resource | Setting up of District Project Management Unit (DPMU) at Purulia, Bankura, Purba & Paschim Medinipur, Jhargram, Howrah, Hooghly, South & North 24 Parganas and nadia districts under Jal Jeevan Mission | SM/19239 |  | Engagement of one consulting agency for Setting up of District Project Management Unit (DPMU) at Howrah, Hooghly, South 24 Parganas, North 24 Parganas andNadiadistricts under Jal Jeevan Mission/ Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000357/2023-2024 | 701/RS | 29/02/2024 | 31/12/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 255.26 | 214.18 | 83.91 | 10
7 | PASCHIM MEDINIPUR |  | Resource | Setting up of District Project Management Unit (DPMU) at Purulia, Bankura, Purba & Paschim Medinipur, Jhargram, Howrah, Hooghly, South & North 24 Parganas and nadia districts under Jal Jeevan Mission | SM/19239 |  | Engagement of one consulting agency for Setting up of District Project Management Unit (DPMU) at Howrah, Hooghly, South 24 Parganas, North 24 Parganas andNadiadistricts under Jal Jeevan Mission/ Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000357/2023-2024 | 701/RS | 29/02/2024 | 31/12/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 255.26 | 214.18 | 83.91 | 10
8 | PURBA MEDINIPUR |  | Resource | Setting up of District Project Management Unit (DPMU) at Purulia, Bankura, Purba & Paschim Medinipur, Jhargram, Howrah, Hooghly, South & North 24 Parganas and nadia districts under Jal Jeevan Mission | SM/19239 |  | Engagement of one consulting agency for Setting up of District Project Management Unit (DPMU) at Howrah, Hooghly, South 24 Parganas, North 24 Parganas andNadiadistricts under Jal Jeevan Mission/ Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000357/2023-2024 | 701/RS | 29/02/2024 | 31/12/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 255.26 | 214.18 | 83.91 | 10
9 | PURULIA |  | Resource | Setting up of District Project Management Unit (DPMU) at Purulia, Bankura, Purba & Paschim Medinipur, Jhargram, Howrah, Hooghly, South & North 24 Parganas and nadia districts under Jal Jeevan Mission | SM/19239 |  | Engagement of one consulting agency for Setting up of District Project Management Unit (DPMU) at Howrah, Hooghly, South 24 Parganas, North 24 Parganas andNadiadistricts under Jal Jeevan Mission/ Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000357/2023-2024 | 701/RS | 29/02/2024 | 31/12/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 255.26 | 214.18 | 83.91 | 10
10 | SOUTH 24 PARGANAS |  | Resource | Setting up of District Project Management Unit (DPMU) at Purulia, Bankura, Purba & Paschim Medinipur, Jhargram, Howrah, Hooghly, South & North 24 Parganas and nadia districts under Jal Jeevan Mission | SM/19239 |  | Engagement of one consulting agency for Setting up of District Project Management Unit (DPMU) at Howrah, Hooghly, South 24 Parganas, North 24 Parganas andNadiadistricts under Jal Jeevan Mission/ Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000357/2023-2024 | 701/RS | 29/02/2024 | 31/12/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 255.26 | 214.18 | 83.91 | 10
11 | BANKURA |  | Resource | Setting up of District Project Management Unit (DPMU) at Purulia, Bankura, Purba & Paschim Medinipur, Jhargram, Howrah, Hooghly, South & North 24 Parganas and nadia districts under Jal Jeevan Mission | SM/19239 |  | Engagement of one consulting agency for Setting up of District Project Management Unit (DPMU) at Purba Medinipur, Paschim Medinipur, Jhargram,Bankura and Purulia under Jal Jeevan Mission / Jal Swapna. |  |  | ORD/000295/2024-2025 | 604/RS | 17/03/2025 | 17/03/2026 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 333 | 0 | 0 | 5
12 | HOOGHLY |  | Resource | Setting up of District Project Management Unit (DPMU) at Purulia, Bankura, Purba & Paschim Medinipur, Jhargram, Howrah, Hooghly, South & North 24 Parganas and nadia districts under Jal Jeevan Mission | SM/19239 |  | Engagement of one consulting agency for Setting up of District Project Management Unit (DPMU) at Purba Medinipur, Paschim Medinipur, Jhargram,Bankura and Purulia under Jal Jeevan Mission / Jal Swapna. |  |  | ORD/000295/2024-2025 | 604/RS | 17/03/2025 | 17/03/2026 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 333 | 0 | 0 | 5
13 | HOWRAH |  | Resource | Setting up of District Project Management Unit (DPMU) at Purulia, Bankura, Purba & Paschim Medinipur, Jhargram, Howrah, Hooghly, South & North 24 Parganas and nadia districts under Jal Jeevan Mission | SM/19239 |  | Engagement of one consulting agency for Setting up of District Project Management Unit (DPMU) at Purba Medinipur, Paschim Medinipur, Jhargram,Bankura and Purulia under Jal Jeevan Mission / Jal Swapna. |  |  | ORD/000295/2024-2025 | 604/RS | 17/03/2025 | 17/03/2026 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 333 | 0 | 0 | 5
14 | JHARGRAM |  | Resource | Setting up of District Project Management Unit (DPMU) at Purulia, Bankura, Purba & Paschim Medinipur, Jhargram, Howrah, Hooghly, South & North 24 Parganas and nadia districts under Jal Jeevan Mission | SM/19239 |  | Engagement of one consulting agency for Setting up of District Project Management Unit (DPMU) at Purba Medinipur, Paschim Medinipur, Jhargram,Bankura and Purulia under Jal Jeevan Mission / Jal Swapna. |  |  | ORD/000295/2024-2025 | 604/RS | 17/03/2025 | 17/03/2026 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 333 | 0 | 0 | 5
15 | NADIA |  | Resource | Setting up of District Project Management Unit (DPMU) at Purulia, Bankura, Purba & Paschim Medinipur, Jhargram, Howrah, Hooghly, South & North 24 Parganas and nadia districts under Jal Jeevan Mission | SM/19239 |  | Engagement of one consulting agency for Setting up of District Project Management Unit (DPMU) at Purba Medinipur, Paschim Medinipur, Jhargram,Bankura and Purulia under Jal Jeevan Mission / Jal Swapna. |  |  | ORD/000295/2024-2025 | 604/RS | 17/03/2025 | 17/03/2026 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 333 | 0 | 0 | 5
16 | NORTH 24 PARGANAS |  | Resource | Setting up of District Project Management Unit (DPMU) at Purulia, Bankura, Purba & Paschim Medinipur, Jhargram, Howrah, Hooghly, South & North 24 Parganas and nadia districts under Jal Jeevan Mission | SM/19239 |  | Engagement of one consulting agency for Setting up of District Project Management Unit (DPMU) at Purba Medinipur, Paschim Medinipur, Jhargram,Bankura and Purulia under Jal Jeevan Mission / Jal Swapna. |  |  | ORD/000295/2024-2025 | 604/RS | 17/03/2025 | 17/03/2026 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 333 | 0 | 0 | 5
17 | PASCHIM MEDINIPUR |  | Resource | Setting up of District Project Management Unit (DPMU) at Purulia, Bankura, Purba & Paschim Medinipur, Jhargram, Howrah, Hooghly, South & North 24 Parganas and nadia districts under Jal Jeevan Mission | SM/19239 |  | Engagement of one consulting agency for Setting up of District Project Management Unit (DPMU) at Purba Medinipur, Paschim Medinipur, Jhargram,Bankura and Purulia under Jal Jeevan Mission / Jal Swapna. |  |  | ORD/000295/2024-2025 | 604/RS | 17/03/2025 | 17/03/2026 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 333 | 0 | 0 | 5
18 | PURBA MEDINIPUR |  | Resource | Setting up of District Project Management Unit (DPMU) at Purulia, Bankura, Purba & Paschim Medinipur, Jhargram, Howrah, Hooghly, South & North 24 Parganas and nadia districts under Jal Jeevan Mission | SM/19239 |  | Engagement of one consulting agency for Setting up of District Project Management Unit (DPMU) at Purba Medinipur, Paschim Medinipur, Jhargram,Bankura and Purulia under Jal Jeevan Mission / Jal Swapna. |  |  | ORD/000295/2024-2025 | 604/RS | 17/03/2025 | 17/03/2026 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 333 | 0 | 0 | 5
19 | PURULIA |  | Resource | Setting up of District Project Management Unit (DPMU) at Purulia, Bankura, Purba & Paschim Medinipur, Jhargram, Howrah, Hooghly, South & North 24 Parganas and nadia districts under Jal Jeevan Mission | SM/19239 |  | Engagement of one consulting agency for Setting up of District Project Management Unit (DPMU) at Purba Medinipur, Paschim Medinipur, Jhargram,Bankura and Purulia under Jal Jeevan Mission / Jal Swapna. |  |  | ORD/000295/2024-2025 | 604/RS | 17/03/2025 | 17/03/2026 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 333 | 0 | 0 | 5
20 | SOUTH 24 PARGANAS |  | Resource | Setting up of District Project Management Unit (DPMU) at Purulia, Bankura, Purba & Paschim Medinipur, Jhargram, Howrah, Hooghly, South & North 24 Parganas and nadia districts under Jal Jeevan Mission | SM/19239 |  | Engagement of one consulting agency for Setting up of District Project Management Unit (DPMU) at Purba Medinipur, Paschim Medinipur, Jhargram,Bankura and Purulia under Jal Jeevan Mission / Jal Swapna. |  |  | ORD/000295/2024-2025 | 604/RS | 17/03/2025 | 17/03/2026 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 333 | 0 | 0 | 5
21 | BANKURA |  | Resource | Setting up of District Project Management Unit (DPMU) at Purulia, Bankura, Purba & Paschim Medinipur, Jhargram, Howrah, Hooghly, South & North 24 Parganas and nadia districts under Jal Jeevan Mission | SM/19239 |  | Engagement of one consulting agency for Setting up of District Project Management Unit (DPMU) at Howrah, Hooghly, South 24 Parganas, North 24 Parganas and Nadia districts under Jal Jeevan Mission/ Jal Swapna. |  |  | ORD/000296/2024-2025 | 605/RS | 17/03/2025 | 17/03/2026 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 331.14 | 0 | 0 | 5
22 | HOOGHLY |  | Resource | Setting up of District Project Management Unit (DPMU) at Purulia, Bankura, Purba & Paschim Medinipur, Jhargram, Howrah, Hooghly, South & North 24 Parganas and nadia districts under Jal Jeevan Mission | SM/19239 |  | Engagement of one consulting agency for Setting up of District Project Management Unit (DPMU) at Howrah, Hooghly, South 24 Parganas, North 24 Parganas and Nadia districts under Jal Jeevan Mission/ Jal Swapna. |  |  | ORD/000296/2024-2025 | 605/RS | 17/03/2025 | 17/03/2026 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 331.14 | 0 | 0 | 5
23 | HOWRAH |  | Resource | Setting up of District Project Management Unit (DPMU) at Purulia, Bankura, Purba & Paschim Medinipur, Jhargram, Howrah, Hooghly, South & North 24 Parganas and nadia districts under Jal Jeevan Mission | SM/19239 |  | Engagement of one consulting agency for Setting up of District Project Management Unit (DPMU) at Howrah, Hooghly, South 24 Parganas, North 24 Parganas and Nadia districts under Jal Jeevan Mission/ Jal Swapna. |  |  | ORD/000296/2024-2025 | 605/RS | 17/03/2025 | 17/03/2026 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 331.14 | 0 | 0 | 5
24 | JHARGRAM |  | Resource | Setting up of District Project Management Unit (DPMU) at Purulia, Bankura, Purba & Paschim Medinipur, Jhargram, Howrah, Hooghly, South & North 24 Parganas and nadia districts under Jal Jeevan Mission | SM/19239 |  | Engagement of one consulting agency for Setting up of District Project Management Unit (DPMU) at Howrah, Hooghly, South 24 Parganas, North 24 Parganas and Nadia districts under Jal Jeevan Mission/ Jal Swapna. |  |  | ORD/000296/2024-2025 | 605/RS | 17/03/2025 | 17/03/2026 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 331.14 | 0 | 0 | 5
25 | NADIA |  | Resource | Setting up of District Project Management Unit (DPMU) at Purulia, Bankura, Purba & Paschim Medinipur, Jhargram, Howrah, Hooghly, South & North 24 Parganas and nadia districts under Jal Jeevan Mission | SM/19239 |  | Engagement of one consulting agency for Setting up of District Project Management Unit (DPMU) at Howrah, Hooghly, South 24 Parganas, North 24 Parganas and Nadia districts under Jal Jeevan Mission/ Jal Swapna. |  |  | ORD/000296/2024-2025 | 605/RS | 17/03/2025 | 17/03/2026 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 331.14 | 0 | 0 | 5
26 | NORTH 24 PARGANAS |  | Resource | Setting up of District Project Management Unit (DPMU) at Purulia, Bankura, Purba & Paschim Medinipur, Jhargram, Howrah, Hooghly, South & North 24 Parganas and nadia districts under Jal Jeevan Mission | SM/19239 |  | Engagement of one consulting agency for Setting up of District Project Management Unit (DPMU) at Howrah, Hooghly, South 24 Parganas, North 24 Parganas and Nadia districts under Jal Jeevan Mission/ Jal Swapna. |  |  | ORD/000296/2024-2025 | 605/RS | 17/03/2025 | 17/03/2026 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 331.14 | 0 | 0 | 5
27 | PASCHIM MEDINIPUR |  | Resource | Setting up of District Project Management Unit (DPMU) at Purulia, Bankura, Purba & Paschim Medinipur, Jhargram, Howrah, Hooghly, South & North 24 Parganas and nadia districts under Jal Jeevan Mission | SM/19239 |  | Engagement of one consulting agency for Setting up of District Project Management Unit (DPMU) at Howrah, Hooghly, South 24 Parganas, North 24 Parganas and Nadia districts under Jal Jeevan Mission/ Jal Swapna. |  |  | ORD/000296/2024-2025 | 605/RS | 17/03/2025 | 17/03/2026 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 331.14 | 0 | 0 | 5
28 | PURBA MEDINIPUR |  | Resource | Setting up of District Project Management Unit (DPMU) at Purulia, Bankura, Purba & Paschim Medinipur, Jhargram, Howrah, Hooghly, South & North 24 Parganas and nadia districts under Jal Jeevan Mission | SM/19239 |  | Engagement of one consulting agency for Setting up of District Project Management Unit (DPMU) at Howrah, Hooghly, South 24 Parganas, North 24 Parganas and Nadia districts under Jal Jeevan Mission/ Jal Swapna. |  |  | ORD/000296/2024-2025 | 605/RS | 17/03/2025 | 17/03/2026 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 331.14 | 0 | 0 | 5
29 | PURULIA |  | Resource | Setting up of District Project Management Unit (DPMU) at Purulia, Bankura, Purba & Paschim Medinipur, Jhargram, Howrah, Hooghly, South & North 24 Parganas and nadia districts under Jal Jeevan Mission | SM/19239 |  | Engagement of one consulting agency for Setting up of District Project Management Unit (DPMU) at Howrah, Hooghly, South 24 Parganas, North 24 Parganas and Nadia districts under Jal Jeevan Mission/ Jal Swapna. |  |  | ORD/000296/2024-2025 | 605/RS | 17/03/2025 | 17/03/2026 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 331.14 | 0 | 0 | 5
30 | SOUTH 24 PARGANAS |  | Resource | Setting up of District Project Management Unit (DPMU) at Purulia, Bankura, Purba & Paschim Medinipur, Jhargram, Howrah, Hooghly, South & North 24 Parganas and nadia districts under Jal Jeevan Mission | SM/19239 |  | Engagement of one consulting agency for Setting up of District Project Management Unit (DPMU) at Howrah, Hooghly, South 24 Parganas, North 24 Parganas and Nadia districts under Jal Jeevan Mission/ Jal Swapna. |  |  | ORD/000296/2024-2025 | 605/RS | 17/03/2025 | 17/03/2026 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 331.14 | 0 | 0 | 5
Total | [13 empty] | 9194 | 2141.79 | 23.3