## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Resource | Acquisition of Field Level Data of Headwork Site and Distribution System of different Piped Water Supply Schemes and Updation of the Same in the WB-PHED Web Module for the Districts of Bankura, Hooghly, Howrah and Jhargram (Phase-I) | SM/19252 | Support-MIS | Collection, Scanning and Digitization of printed distribution drawings from divisions/subdivisions of the PHE Directorate into Geo-referenced CAD files and uploading them in the PHED "Scheme Drawing & Litholog" Module along with development of a GIS tool facilitating a user-friendly, integrated data entry panel designed for capturing essential attributes such as material, diameter, and connection points to convert a design drawing into an in-built drawing under Support Activities of Jal Jeevan Mission. | Assistant Engineer | Junior Engineer | ORD/000018/2025-2026 | 1026/RS | 14/05/2025 | 11/09/2025 | HORIZEN | 78.73 | 0 | 0 | 10
2 | HOOGHLY |  | Resource | Acquisition of Field Level Data of Headwork Site and Distribution System of different Piped Water Supply Schemes and Updation of the Same in the WB-PHED Web Module for the Districts of Bankura, Hooghly, Howrah and Jhargram (Phase-I) | SM/19252 | Support-MIS | Collection, Scanning and Digitization of printed distribution drawings from divisions/subdivisions of the PHE Directorate into Geo-referenced CAD files and uploading them in the PHED "Scheme Drawing & Litholog" Module along with development of a GIS tool facilitating a user-friendly, integrated data entry panel designed for capturing essential attributes such as material, diameter, and connection points to convert a design drawing into an in-built drawing under Support Activities of Jal Jeevan Mission. | Assistant Engineer | Junior Engineer | ORD/000018/2025-2026 | 1026/RS | 14/05/2025 | 11/09/2025 | HORIZEN | 78.73 | 0 | 0 | 10
3 | HOWRAH |  | Resource | Acquisition of Field Level Data of Headwork Site and Distribution System of different Piped Water Supply Schemes and Updation of the Same in the WB-PHED Web Module for the Districts of Bankura, Hooghly, Howrah and Jhargram (Phase-I) | SM/19252 | Support-MIS | Collection, Scanning and Digitization of printed distribution drawings from divisions/subdivisions of the PHE Directorate into Geo-referenced CAD files and uploading them in the PHED "Scheme Drawing & Litholog" Module along with development of a GIS tool facilitating a user-friendly, integrated data entry panel designed for capturing essential attributes such as material, diameter, and connection points to convert a design drawing into an in-built drawing under Support Activities of Jal Jeevan Mission. | Assistant Engineer | Junior Engineer | ORD/000018/2025-2026 | 1026/RS | 14/05/2025 | 11/09/2025 | HORIZEN | 78.73 | 0 | 0 | 10
4 | JHARGRAM |  | Resource | Acquisition of Field Level Data of Headwork Site and Distribution System of different Piped Water Supply Schemes and Updation of the Same in the WB-PHED Web Module for the Districts of Bankura, Hooghly, Howrah and Jhargram (Phase-I) | SM/19252 | Support-MIS | Collection, Scanning and Digitization of printed distribution drawings from divisions/subdivisions of the PHE Directorate into Geo-referenced CAD files and uploading them in the PHED "Scheme Drawing & Litholog" Module along with development of a GIS tool facilitating a user-friendly, integrated data entry panel designed for capturing essential attributes such as material, diameter, and connection points to convert a design drawing into an in-built drawing under Support Activities of Jal Jeevan Mission. | Assistant Engineer | Junior Engineer | ORD/000018/2025-2026 | 1026/RS | 14/05/2025 | 11/09/2025 | HORIZEN | 78.73 | 0 | 0 | 10
5 | BANKURA |  | Resource | Acquisition of Field Level Data of Headwork Site and Distribution System of different Piped Water Supply Schemes and Updation of the Same in the WB-PHED Web Module for the Districts of Bankura, Hooghly, Howrah and Jhargram (Phase-I) | SM/19252 | Support-MIS | Digitization of the transmission, distribution system, and all assets of piped water supply schemes, converting them to Keyhole Markup Language (.kml) files for uploading in the PM Gati Shakti Portal, along with digitization, preparation, and upload of lithologic drawings received from divisions/sub-divisions of the PHED Directorate under Support Activities of Jal Jeevan Mission | Assistant Engineer | Junior Engineer | ORD/000008/2025-2026 | 929/RS | 29/04/2025 | 26/10/2025 | HORIZEN | 80.97 | 0 | 0 | 56
6 | HOOGHLY |  | Resource | Acquisition of Field Level Data of Headwork Site and Distribution System of different Piped Water Supply Schemes and Updation of the Same in the WB-PHED Web Module for the Districts of Bankura, Hooghly, Howrah and Jhargram (Phase-I) | SM/19252 | Support-MIS | Digitization of the transmission, distribution system, and all assets of piped water supply schemes, converting them to Keyhole Markup Language (.kml) files for uploading in the PM Gati Shakti Portal, along with digitization, preparation, and upload of lithologic drawings received from divisions/sub-divisions of the PHED Directorate under Support Activities of Jal Jeevan Mission | Assistant Engineer | Junior Engineer | ORD/000008/2025-2026 | 929/RS | 29/04/2025 | 26/10/2025 | HORIZEN | 80.97 | 0 | 0 | 56
7 | HOWRAH |  | Resource | Acquisition of Field Level Data of Headwork Site and Distribution System of different Piped Water Supply Schemes and Updation of the Same in the WB-PHED Web Module for the Districts of Bankura, Hooghly, Howrah and Jhargram (Phase-I) | SM/19252 | Support-MIS | Digitization of the transmission, distribution system, and all assets of piped water supply schemes, converting them to Keyhole Markup Language (.kml) files for uploading in the PM Gati Shakti Portal, along with digitization, preparation, and upload of lithologic drawings received from divisions/sub-divisions of the PHED Directorate under Support Activities of Jal Jeevan Mission | Assistant Engineer | Junior Engineer | ORD/000008/2025-2026 | 929/RS | 29/04/2025 | 26/10/2025 | HORIZEN | 80.97 | 0 | 0 | 56
8 | JHARGRAM |  | Resource | Acquisition of Field Level Data of Headwork Site and Distribution System of different Piped Water Supply Schemes and Updation of the Same in the WB-PHED Web Module for the Districts of Bankura, Hooghly, Howrah and Jhargram (Phase-I) | SM/19252 | Support-MIS | Digitization of the transmission, distribution system, and all assets of piped water supply schemes, converting them to Keyhole Markup Language (.kml) files for uploading in the PM Gati Shakti Portal, along with digitization, preparation, and upload of lithologic drawings received from divisions/sub-divisions of the PHED Directorate under Support Activities of Jal Jeevan Mission | Assistant Engineer | Junior Engineer | ORD/000008/2025-2026 | 929/RS | 29/04/2025 | 26/10/2025 | HORIZEN | 80.97 | 0 | 0 | 56
9 | BANKURA |  | Resource | Acquisition of Field Level Data of Headwork Site and Distribution System of different Piped Water Supply Schemes and Updation of the Same in the WB-PHED Web Module for the Districts of Bankura, Hooghly, Howrah and Jhargram (Phase-I) | SM/19252 | Support-MIS | Scrutinization and verification of pump house data under WBSEDCL through continuous field visits and consultation with the Mechanical/Electrical wing of the PHE Department, including creation of an online monitoring system to ensure accurate and seamless recording of daily activities at pump houses regarding functioning of pumps & motors, chlorination arrangements etc. to facilitate continuous energy audits and future verification of WBSEDCL data | Assistant Engineer | Junior Engineer | ORD/000102/2025-2026 | 2033/RS | 04/09/2025 | 04/09/2026 | HORIZEN | 86.02 | 0 | 0 | 7
10 | HOOGHLY |  | Resource | Acquisition of Field Level Data of Headwork Site and Distribution System of different Piped Water Supply Schemes and Updation of the Same in the WB-PHED Web Module for the Districts of Bankura, Hooghly, Howrah and Jhargram (Phase-I) | SM/19252 | Support-MIS | Scrutinization and verification of pump house data under WBSEDCL through continuous field visits and consultation with the Mechanical/Electrical wing of the PHE Department, including creation of an online monitoring system to ensure accurate and seamless recording of daily activities at pump houses regarding functioning of pumps & motors, chlorination arrangements etc. to facilitate continuous energy audits and future verification of WBSEDCL data | Assistant Engineer | Junior Engineer | ORD/000102/2025-2026 | 2033/RS | 04/09/2025 | 04/09/2026 | HORIZEN | 86.02 | 0 | 0 | 7
11 | HOWRAH |  | Resource | Acquisition of Field Level Data of Headwork Site and Distribution System of different Piped Water Supply Schemes and Updation of the Same in the WB-PHED Web Module for the Districts of Bankura, Hooghly, Howrah and Jhargram (Phase-I) | SM/19252 | Support-MIS | Scrutinization and verification of pump house data under WBSEDCL through continuous field visits and consultation with the Mechanical/Electrical wing of the PHE Department, including creation of an online monitoring system to ensure accurate and seamless recording of daily activities at pump houses regarding functioning of pumps & motors, chlorination arrangements etc. to facilitate continuous energy audits and future verification of WBSEDCL data | Assistant Engineer | Junior Engineer | ORD/000102/2025-2026 | 2033/RS | 04/09/2025 | 04/09/2026 | HORIZEN | 86.02 | 0 | 0 | 7
12 | JHARGRAM |  | Resource | Acquisition of Field Level Data of Headwork Site and Distribution System of different Piped Water Supply Schemes and Updation of the Same in the WB-PHED Web Module for the Districts of Bankura, Hooghly, Howrah and Jhargram (Phase-I) | SM/19252 | Support-MIS | Scrutinization and verification of pump house data under WBSEDCL through continuous field visits and consultation with the Mechanical/Electrical wing of the PHE Department, including creation of an online monitoring system to ensure accurate and seamless recording of daily activities at pump houses regarding functioning of pumps & motors, chlorination arrangements etc. to facilitate continuous energy audits and future verification of WBSEDCL data | Assistant Engineer | Junior Engineer | ORD/000102/2025-2026 | 2033/RS | 04/09/2025 | 04/09/2026 | HORIZEN | 86.02 | 0 | 0 | 7
13 | BANKURA |  | Resource | Acquisition of Field Level Data of Headwork Site and Distribution System of different Piped Water Supply Schemes and Updation of the Same in the WB-PHED Web Module for the Districts of Bankura, Hooghly, Howrah and Jhargram (Phase-I) | SM/19252 | Support-MIS | Development and Deployment of a Technology-Enabled, Multi-Channel Grievance Redressal System to Enhance Transparency, Service Accountability, and Real-Time Citizen Engagement in Rural Water Supply Management for Asset Management and Maintenance under Jal Jeevan Mission | Assistant Engineer | Junior Engineer | ORD/000121/2025-2026 | 2184/RS | 23/09/2025 | 23/09/2026 | HORIZEN | 96.41 | 0 | 0 | 60
14 | HOOGHLY |  | Resource | Acquisition of Field Level Data of Headwork Site and Distribution System of different Piped Water Supply Schemes and Updation of the Same in the WB-PHED Web Module for the Districts of Bankura, Hooghly, Howrah and Jhargram (Phase-I) | SM/19252 | Support-MIS | Development and Deployment of a Technology-Enabled, Multi-Channel Grievance Redressal System to Enhance Transparency, Service Accountability, and Real-Time Citizen Engagement in Rural Water Supply Management for Asset Management and Maintenance under Jal Jeevan Mission | Assistant Engineer | Junior Engineer | ORD/000121/2025-2026 | 2184/RS | 23/09/2025 | 23/09/2026 | HORIZEN | 96.41 | 0 | 0 | 60
15 | HOWRAH |  | Resource | Acquisition of Field Level Data of Headwork Site and Distribution System of different Piped Water Supply Schemes and Updation of the Same in the WB-PHED Web Module for the Districts of Bankura, Hooghly, Howrah and Jhargram (Phase-I) | SM/19252 | Support-MIS | Development and Deployment of a Technology-Enabled, Multi-Channel Grievance Redressal System to Enhance Transparency, Service Accountability, and Real-Time Citizen Engagement in Rural Water Supply Management for Asset Management and Maintenance under Jal Jeevan Mission | Assistant Engineer | Junior Engineer | ORD/000121/2025-2026 | 2184/RS | 23/09/2025 | 23/09/2026 | HORIZEN | 96.41 | 0 | 0 | 60
16 | JHARGRAM |  | Resource | Acquisition of Field Level Data of Headwork Site and Distribution System of different Piped Water Supply Schemes and Updation of the Same in the WB-PHED Web Module for the Districts of Bankura, Hooghly, Howrah and Jhargram (Phase-I) | SM/19252 | Support-MIS | Development and Deployment of a Technology-Enabled, Multi-Channel Grievance Redressal System to Enhance Transparency, Service Accountability, and Real-Time Citizen Engagement in Rural Water Supply Management for Asset Management and Maintenance under Jal Jeevan Mission | Assistant Engineer | Junior Engineer | ORD/000121/2025-2026 | 2184/RS | 23/09/2025 | 23/09/2026 | HORIZEN | 96.41 | 0 | 0 | 60
17 | BANKURA |  | Resource | Acquisition of Field Level Data of Headwork Site and Distribution System of different Piped Water Supply Schemes and Updation of the Same in the WB-PHED Web Module for the Districts of Bankura, Hooghly, Howrah and Jhargram (Phase-I) | SM/19252 | Support-MIS | Extraction, harmonization, and spatial integration of pipeline infrastructure data across all relevant Piped Water Supply Schemes to enable geospatial visualization, performance monitoring, functionality assessment, and data-driven strategic planning for Asset management and subsequent Operation & Maintenance procedure within the Jal Jeevan Mission implementation framework under PHED WB. | Assistant Engineer | Junior Engineer | ORD/000156/2025-2026 | 2617/RS | 10/12/2025 | 08/06/2026 | HORIZEN | 224.32 | 0 | 0 | 40
18 | HOOGHLY |  | Resource | Acquisition of Field Level Data of Headwork Site and Distribution System of different Piped Water Supply Schemes and Updation of the Same in the WB-PHED Web Module for the Districts of Bankura, Hooghly, Howrah and Jhargram (Phase-I) | SM/19252 | Support-MIS | Extraction, harmonization, and spatial integration of pipeline infrastructure data across all relevant Piped Water Supply Schemes to enable geospatial visualization, performance monitoring, functionality assessment, and data-driven strategic planning for Asset management and subsequent Operation & Maintenance procedure within the Jal Jeevan Mission implementation framework under PHED WB. | Assistant Engineer | Junior Engineer | ORD/000156/2025-2026 | 2617/RS | 10/12/2025 | 08/06/2026 | HORIZEN | 224.32 | 0 | 0 | 40
19 | HOWRAH |  | Resource | Acquisition of Field Level Data of Headwork Site and Distribution System of different Piped Water Supply Schemes and Updation of the Same in the WB-PHED Web Module for the Districts of Bankura, Hooghly, Howrah and Jhargram (Phase-I) | SM/19252 | Support-MIS | Extraction, harmonization, and spatial integration of pipeline infrastructure data across all relevant Piped Water Supply Schemes to enable geospatial visualization, performance monitoring, functionality assessment, and data-driven strategic planning for Asset management and subsequent Operation & Maintenance procedure within the Jal Jeevan Mission implementation framework under PHED WB. | Assistant Engineer | Junior Engineer | ORD/000156/2025-2026 | 2617/RS | 10/12/2025 | 08/06/2026 | HORIZEN | 224.32 | 0 | 0 | 40
20 | JHARGRAM |  | Resource | Acquisition of Field Level Data of Headwork Site and Distribution System of different Piped Water Supply Schemes and Updation of the Same in the WB-PHED Web Module for the Districts of Bankura, Hooghly, Howrah and Jhargram (Phase-I) | SM/19252 | Support-MIS | Extraction, harmonization, and spatial integration of pipeline infrastructure data across all relevant Piped Water Supply Schemes to enable geospatial visualization, performance monitoring, functionality assessment, and data-driven strategic planning for Asset management and subsequent Operation & Maintenance procedure within the Jal Jeevan Mission implementation framework under PHED WB. | Assistant Engineer | Junior Engineer | ORD/000156/2025-2026 | 2617/RS | 10/12/2025 | 08/06/2026 | HORIZEN | 224.32 | 0 | 0 | 40
Total | [13 empty] | 2265.8 | 0 | 0