## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Resource | Acquisition of Field Level Data of Headwork Site and Distribution System of different Piped Water Supply Schemes and Updation of the Same in the WB-PHED Web Module for the Districts of Bankura, Hooghly, Howrah and Jhargram (Phase-I) | SM/19252 | Support-MIS | Collection, Scanning and Digitization of printed distribution drawings from divisions/subdivisions of the PHE Directorate into Geo-referenced CAD files and uploading them in the PHED "Scheme Drawing & Litholog" Module along with development of a GIS tool facilitating a user-friendly, integrated data entry panel designed for capturing essential attributes such as material, diameter, and connection points to convert a design drawing into an in-built drawing under Support Activities of Jal Jeevan Mission. | Assistant Engineer | Junior Engineer | ORD/000018/2025-2026 | 1026/RS | 14/05/2025 | 11/09/2025 | HORIZEN | 78.73 | 0 | 0 | 10
2 | HOOGHLY |  | Resource | Acquisition of Field Level Data of Headwork Site and Distribution System of different Piped Water Supply Schemes and Updation of the Same in the WB-PHED Web Module for the Districts of Bankura, Hooghly, Howrah and Jhargram (Phase-I) | SM/19252 | Support-MIS | Collection, Scanning and Digitization of printed distribution drawings from divisions/subdivisions of the PHE Directorate into Geo-referenced CAD files and uploading them in the PHED "Scheme Drawing & Litholog" Module along with development of a GIS tool facilitating a user-friendly, integrated data entry panel designed for capturing essential attributes such as material, diameter, and connection points to convert a design drawing into an in-built drawing under Support Activities of Jal Jeevan Mission. | Assistant Engineer | Junior Engineer | ORD/000018/2025-2026 | 1026/RS | 14/05/2025 | 11/09/2025 | HORIZEN | 78.73 | 0 | 0 | 10
3 | HOWRAH |  | Resource | Acquisition of Field Level Data of Headwork Site and Distribution System of different Piped Water Supply Schemes and Updation of the Same in the WB-PHED Web Module for the Districts of Bankura, Hooghly, Howrah and Jhargram (Phase-I) | SM/19252 | Support-MIS | Collection, Scanning and Digitization of printed distribution drawings from divisions/subdivisions of the PHE Directorate into Geo-referenced CAD files and uploading them in the PHED "Scheme Drawing & Litholog" Module along with development of a GIS tool facilitating a user-friendly, integrated data entry panel designed for capturing essential attributes such as material, diameter, and connection points to convert a design drawing into an in-built drawing under Support Activities of Jal Jeevan Mission. | Assistant Engineer | Junior Engineer | ORD/000018/2025-2026 | 1026/RS | 14/05/2025 | 11/09/2025 | HORIZEN | 78.73 | 0 | 0 | 10
4 | JHARGRAM |  | Resource | Acquisition of Field Level Data of Headwork Site and Distribution System of different Piped Water Supply Schemes and Updation of the Same in the WB-PHED Web Module for the Districts of Bankura, Hooghly, Howrah and Jhargram (Phase-I) | SM/19252 | Support-MIS | Collection, Scanning and Digitization of printed distribution drawings from divisions/subdivisions of the PHE Directorate into Geo-referenced CAD files and uploading them in the PHED "Scheme Drawing & Litholog" Module along with development of a GIS tool facilitating a user-friendly, integrated data entry panel designed for capturing essential attributes such as material, diameter, and connection points to convert a design drawing into an in-built drawing under Support Activities of Jal Jeevan Mission. | Assistant Engineer | Junior Engineer | ORD/000018/2025-2026 | 1026/RS | 14/05/2025 | 11/09/2025 | HORIZEN | 78.73 | 0 | 0 | 10
5 | BANKURA |  | Resource | Acquisition of Field Level Data of Headwork Site and Distribution System of different Piped Water Supply Schemes and Updation of the Same in the WB-PHED Web Module for the Districts of Bankura, Hooghly, Howrah and Jhargram (Phase-I) | SM/19252 | Support-MIS | Scrutinization and verification of pump house data under WBSEDCL through continuous field visits and consultation with the Mechanical/Electrical wing of the PHE Department, including creation of an online monitoring system to ensure accurate and seamless recording of daily activities at pump houses regarding functioning of pumps & motors, chlorination arrangements etc. to facilitate continuous energy audits and future verification of WBSEDCL data | Assistant Engineer | Junior Engineer | ORD/000102/2025-2026 | 2033/RS | 04/09/2025 | 04/09/2026 | HORIZEN | 86.02 | 0 | 0 | 7
6 | HOOGHLY |  | Resource | Acquisition of Field Level Data of Headwork Site and Distribution System of different Piped Water Supply Schemes and Updation of the Same in the WB-PHED Web Module for the Districts of Bankura, Hooghly, Howrah and Jhargram (Phase-I) | SM/19252 | Support-MIS | Scrutinization and verification of pump house data under WBSEDCL through continuous field visits and consultation with the Mechanical/Electrical wing of the PHE Department, including creation of an online monitoring system to ensure accurate and seamless recording of daily activities at pump houses regarding functioning of pumps & motors, chlorination arrangements etc. to facilitate continuous energy audits and future verification of WBSEDCL data | Assistant Engineer | Junior Engineer | ORD/000102/2025-2026 | 2033/RS | 04/09/2025 | 04/09/2026 | HORIZEN | 86.02 | 0 | 0 | 7
7 | HOWRAH |  | Resource | Acquisition of Field Level Data of Headwork Site and Distribution System of different Piped Water Supply Schemes and Updation of the Same in the WB-PHED Web Module for the Districts of Bankura, Hooghly, Howrah and Jhargram (Phase-I) | SM/19252 | Support-MIS | Scrutinization and verification of pump house data under WBSEDCL through continuous field visits and consultation with the Mechanical/Electrical wing of the PHE Department, including creation of an online monitoring system to ensure accurate and seamless recording of daily activities at pump houses regarding functioning of pumps & motors, chlorination arrangements etc. to facilitate continuous energy audits and future verification of WBSEDCL data | Assistant Engineer | Junior Engineer | ORD/000102/2025-2026 | 2033/RS | 04/09/2025 | 04/09/2026 | HORIZEN | 86.02 | 0 | 0 | 7
8 | JHARGRAM |  | Resource | Acquisition of Field Level Data of Headwork Site and Distribution System of different Piped Water Supply Schemes and Updation of the Same in the WB-PHED Web Module for the Districts of Bankura, Hooghly, Howrah and Jhargram (Phase-I) | SM/19252 | Support-MIS | Scrutinization and verification of pump house data under WBSEDCL through continuous field visits and consultation with the Mechanical/Electrical wing of the PHE Department, including creation of an online monitoring system to ensure accurate and seamless recording of daily activities at pump houses regarding functioning of pumps & motors, chlorination arrangements etc. to facilitate continuous energy audits and future verification of WBSEDCL data | Assistant Engineer | Junior Engineer | ORD/000102/2025-2026 | 2033/RS | 04/09/2025 | 04/09/2026 | HORIZEN | 86.02 | 0 | 0 | 7
Total | [13 empty] | 658.98 | 0 | 0