## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Procurement of Service of Consultants for preparation of DPR of New PWSS for uncovered rural areas of Nadia, Bankura, Paschim Bardhaman and Kalimpong districts. | SM/10564 | Support-M&E | Preparation of piped network system & design the same including Route Survey using DGPS & all related field work for technical data and JJM compliant data collection preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone wise command area of water distribution and transmission network (WD & TN) Showing all requisite design physical features including cost and estimate of different real component of PWSS like OHR, TW,PUMP HOUSE, B/W electronica component etc. including preparation and submission of DPR booklet of PWSS all complete in consultation with PHED Planning Wings and clearance from SLSSC including preparation of bid documents in different PWSS of uncovered area within Joypur Block under Bishnupur Sub-Division under Bankura Division, PHE Dte. | Assistant Engineer |  | ORD/000219/2022-2023 | 1117/BQA | 18/05/2022 | 17/07/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 120.45 | 0 | 0 | 100
2 | KALIMPONG |  | Bankura Division | Procurement of Service of Consultants for preparation of DPR of New PWSS for uncovered rural areas of Nadia, Bankura, Paschim Bardhaman and Kalimpong districts. | SM/10564 | Support-M&E | Preparation of piped network system & design the same including Route Survey using DGPS & all related field work for technical data and JJM compliant data collection preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone wise command area of water distribution and transmission network (WD & TN) Showing all requisite design physical features including cost and estimate of different real component of PWSS like OHR, TW,PUMP HOUSE, B/W electronica component etc. including preparation and submission of DPR booklet of PWSS all complete in consultation with PHED Planning Wings and clearance from SLSSC including preparation of bid documents in different PWSS of uncovered area within Joypur Block under Bishnupur Sub-Division under Bankura Division, PHE Dte. | Assistant Engineer |  | ORD/000219/2022-2023 | 1117/BQA | 18/05/2022 | 17/07/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 120.45 | 0 | 0 | 100
3 | NADIA |  | Bankura Division | Procurement of Service of Consultants for preparation of DPR of New PWSS for uncovered rural areas of Nadia, Bankura, Paschim Bardhaman and Kalimpong districts. | SM/10564 | Support-M&E | Preparation of piped network system & design the same including Route Survey using DGPS & all related field work for technical data and JJM compliant data collection preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone wise command area of water distribution and transmission network (WD & TN) Showing all requisite design physical features including cost and estimate of different real component of PWSS like OHR, TW,PUMP HOUSE, B/W electronica component etc. including preparation and submission of DPR booklet of PWSS all complete in consultation with PHED Planning Wings and clearance from SLSSC including preparation of bid documents in different PWSS of uncovered area within Joypur Block under Bishnupur Sub-Division under Bankura Division, PHE Dte. | Assistant Engineer |  | ORD/000219/2022-2023 | 1117/BQA | 18/05/2022 | 17/07/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 120.45 | 0 | 0 | 100
4 | PASCHIM BARDHAMAN |  | Bankura Division | Procurement of Service of Consultants for preparation of DPR of New PWSS for uncovered rural areas of Nadia, Bankura, Paschim Bardhaman and Kalimpong districts. | SM/10564 | Support-M&E | Preparation of piped network system & design the same including Route Survey using DGPS & all related field work for technical data and JJM compliant data collection preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone wise command area of water distribution and transmission network (WD & TN) Showing all requisite design physical features including cost and estimate of different real component of PWSS like OHR, TW,PUMP HOUSE, B/W electronica component etc. including preparation and submission of DPR booklet of PWSS all complete in consultation with PHED Planning Wings and clearance from SLSSC including preparation of bid documents in different PWSS of uncovered area within Joypur Block under Bishnupur Sub-Division under Bankura Division, PHE Dte. | Assistant Engineer |  | ORD/000219/2022-2023 | 1117/BQA | 18/05/2022 | 17/07/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 120.45 | 0 | 0 | 100
5 | BANKURA |  | Bankura Division | Procurement of Service of Consultants for preparation of DPR of New PWSS for uncovered rural areas of Nadia, Bankura, Paschim Bardhaman and Kalimpong districts. | SM/10564 | Support-M&E | Preparation of piped network system & design the same including Route Survey using DGPS & all related field work for technical data and JJM compliant data collection preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone wise command area of water distribution and transmission network (WD & TN) Showing all requisite design physical features including cost and estimate of different real component of PWSS like OHR, TW,PUMP HOUSE, B/W electronica component etc. including preparation and submission of DPR booklet of PWSS all complete in consultation with PHED Planning Wings and clearance from SLSSC including preparation of bid documents in different PWSS of uncovered area within Kotulpur Block under Bishnupur Sub-Division under Bankura Division, PHE Dte.. | Assistant Engineer |  | ORD/000220/2022-2023 | 1118/BQA | 18/05/2022 | 17/07/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 153.3 | 0 | 0 | 100
6 | KALIMPONG |  | Bankura Division | Procurement of Service of Consultants for preparation of DPR of New PWSS for uncovered rural areas of Nadia, Bankura, Paschim Bardhaman and Kalimpong districts. | SM/10564 | Support-M&E | Preparation of piped network system & design the same including Route Survey using DGPS & all related field work for technical data and JJM compliant data collection preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone wise command area of water distribution and transmission network (WD & TN) Showing all requisite design physical features including cost and estimate of different real component of PWSS like OHR, TW,PUMP HOUSE, B/W electronica component etc. including preparation and submission of DPR booklet of PWSS all complete in consultation with PHED Planning Wings and clearance from SLSSC including preparation of bid documents in different PWSS of uncovered area within Kotulpur Block under Bishnupur Sub-Division under Bankura Division, PHE Dte.. | Assistant Engineer |  | ORD/000220/2022-2023 | 1118/BQA | 18/05/2022 | 17/07/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 153.3 | 0 | 0 | 100
7 | NADIA |  | Bankura Division | Procurement of Service of Consultants for preparation of DPR of New PWSS for uncovered rural areas of Nadia, Bankura, Paschim Bardhaman and Kalimpong districts. | SM/10564 | Support-M&E | Preparation of piped network system & design the same including Route Survey using DGPS & all related field work for technical data and JJM compliant data collection preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone wise command area of water distribution and transmission network (WD & TN) Showing all requisite design physical features including cost and estimate of different real component of PWSS like OHR, TW,PUMP HOUSE, B/W electronica component etc. including preparation and submission of DPR booklet of PWSS all complete in consultation with PHED Planning Wings and clearance from SLSSC including preparation of bid documents in different PWSS of uncovered area within Kotulpur Block under Bishnupur Sub-Division under Bankura Division, PHE Dte.. | Assistant Engineer |  | ORD/000220/2022-2023 | 1118/BQA | 18/05/2022 | 17/07/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 153.3 | 0 | 0 | 100
8 | PASCHIM BARDHAMAN |  | Bankura Division | Procurement of Service of Consultants for preparation of DPR of New PWSS for uncovered rural areas of Nadia, Bankura, Paschim Bardhaman and Kalimpong districts. | SM/10564 | Support-M&E | Preparation of piped network system & design the same including Route Survey using DGPS & all related field work for technical data and JJM compliant data collection preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone wise command area of water distribution and transmission network (WD & TN) Showing all requisite design physical features including cost and estimate of different real component of PWSS like OHR, TW,PUMP HOUSE, B/W electronica component etc. including preparation and submission of DPR booklet of PWSS all complete in consultation with PHED Planning Wings and clearance from SLSSC including preparation of bid documents in different PWSS of uncovered area within Kotulpur Block under Bishnupur Sub-Division under Bankura Division, PHE Dte.. | Assistant Engineer |  | ORD/000220/2022-2023 | 1118/BQA | 18/05/2022 | 17/07/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 153.3 | 0 | 0 | 100
9 | BANKURA |  | Bankura Division | Procurement of Service of Consultants for preparation of DPR of New PWSS for uncovered rural areas of Nadia, Bankura, Paschim Bardhaman and Kalimpong districts. | SM/10564 | Support-M&E | Preparation of piped network system & design the same including Route Survey using DGPS & all related field work for technical data and JJM compliant data collection preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone wise command area of water distribution and transmission network (WD & TN) Showing all requisite design physical features including cost and estimate of different real component of PWSS like OHR, TW,PUMP HOUSE, B/W electronica component etc. including preparation and submission of DPR booklet of PWSS all complete in consultation with PHED Planning Wings and clearance from SLSSC including preparation of bid documents in different PWSS of uncovered area within Sonamukhi Block under Bishnupur Sub-Division under Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000215/2022-2023 | 1115/BQA | 18/05/2022 | 17/07/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 135.05 | 0 | 0 | 100
10 | KALIMPONG |  | Bankura Division | Procurement of Service of Consultants for preparation of DPR of New PWSS for uncovered rural areas of Nadia, Bankura, Paschim Bardhaman and Kalimpong districts. | SM/10564 | Support-M&E | Preparation of piped network system & design the same including Route Survey using DGPS & all related field work for technical data and JJM compliant data collection preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone wise command area of water distribution and transmission network (WD & TN) Showing all requisite design physical features including cost and estimate of different real component of PWSS like OHR, TW,PUMP HOUSE, B/W electronica component etc. including preparation and submission of DPR booklet of PWSS all complete in consultation with PHED Planning Wings and clearance from SLSSC including preparation of bid documents in different PWSS of uncovered area within Sonamukhi Block under Bishnupur Sub-Division under Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000215/2022-2023 | 1115/BQA | 18/05/2022 | 17/07/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 135.05 | 0 | 0 | 100
11 | NADIA |  | Bankura Division | Procurement of Service of Consultants for preparation of DPR of New PWSS for uncovered rural areas of Nadia, Bankura, Paschim Bardhaman and Kalimpong districts. | SM/10564 | Support-M&E | Preparation of piped network system & design the same including Route Survey using DGPS & all related field work for technical data and JJM compliant data collection preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone wise command area of water distribution and transmission network (WD & TN) Showing all requisite design physical features including cost and estimate of different real component of PWSS like OHR, TW,PUMP HOUSE, B/W electronica component etc. including preparation and submission of DPR booklet of PWSS all complete in consultation with PHED Planning Wings and clearance from SLSSC including preparation of bid documents in different PWSS of uncovered area within Sonamukhi Block under Bishnupur Sub-Division under Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000215/2022-2023 | 1115/BQA | 18/05/2022 | 17/07/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 135.05 | 0 | 0 | 100
12 | PASCHIM BARDHAMAN |  | Bankura Division | Procurement of Service of Consultants for preparation of DPR of New PWSS for uncovered rural areas of Nadia, Bankura, Paschim Bardhaman and Kalimpong districts. | SM/10564 | Support-M&E | Preparation of piped network system & design the same including Route Survey using DGPS & all related field work for technical data and JJM compliant data collection preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone wise command area of water distribution and transmission network (WD & TN) Showing all requisite design physical features including cost and estimate of different real component of PWSS like OHR, TW,PUMP HOUSE, B/W electronica component etc. including preparation and submission of DPR booklet of PWSS all complete in consultation with PHED Planning Wings and clearance from SLSSC including preparation of bid documents in different PWSS of uncovered area within Sonamukhi Block under Bishnupur Sub-Division under Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000215/2022-2023 | 1115/BQA | 18/05/2022 | 17/07/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 135.05 | 0 | 0 | 100
13 | BANKURA |  | Bankura Division | Procurement of Service of Consultants for preparation of DPR of New PWSS for uncovered rural areas of Nadia, Bankura, Paschim Bardhaman and Kalimpong districts. | SM/10564 | Support-M&E | Preparation of piped network system & design the same including Route Survey using DGPS & all related field work for technical data and JJM compliant data collection preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone wise command area of water distribution and transmission network (WD & TN) Showing all requisite design physical features including cost and estimate of different real component of PWSS like OHR, TW,PUMP HOUSE, B/W electronica component etc. including preparation and submission of DPR booklet of PWSS all complete in consultation with PHED Planning Wings and clearance from SLSSC including preparation of bid documents in different PWSS of uncovered area within Patrasayer Block under Bishnupur Sub-Division under Bankura Division, PHE Dte.. | Assistant Engineer | Junior Engineer | ORD/000218/2022-2023 | 1116/BQA | 18/05/2022 | 17/07/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 156.95 | 0 | 0 | 100
14 | KALIMPONG |  | Bankura Division | Procurement of Service of Consultants for preparation of DPR of New PWSS for uncovered rural areas of Nadia, Bankura, Paschim Bardhaman and Kalimpong districts. | SM/10564 | Support-M&E | Preparation of piped network system & design the same including Route Survey using DGPS & all related field work for technical data and JJM compliant data collection preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone wise command area of water distribution and transmission network (WD & TN) Showing all requisite design physical features including cost and estimate of different real component of PWSS like OHR, TW,PUMP HOUSE, B/W electronica component etc. including preparation and submission of DPR booklet of PWSS all complete in consultation with PHED Planning Wings and clearance from SLSSC including preparation of bid documents in different PWSS of uncovered area within Patrasayer Block under Bishnupur Sub-Division under Bankura Division, PHE Dte.. | Assistant Engineer | Junior Engineer | ORD/000218/2022-2023 | 1116/BQA | 18/05/2022 | 17/07/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 156.95 | 0 | 0 | 100
15 | NADIA |  | Bankura Division | Procurement of Service of Consultants for preparation of DPR of New PWSS for uncovered rural areas of Nadia, Bankura, Paschim Bardhaman and Kalimpong districts. | SM/10564 | Support-M&E | Preparation of piped network system & design the same including Route Survey using DGPS & all related field work for technical data and JJM compliant data collection preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone wise command area of water distribution and transmission network (WD & TN) Showing all requisite design physical features including cost and estimate of different real component of PWSS like OHR, TW,PUMP HOUSE, B/W electronica component etc. including preparation and submission of DPR booklet of PWSS all complete in consultation with PHED Planning Wings and clearance from SLSSC including preparation of bid documents in different PWSS of uncovered area within Patrasayer Block under Bishnupur Sub-Division under Bankura Division, PHE Dte.. | Assistant Engineer | Junior Engineer | ORD/000218/2022-2023 | 1116/BQA | 18/05/2022 | 17/07/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 156.95 | 0 | 0 | 100
16 | PASCHIM BARDHAMAN |  | Bankura Division | Procurement of Service of Consultants for preparation of DPR of New PWSS for uncovered rural areas of Nadia, Bankura, Paschim Bardhaman and Kalimpong districts. | SM/10564 | Support-M&E | Preparation of piped network system & design the same including Route Survey using DGPS & all related field work for technical data and JJM compliant data collection preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone wise command area of water distribution and transmission network (WD & TN) Showing all requisite design physical features including cost and estimate of different real component of PWSS like OHR, TW,PUMP HOUSE, B/W electronica component etc. including preparation and submission of DPR booklet of PWSS all complete in consultation with PHED Planning Wings and clearance from SLSSC including preparation of bid documents in different PWSS of uncovered area within Patrasayer Block under Bishnupur Sub-Division under Bankura Division, PHE Dte.. | Assistant Engineer | Junior Engineer | ORD/000218/2022-2023 | 1116/BQA | 18/05/2022 | 17/07/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 156.95 | 0 | 0 | 100
17 | BANKURA |  | Bankura Division | Procurement of Service of Consultants for preparation of DPR of New PWSS for uncovered rural areas of Nadia, Bankura, Paschim Bardhaman and Kalimpong districts. | SM/10564 | Support-M&E | Preparation of Detailed Project Report for Proposed ground water based KATUL pipe water supply scheme, under Bankura Division, Block : Bishnupur, District : Bankura under Jal Jeevan Mission Program under Bishnupur Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001209/2023-2024 | 483/BQA | 09/02/2024 | 10/03/2024 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 2.82 | 0 | 0 | 75
18 | KALIMPONG |  | Bankura Division | Procurement of Service of Consultants for preparation of DPR of New PWSS for uncovered rural areas of Nadia, Bankura, Paschim Bardhaman and Kalimpong districts. | SM/10564 | Support-M&E | Preparation of Detailed Project Report for Proposed ground water based KATUL pipe water supply scheme, under Bankura Division, Block : Bishnupur, District : Bankura under Jal Jeevan Mission Program under Bishnupur Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001209/2023-2024 | 483/BQA | 09/02/2024 | 10/03/2024 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 2.82 | 0 | 0 | 75
19 | NADIA |  | Bankura Division | Procurement of Service of Consultants for preparation of DPR of New PWSS for uncovered rural areas of Nadia, Bankura, Paschim Bardhaman and Kalimpong districts. | SM/10564 | Support-M&E | Preparation of Detailed Project Report for Proposed ground water based KATUL pipe water supply scheme, under Bankura Division, Block : Bishnupur, District : Bankura under Jal Jeevan Mission Program under Bishnupur Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001209/2023-2024 | 483/BQA | 09/02/2024 | 10/03/2024 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 2.82 | 0 | 0 | 75
20 | PASCHIM BARDHAMAN |  | Bankura Division | Procurement of Service of Consultants for preparation of DPR of New PWSS for uncovered rural areas of Nadia, Bankura, Paschim Bardhaman and Kalimpong districts. | SM/10564 | Support-M&E | Preparation of Detailed Project Report for Proposed ground water based KATUL pipe water supply scheme, under Bankura Division, Block : Bishnupur, District : Bankura under Jal Jeevan Mission Program under Bishnupur Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001209/2023-2024 | 483/BQA | 09/02/2024 | 10/03/2024 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 2.82 | 0 | 0 | 75
21 | BANKURA |  | Bankura Division | Procurement of Service of Consultants for preparation of DPR of New PWSS for uncovered rural areas of Nadia, Bankura, Paschim Bardhaman and Kalimpong districts. | SM/10564 | Support-M&E | Preparation of Detailed Project Report for Proposed ground water based ICHHARIA pipe water supply scheme, under Block : Sonamukhi, District : Bankura under Jal Jeevan Mission Program under Bishnupur Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001208/2023-2024 | 482/BQA | 09/02/2024 | 09/04/2024 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.17 | 0 | 0 | 100
22 | KALIMPONG |  | Bankura Division | Procurement of Service of Consultants for preparation of DPR of New PWSS for uncovered rural areas of Nadia, Bankura, Paschim Bardhaman and Kalimpong districts. | SM/10564 | Support-M&E | Preparation of Detailed Project Report for Proposed ground water based ICHHARIA pipe water supply scheme, under Block : Sonamukhi, District : Bankura under Jal Jeevan Mission Program under Bishnupur Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001208/2023-2024 | 482/BQA | 09/02/2024 | 09/04/2024 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.17 | 0 | 0 | 100
23 | NADIA |  | Bankura Division | Procurement of Service of Consultants for preparation of DPR of New PWSS for uncovered rural areas of Nadia, Bankura, Paschim Bardhaman and Kalimpong districts. | SM/10564 | Support-M&E | Preparation of Detailed Project Report for Proposed ground water based ICHHARIA pipe water supply scheme, under Block : Sonamukhi, District : Bankura under Jal Jeevan Mission Program under Bishnupur Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001208/2023-2024 | 482/BQA | 09/02/2024 | 09/04/2024 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.17 | 0 | 0 | 100
24 | PASCHIM BARDHAMAN |  | Bankura Division | Procurement of Service of Consultants for preparation of DPR of New PWSS for uncovered rural areas of Nadia, Bankura, Paschim Bardhaman and Kalimpong districts. | SM/10564 | Support-M&E | Preparation of Detailed Project Report for Proposed ground water based ICHHARIA pipe water supply scheme, under Block : Sonamukhi, District : Bankura under Jal Jeevan Mission Program under Bishnupur Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001208/2023-2024 | 482/BQA | 09/02/2024 | 09/04/2024 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.17 | 0 | 0 | 100
Total | [13 empty] | 2286.96 | 0 | 0