## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Resource | Additional Cost Requirement for Procurement of Service of Consultants for Preparation of DPR, District - Nadia, Bankura, Paschim Bardhaman, Kalimpong, North-24 Parganas, Purba Medinipur and Jhargram. | SM/18986 |  | Formal order for Preparation of DPR for Schemes under Jal Jeevan Mission in West Bengal. |  |  | ORD/000082/2021-2022 | 1997/RS | 03/11/2021 | 02/05/2022 | NABCONS PRIVATE LIMITED | 5500 | 0 | 0 | 80
2 | JHARGRAM |  | Resource | Additional Cost Requirement for Procurement of Service of Consultants for Preparation of DPR, District - Nadia, Bankura, Paschim Bardhaman, Kalimpong, North-24 Parganas, Purba Medinipur and Jhargram. | SM/18986 |  | Formal order for Preparation of DPR for Schemes under Jal Jeevan Mission in West Bengal. |  |  | ORD/000082/2021-2022 | 1997/RS | 03/11/2021 | 02/05/2022 | NABCONS PRIVATE LIMITED | 5500 | 0 | 0 | 80
3 | KALIMPONG |  | Resource | Additional Cost Requirement for Procurement of Service of Consultants for Preparation of DPR, District - Nadia, Bankura, Paschim Bardhaman, Kalimpong, North-24 Parganas, Purba Medinipur and Jhargram. | SM/18986 |  | Formal order for Preparation of DPR for Schemes under Jal Jeevan Mission in West Bengal. |  |  | ORD/000082/2021-2022 | 1997/RS | 03/11/2021 | 02/05/2022 | NABCONS PRIVATE LIMITED | 5500 | 0 | 0 | 80
4 | NADIA |  | Resource | Additional Cost Requirement for Procurement of Service of Consultants for Preparation of DPR, District - Nadia, Bankura, Paschim Bardhaman, Kalimpong, North-24 Parganas, Purba Medinipur and Jhargram. | SM/18986 |  | Formal order for Preparation of DPR for Schemes under Jal Jeevan Mission in West Bengal. |  |  | ORD/000082/2021-2022 | 1997/RS | 03/11/2021 | 02/05/2022 | NABCONS PRIVATE LIMITED | 5500 | 0 | 0 | 80
5 | NORTH 24 PARGANAS |  | Resource | Additional Cost Requirement for Procurement of Service of Consultants for Preparation of DPR, District - Nadia, Bankura, Paschim Bardhaman, Kalimpong, North-24 Parganas, Purba Medinipur and Jhargram. | SM/18986 |  | Formal order for Preparation of DPR for Schemes under Jal Jeevan Mission in West Bengal. |  |  | ORD/000082/2021-2022 | 1997/RS | 03/11/2021 | 02/05/2022 | NABCONS PRIVATE LIMITED | 5500 | 0 | 0 | 80
6 | PASCHIM BARDHAMAN |  | Resource | Additional Cost Requirement for Procurement of Service of Consultants for Preparation of DPR, District - Nadia, Bankura, Paschim Bardhaman, Kalimpong, North-24 Parganas, Purba Medinipur and Jhargram. | SM/18986 |  | Formal order for Preparation of DPR for Schemes under Jal Jeevan Mission in West Bengal. |  |  | ORD/000082/2021-2022 | 1997/RS | 03/11/2021 | 02/05/2022 | NABCONS PRIVATE LIMITED | 5500 | 0 | 0 | 80
7 | PURBA MEDINIPUR |  | Resource | Additional Cost Requirement for Procurement of Service of Consultants for Preparation of DPR, District - Nadia, Bankura, Paschim Bardhaman, Kalimpong, North-24 Parganas, Purba Medinipur and Jhargram. | SM/18986 |  | Formal order for Preparation of DPR for Schemes under Jal Jeevan Mission in West Bengal. |  |  | ORD/000082/2021-2022 | 1997/RS | 03/11/2021 | 02/05/2022 | NABCONS PRIVATE LIMITED | 5500 | 0 | 0 | 80
8 | SOUTH 24 PARGANAS |  | Resource | Additional Cost Requirement for Procurement of Service of Consultants for Preparation of DPR, District - Nadia, Bankura, Paschim Bardhaman, Kalimpong, North-24 Parganas, Purba Medinipur and Jhargram. | SM/18986 |  | Formal order for Preparation of DPR for Schemes under Jal Jeevan Mission in West Bengal. |  |  | ORD/000082/2021-2022 | 1997/RS | 03/11/2021 | 02/05/2022 | NABCONS PRIVATE LIMITED | 5500 | 0 | 0 | 80
Total | [13 empty] | 44000 | 0 | 0