## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURULIA |  | Purulia Division | Arrangement for drinking water supply through FHTC to meet up the acute crisis by extending distribution line to Surulia Village from existing Bongabari WSS under Jalswapna Programme. | SM/06826 | Augmentation | Arrangement for drinking water supply through FHTC to meet up the acute crisis by extending distribution line to Surulia Village from existing Bongabari W/s Scheme under Jal Swapna Programme. (Tender No. 14/SE/PMU of 2020-21) |  |  | VCH/000892/2020-2021 | 448/8443187 | 30/03/2021 | 30/03/2021 | SWAPAN MANDAL | 26.54 | 0 | 0 | 0
2 | PURULIA |  | Purulia Division | Arrangement for drinking water supply through FHTC to meet up the acute crisis by extending distribution line to Surulia Village from existing Bongabari WSS under Jalswapna Programme. | SM/06826 | Augmentation | Re-Sinking of No-1 Tube-well 200mm 200mm dia river bed tube-well at riverbed of Kansai at Pindra site of Bongabari W/s Scheme. (Tender No. 868/EE/PD of 2019-20) |  |  | VCH/000229/2021-2022 | 95/8443116 | 19/07/2021 | 19/07/2021 | SANTANU BANERJEE | 0.45 | 0 | 0 | 0
3 | PURULIA |  | Purulia Division | Arrangement for drinking water supply through FHTC to meet up the acute crisis by extending distribution line to Surulia Village from existing Bongabari WSS under Jalswapna Programme. | SM/06826 | Augmentation | Laying of HDPE pipe & distribution main (loop line) from Surulia Roads side Hari Mandir to Surulia Shiv Mandir in Surulia village for deinking water supply through FHTC to metup the water crisis at upar Surulia village from existing Bongabari W/s Scheme under Jaal Swapna Programme. (Tender No.1031/EE/PD of 2021-22) |  |  | VCH/001055/2021-2022 | 368/8443191 | 31/03/2022 | 31/03/2022 | SOUVIK MANDAL | 4.29 | 0 | 0 | 0
4 | PURULIA |  | Purulia Division | Arrangement for drinking water supply through FHTC to meet up the acute crisis by extending distribution line to Surulia Village from existing Bongabari WSS under Jalswapna Programme. | SM/06826 | Augmentation | Arrangement of drinking water supply through FHTC to meet up the acute crisis by extending distribution like to Surulia village from existing Bongabari W/s Scheme under Jalswapna Programe. (Tender No.567/EE/PD of 2021-22) |  |  | VCH/000727/2021-2022 | 264/8443156/1 | 20/12/2021 | 20/12/2021 | SWAPAN MANDAL | 4.27 | 0 | 0 | 0
5 | PURULIA |  | Purulia Division | Arrangement for drinking water supply through FHTC to meet up the acute crisis by extending distribution line to Surulia Village from existing Bongabari WSS under Jalswapna Programme. | SM/06826 | Augmentation | Arrangement of drinking water supply through FHTC to meet up the acute crisis by extending distribution like to Surulia village from existing Bongabari W/s Scheme under Jalswapna Programe. (Tender No.14/EE/PD of 2020-21) |  |  | VCH/000728/2021-2022 | 264/8443156/2 | 20/12/2021 | 20/12/2021 | SWAPAN MANDAL | 13.72 | 0 | 0 | 0
6 | PURULIA |  | Purulia Division | Arrangement for drinking water supply through FHTC to meet up the acute crisis by extending distribution line to Surulia Village from existing Bongabari WSS under Jalswapna Programme. | SM/06826 | Augmentation | Construction of Guard Room & boundarry wall near Guest House Campus and with drawing and relaying of CI pipes under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/001022/2022-2023 | 184/PD | 07/02/2023 | 18/05/2023 | MANATOSH SINGH | 4.19 | 0 | 0 | 0
7 | PURULIA |  | Purulia Division | Arrangement for drinking water supply through FHTC to meet up the acute crisis by extending distribution line to Surulia Village from existing Bongabari WSS under Jalswapna Programme. | SM/06826 | Augmentation | Arrangement for drinking water supply through FHTC to meet up the acute crisis by extending distribution line to Surulia Village from existing Bongabari W/S Scheme under Jalswapna Programme under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000159/2020-2021 | 1412/PD | 29/12/2020 | 12/02/2021 | SWAPAN MANDAL | 68.85 | 6.6 | 9.58 | 100
8 | PURULIA |  | Purulia Division | Arrangement for drinking water supply through FHTC to meet up the acute crisis by extending distribution line to Surulia Village from existing Bongabari WSS under Jalswapna Programme. | SM/06826 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at Uppar Pindra Village of Pindra G.P. under command area of Bongabari Water Supply Scheme at Purulia-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000112/2022-2023 | 648/PD | 22/04/2022 | 06/06/2022 | KABERI DUTTA | 9.84 | 0 | 0 | 100
9 | PURULIA |  | Purulia Division | Arrangement for drinking water supply through FHTC to meet up the acute crisis by extending distribution line to Surulia Village from existing Bongabari WSS under Jalswapna Programme. | SM/06826 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at Surulia Village Bauri Para of Raghabpur G.P. under command area of Bongabari Water Supply Scheme at Purulia-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-1 | ORD/000623/2022-2023 | 1390/PD | 01/09/2022 | 16/10/2022 | SOUVIK MANDAL | 23.21 | 0 | 0 | 100
Total | [13 empty] | 155.37 | 6.6 | 4.25