## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURULIA |  | Purulia Division | Retrofitting of Beldi Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/06940 | Retrofitting | Retrofitting of Beldi W/s Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under Jal Sapna Programme (Habitation Covered Beldi, Bhursha, Kumirkuli, Domepara, Goaladih Jatratar) Part-A (Tender No. 8/SE/PMU of 2020-21) |  |  | VCH/000819/2020-2021 | 387/844341 | 08/03/2021 | 08/03/2021 | BOSE CONSTRUCTION | 31.34 | 0 | 0 | 0
2 | PURULIA |  | Purulia Division | Retrofitting of Beldi Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/06940 | Retrofitting | Retrofitting of Beldi water supply scheme at Arsha Block of Purulia Sadar Sub-Division for Providing Functional House Hold Tap connection (FHTC) under JAL SWAPNA Program (Habitation covered Beldi, Bursha Kalimati, Dome Para, Goaladih ...) Part-A. (Tender No.08/SE/PMU of 2020-21) |  |  | VCH/000380/2021-2022 | 158/8443209 | 17/09/2021 | 17/09/2021 | BOSE CONSTRUCTION | 10.57 | 0 | 0 | 0
3 | PURULIA |  | Purulia Division | Retrofitting of Beldi Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/06940 | Retrofitting | Retrofitting of Beldi W/s Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under Jal Sapna Programme (Habitation Covered Tumba Jhalda, Gouradag & Jharidih) Part-B (Tender No. 191/EE/PD of 2020-21) |  |  | VCH/000815/2020-2021 | 378/84432 | 01/03/2021 | 01/03/2021 | SUSANTA KR DUTTA | 28.44 | 0 | 0 | 0
4 | PURULIA |  | Purulia Division | Retrofitting of Beldi Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/06940 | Retrofitting | Repairing & restoration of the damaged elevated watch reservoir ...under Beldi water supply scheme. (Tender No.08/EE/PD of 2022-23) (Ad-interim) |  |  | VCH/000830/2022-2023 | 127/8443195 | 28/09/2022 | 28/09/2022 | KOUSHIK CHATTERJEE | 5.5 | 0 | 0 | 0
5 | PURULIA |  | Purulia Division | Retrofitting of Beldi Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/06940 | Retrofitting | Additional pipe line of 20mm HDPE (OD) for the work of FHTC of Beldi W/s Scheme at Arsha Block Providing of FHTC under Jal Swapna Programe. (Habitation Name: Tumba Jhalda Goradag) (Tender No.191/EE/PD of 2020-21) |  |  | VCH/000970/2021-2022 | 301/8443105/2 | 18/02/2022 | 18/02/2022 | SUSANTA KR DUTTA | 2.88 | 0 | 0 | 0
6 | PURULIA |  | Purulia Division | Retrofitting of Beldi Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/06940 | Retrofitting | Additional estimate for retrofitting of Beldi Water supply scheme for FHTC in connection with Jal Swapna Project at Arsha Block. (Tender No.324/EE/PD of 2021-22) |  |  | VCH/001060/2021-2022 | 342/8443126/2 | 22/03/2022 | 22/03/2022 | BOSE CONSTRUCTION | 2.83 | 0 | 0 | 0
7 | PURULIA |  | Purulia Division | Retrofitting of Beldi Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/06940 | Retrofitting | Extension of distribution pipeline Providing FHTC under Jal Sapna Programme of Beldi W/S Scheme under Purulia Division PHE Dte. (Habitation Name:-Tumba Jhalda, Gouradag, Jhariadih) (Tender No.878/EE/PD of 2021-22) |  |  | VCH/001052/2021-2022 | 342/8443126/1 | 22/03/2022 | 22/03/2022 | BOSE CONSTRUCTION | 5.26 | 0 | 0 | 0
8 | PURULIA |  | Purulia Division | Retrofitting of Beldi Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/06940 | Retrofitting | Retrofitting of Beldi Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for Providing Functional Household Tap Connection (FHTC) under JAL SAPNA programme under Purulia Division, PHE Dte. (Habitation covered Tumba-Jhalda, Gouradag & Jhariadih) Part-B (Tender No.191/EE/PD of 2020-21) |  |  | VCH/000969/2021-2022 | 301/8443105/1 | 18/02/2022 | 18/02/2022 | SUSANTA KR DUTTA | 1.97 | 0 | 0 | 0
9 | PURULIA |  | Purulia Division | Retrofitting of Beldi Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/06940 | Retrofitting | Retrofitting of Beldi Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for Providing Functional Household Tap Connection (FHTC) under JAL SAPNA programme under Purulia Division, PHE Dte. (Habitation covered Beldi, Bhursa, Kumirkuli, Domepara, Goaladih & Jatratanr) Part-A | Assistant Engineer |  | ORD/000157/2020-2021 | 1410/PD | 29/12/2020 | 12/02/2021 | BOSE CONSTRUCTION | 43.92 | 0 | 0 | 0
10 | PURULIA |  | Purulia Division | Retrofitting of Beldi Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/06940 | Retrofitting | Retrofitting of Beldi Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for Providing Functional Household Tap Connection (FHTC) under JAL SAPNA programme under Purulia Division, PHE Dte. (Habitation covered Tumba-Jhalda, Gouradag & Jhariadih) Part-B | Assistant Engineer | Junior Engineer-3 | ORD/000114/2020-2021 | 1241/PD | 01/12/2020 | 15/01/2021 | SUSANTA KR DUTTA | 42.97 | 7.3 | 16.98 | 0
Total | [13 empty] | 175.68 | 7.3 | 4.15