## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURULIA |  | Purulia Division | Retrofitting of Kudagara Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/06941 | Retrofitting | Retrofitting of Kudagara W/s Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under Jal Sapna Programme (Habitation Covered Kudagar & Bamundiha) Part-A (Tender No. 12/SE/PMU of 2020-21) |  |  | VCH/000914/2020-2021 | 419/8443127 | 18/03/2021 | 18/03/2021 | GOUTAM CHAKRABORTY | 28.55 | 0 | 0 | 0
2 | PURULIA |  | Purulia Division | Retrofitting of Kudagara Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/06941 | Retrofitting | Retrofitting of Kudagara W/s Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional house hold tap connection (FHTC) under Jal Swapna Programme under Purulia Division PHE Dte. (Habitation covered: Gourangdi, Manpur, Kanchanpur & Juradi) Part-B. (Tender No. 195/EE/PD of 2020-21) |  |  | VCH/000906/2020-2021 | 437/8443179 | 27/03/2021 | 27/03/2021 | HIRAK KUMAR SAO | 11.08 | 0 | 0 | 0
3 | PURULIA |  | Purulia Division | Retrofitting of Kudagara Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/06941 | Retrofitting | FHTC water tap connection in each house hold from existing distribution system within scheme jurisdiction in Gourangdi, Manpur, Kanchanpur & Juradi Mouza of Kudagara Piped W/s Scheme (Phase-2) (Tender No.422/EE/PD of 2020-21) |  |  | VCH/000408/2021-2022 | 142/844349/1 | 08/09/2021 | 08/09/2021 | HIRAK KUMAR SAO | 3.03 | 0 | 0 | 0
4 | PURULIA |  | Purulia Division | Retrofitting of Kudagara Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/06941 | Retrofitting | Retrofitting of Khudagara W/s Scheme at Arsha Block of Purulia Sadar Sub-Division for Providing Functional Household Tap Connection (FHTC) under JAL SAPNA program (Habitation covered: Gourangdi, Manpur, Kanchanpur & Juradi) Part-B (Tender No.195/EE/PD of 2020-21) |  |  | VCH/000409/2021-2022 | 142/844349/2 | 08/09/2021 | 08/09/2021 | HIRAK KUMAR SAO | 1.83 | 0 | 0 | 0
5 | PURULIA |  | Purulia Division | Retrofitting of Kudagara Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/06941 | Retrofitting | FHTC water tap connection ineach house hold from existing distribution system within scheme jurisdiction in Kudagara & Bamundiha Mouza of Khudagar Piped Water Supply Scheme with in Purulia Sadar Sub-Division under Purulia Division, PHE Dte. (Phase-2) (Tender No. 408/SE/PMU of 2020-21) |  |  | VCH/000423/2021-2022 | 137/84433/2 | 01/09/2021 | 01/09/2021 | M/S CHAKRABORTY CONSTRUCTION | 4.28 | 0 | 0 | 0
6 | PURULIA |  | Purulia Division | Retrofitting of Kudagara Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/06941 | Retrofitting | Retrofitting of Kudagara Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for Providing Functional Household Tap Connection (FHTC) under JAL SAPNA programme under Purulia Division, PHE Dte. (Habitation covered Gourangdih, Manpur, Kanchanpur & Juradi) Part-B | Assistant Engineer | Junior Engineer-3 | ORD/000116/2020-2021 | 1242/PD | 01/12/2020 | 15/01/2021 | HIRAK KUMAR SAO | 16.01 | 0 | 0 | 0
7 | PURULIA |  | Purulia Division | Retrofitting of Kudagara Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/06941 | Retrofitting | Retrofitting of Kudagara Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for Providing Functional Household Tap Connection (FHTC) under JAL SAPNA programme under Purulia Division, PHE Dte. (Habitation covered Kudagara & Bamandia) Part-A | Assistant Engineer |  | ORD/000158/2020-2021 | 1411/PD | 29/12/2020 | 12/02/2021 | GOUTAM CHAKRABORTY | 47.17 | 21.19 | 44.93 | 0
8 | PURULIA |  | Purulia Division | Retrofitting of Kudagara Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/06941 | Retrofitting | New sinking of 4 (Four) nos 200mm dia riverbed tube wells (Horizontal) at river bed of Kansai along with laying of 100 mm dia GI connecting line with all allied works at Puncha river site of Puncha W/S Scheme under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-3 | ORD/000365/2021-2022 | 150/PD | 24/01/2022 | 10/03/2022 | KOUSHIK CHATTERJEE | 25.5 | 2.33 | 9.14 | 100
9 | PURULIA |  | Purulia Division | Retrofitting of Kudagara Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/06941 | Retrofitting | Emergent Repairing of 100 mm dia Collecting line damaged due to flash flood in connection with Jal Jeevan Mission (JJM) under Kudagara W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. | Assistant Engineer | Junior Engineer-3 | ORD/001016/2022-2023 | 185/PD | 07/02/2023 | 22/02/2023 | ANGEL LABOUR CONTRACT & CONSTRUCTION CO OPERATIVE SOCIETY LTD | 3.7 | 3.66 | 98.96 | 100
10 | PURULIA |  | Purulia Division | Retrofitting of Kudagara Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/06941 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at Satra village of Hensla G.P. under command area of Satra Water Supply Scheme at Arsha Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. (Part-K) | Assistant Engineer | Junior Engineer,Junior Engineer-1 | ORD/000249/2020-2021 | 23/PSD | 13/01/2021 | 27/02/2021 | SIDDHARTHA SANKAR SARKAR | 3.63 | 0.16 | 4.47 | 100
11 | PURULIA |  | Purulia Division | Retrofitting of Kudagara Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/06941 | Retrofitting | Emergency piling work along with sand filling at collecting line treanches for protection work against flash flood Khudagara W/S Scheme under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001479/2023-2024 | 1790/PD | 08/12/2023 | 06/02/2024 | ANGEL LABOUR CONTRACT & CONSTRUCTION CO OPERATIVE SOCIETY LTD | 39.43 | 0 | 0 | 100
Total | [13 empty] | 184.19 | 27.35 | 14.85