## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURULIA |  | Purulia Division | Retrofitting of Baram Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/06942 | Retrofitting | Retrofitting of Baram water supply scheme at Arsha Block of Purulia Sadar-Sub Division for providing functional house hold Tap connection (FHTC) under Jal Sapna program (Habitation covered Baram, Thakushima, Bridhistarh, Jharatar) Part-A. (Tender No. 9/SE/PMU of 2020-21) |  |  | VCH/000741/2020-2021 | 369/8443218 | 25/02/2021 | 25/02/2021 | KOUSHIK CHATTERJEE | 28.91 | 0 | 0 | 0
2 | PURULIA |  | Purulia Division | Retrofitting of Baram Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/06942 | Retrofitting | Retrofitting of Boram W/s Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under Jal Sapna Programme (Habitation Covered Mankiyari, Torang, Matkumpiri, Raipur, Jibandity) Part-B. (Tender No. 160/EE/PD of 2020-21) |  |  | VCH/000820/2020-2021 | 386/844340 | 08/03/2021 | 08/03/2021 | SOUMITRA CHAKRABORTY | 20.9 | 0 | 0 | 0
3 | PURULIA |  | Purulia Division | Retrofitting of Baram Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/06942 | Retrofitting | Extention of distribution pipeline for providing FHTC under Jal Sapna Programme of Baram W/S Scheme under Purulia Division PHE Dte. (Habitation Name:-Mankiary,Gundligora,Matkampiri, Torang) (Tender No.875/EE/PD of 2021-22) |  |  | VCH/000823/2022-2023 | 133/8443221/2 | 29/09/2022 | 29/09/2022 | SOUMITRA CHAKRABORTY | 0.44 | 0 | 0 | 0
4 | PURULIA |  | Purulia Division | Retrofitting of Baram Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/06942 | Retrofitting | Extention of distribution pipeline for providing FHTC under Jal Sapna Programme of Baram W/S Scheme under Purulia Division PHE Dte. (Habitation Name:-Baram,Thakurshima,Briddhitanr,Jaratanr) (Tender No.874/EE/PD of 2021-22) |  |  | VCH/000822/2022-2023 | 133/8443221/1 | 29/09/2022 | 29/09/2022 | SOUMITRA CHAKRABORTY | 1.2 | 0 | 0 | 0
5 | PURULIA |  | Purulia Division | Retrofitting of Baram Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/06942 | Retrofitting | Retrofitting of Baram Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for Providing Functional Household Tap Connection (FHTC) under JAL SAPNA programme under Purulia Division, PHE Dte. (Habitation covered Mankiyari, Torang, Matkompiri, Raipur, Jibandih & Gundligora) Part-B (Tender No.160/EE/PD of 2020-21) |  |  | VCH/000895/2021-2022 | 278/844393/2 | 14/01/2022 | 14/01/2022 | SOUMITRA CHAKRABORTY | 5.64 | 0 | 0 | 0
6 | PURULIA |  | Purulia Division | Retrofitting of Baram Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/06942 | Retrofitting | Laying of additional pipeline of 20mm HDPE (OD) for the work of Baram Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for Providing Functional Household Tap Connection (FHTC) under JAL SAPNA programme under Purulia Division, PHE Dte. (Habitation covered Mankiyari, Torang, Matkompiri, Raipur, Jibandih & Gundligora) Part-B (Tender No.721/EE/PD of 2020-21) |  |  | VCH/000894/2021-2022 | 278/844393/1 | 14/01/2022 | 14/01/2022 | SOUMITRA CHAKRABORTY | 2.62 | 0 | 0 | 0
7 | PURULIA |  | Purulia Division | Retrofitting of Baram Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/06942 | Retrofitting | Retrofitting of Baram Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for Providing Functional Household Tap Connection (FHTC) under JAL SAPNA programme under Purulia Division, PHE Dte. (Habitation covered Baram, Thakurshima, Briddhitanr & Joratanr) Part-A | Assistant Engineer |  | ORD/000156/2020-2021 | 1409/PD | 29/12/2020 | 12/02/2021 | KOUSHIK CHATTERJEE | 48.17 | 8.62 | 17.91 | 0
8 | PURULIA |  | Purulia Division | Retrofitting of Baram Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/06942 | Retrofitting | Searching report of land & Retainer Service by Regional Advocate(s) for direct purchase of land for public purpose by Dept. through Zilla Parisad from Intending owners WTP for surface based piped water supply scheme for Purulia District under Division PHE Dte. |  |  | BILL/02079/2023-2024 | 9/2024-25 | 09/04/2024 | 09/04/2024 | RANJEET CHATTERJEE | 1.97 | 0 | 0 | 0
Total | [13 empty] | 109.85 | 8.62 | 7.85