## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURULIA |  | Purulia Division | Retrofitting of Arrah Water Supply Scheme at Raghunathpur-I & Kashipur Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/07563 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara/Jal Sapna under command area of Arrah Water Supply Scheme at Raghunathpur -I Block under Purulia Division, PHE Dte.(Mouza-Arrah , Habitation-Gosaidanga,Jhariardi , Kamalasthan) (Tender No. 37/SE/PMU of 2020-21) |  |  | VCH/000949/2021-2022 | BP-2021-22-247 | 16/02/2022 | 16/02/2022 | PREMNATH MITRA | 29.4 | 0 | 0 | 0
2 | PURULIA |  | Purulia Division | Retrofitting of Arrah Water Supply Scheme at Raghunathpur-I & Kashipur Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/07563 | Retrofitting | Additional works for functional house hold tap connection (FHTC) including other allied works of Augmentation Arrah W/s Scheme (Zone-II) of Kashipur Block. (Tender No. 853/EE/PD of 2021-22) |  |  | VCH/001005/2021-2022 | BP-2021-22-264 | 28/02/2022 | 28/02/2022 | SHYAMAL KUMAR DEY | 4.53 | 0 | 0 | 0
3 | PURULIA |  | Purulia Division | Retrofitting of Arrah Water Supply Scheme at Raghunathpur-I & Kashipur Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/07563 | Retrofitting | Additional work for functional Household Tap Connection (FHTC) including other allied works of Aug. Arrah Water Supply Scheme of Raghunathpur Sub Division under Purulia Division, PHE Dte. (Zone-II) Gagnabad (Part-B) (Tender No.856/EE/PD of 2021-22) |  |  | VCH/001021/2021-2022 | BP-2021-22-265 | 28/02/2022 | 28/02/2022 | M/S KARUNAMOYEE CONSTRUCTION | 3.73 | 0 | 0 | 0
4 | PURULIA |  | Purulia Division | Retrofitting of Arrah Water Supply Scheme at Raghunathpur-I & Kashipur Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/07563 | Retrofitting | Supply & laying different dia HDPE pipe line Adra DHR to Gosaidanga under Arrah W/s Scheme. (Tender No.919/EE/PD of 2021-22) |  |  | VCH/001115/2021-2022 | BP-2021-22-342 | 25/03/2022 | 25/03/2022 | RABIN CHANDRA CHAIL | 21.59 | 0 | 0 | 0
5 | PURULIA |  | Purulia Division | Retrofitting of Arrah Water Supply Scheme at Raghunathpur-I & Kashipur Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/07563 | Retrofitting | Supplying & Laying different dia HDPE pipe line from Arra OHR to lower Beniasole under Arra W/S Scheme (Tender No- 927/2021-22 of EE/PD) |  |  | VCH/001111/2021-2022 | BP-2021-22-371 | 29/03/2022 | 29/03/2022 | RABIN CHANDRA CHAIL | 37.14 | 0 | 0 | 0
6 | PURULIA |  | Purulia Division | Retrofitting of Arrah Water Supply Scheme at Raghunathpur-I & Kashipur Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/07563 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara/Jal Sapna under command area of Arrah Water Supply Scheme at Raghunathpur -I Block under Purulia Division, PHE Dte.(Mouza-Arrah , Habitation-Arrah,Barabagan) | Assistant Engineer | Junior Engineer | ORD/000291/2020-2021 | 180/PD | 02/02/2021 | 19/03/2021 | SADHAN GORAIN | 131.09 | 60.43 | 46.1 | 100
7 | PURULIA |  | Purulia Division | Retrofitting of Arrah Water Supply Scheme at Raghunathpur-I & Kashipur Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/07563 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara/Jal Sapna under command area of Arrah Water Supply Scheme at Kashipur Block under Purulia Division, PHE Dte.(Mouza-Gagnabad , Habitation-Bauripara, Gagnabaid ,Kalu Para ,Pakhirdanga Mouza-Ghorakata(P)Habitation-Ghorakata , Mouza-Jhariatdi (P),Habitation-Jhriadihi,Mouza-Manpura , Habitation-Ganpandi,Manpura, Mouza-Narayangar Alias Karka, Habitation-Kanka,Narayan Nagar.) | Assistant Engineer |  | ORD/000154/2020-2021 | 1407/PD | 29/12/2020 | 12/02/2021 | M/S KARUNAMOYEE CONSTRUCTION | 55.9 | 111.64 | 199.72 | 0
8 | PURULIA |  | Purulia Division | Retrofitting of Arrah Water Supply Scheme at Raghunathpur-I & Kashipur Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/07563 | Retrofitting | Laying of HDPE pipe (PE-100, PN-10) for collecting line of riverbed Intake Well (for 1 & 2) at Narayangarh under Arrah W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000179/2023-2024 | 995/PD | 26/07/2023 | 24/09/2023 | RABIN CHANDRA CHAIL | 6.21 | 5.38 | 86.57 | 100
Total | [13 empty] | 289.58 | 177.44 | 61.28