## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURULIA |  | Purulia Division | Retrofitting of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/07564 | Retrofitting | Functional Household Tap Connection (FHTC) including other allied works of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. at Mouza - Baltora , Habitation - Mathorgoria (30 Nos.),Baltora (82 Nos.) | Assistant Engineer |  | ORD/000207/2020-2021 | 24/RNP | 11/01/2021 | 26/01/2021 | KANAILAL PAL | 4.78 | 0.18 | 3.79 | 100
2 | PURULIA |  | Purulia Division | Retrofitting of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/07564 | Retrofitting | Functional Household Tap Connection (FHTC) including other allied works of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. at Mouza -Dhanasdi, Habitation - Dhanasdi (84 Nos.), Mouza-Ektira, Habitation - Ektira (28 Nos.) | Assistant Engineer |  | ORD/000231/2020-2021 | 29/RNP | 11/01/2021 | 26/01/2021 | KABERI DUTTA | 4.78 | 4.44 | 92.79 | 100
3 | PURULIA |  | Purulia Division | Retrofitting of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/07564 | Retrofitting | Functional house hold tap connection (FHTC) including other allied works of under Balotora W/s Scheme of Santuri Block of mouza Monpur (112 Nos). (Tender No. 286/EE/PD of 2020-21) |  |  | VCH/000068/2021-2022 | 17/844362/1 | 21/04/2021 | 21/04/2021 | CHAIL CONSTRUCTION | 4.44 | 0 | 0 | 0
4 | PURULIA |  | Purulia Division | Retrofitting of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/07564 | Retrofitting | FHTC including other allied works of Balitora water supply scheme at Santuri Block at Mouza-Balitora, Habitation (108 Nos) (Tender No. 288/EE/PD of 2020-21) (Ad-interim) |  |  | VCH/000126/2021-2022 | 70/844369 | 18/06/2021 | 18/06/2021 | NANIGOPAL DEY | 1.86 | 0 | 0 | 0
5 | PURULIA |  | Purulia Division | Retrofitting of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/07564 | Retrofitting | Functional house hold tap connection (FHTC) including other allied works of Balitora W/s Scheme at Santuri Block (Tender No. 363/PD of 2020-21) |  |  | VCH/000128/2021-2022 | 59/844323 | 08/06/2021 | 08/06/2021 | SUPRIYA MAHANTI MISHRA | 4.76 | 0 | 0 | 0
6 | PURULIA |  | Purulia Division | Retrofitting of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/07564 | Retrofitting | Functional Household Tap Connection (FHTC) including other allied works of Balitora W/S Scheme at Santuri Block at Mouza- Balitora, Habitation- Balitora (108 Nos.) (Tender No:- 288/EE/PD of 2020-21) |  |  | VCH/000119/2021-2022 | BP-2021-22-50 | 20/07/2021 | 20/07/2021 | NANIGOPAL DEY | 2.18 | 0 | 0 | 0
7 | PURULIA |  | Purulia Division | Retrofitting of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/07564 | Retrofitting | Functional Household Tap Connection (FHTC) including other allied works of Baltora W/S Scheme at Santuri Block of Raghunathpur Sub- Division PHE Dte. at Mouza- Dandahit, Habitation- Dandahit (108 Nos.) (Tender No:- 414/EE/PD of 2020-21) |  |  | VCH/000215/2021-2022 | BP-2021-22-86 | 23/08/2021 | 23/08/2021 | ASHOK KUMAR CHATTERJEE | 4.79 | 0 | 0 | 0
8 | PURULIA |  | Purulia Division | Retrofitting of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/07564 | Retrofitting | Functional Household Tap Connection (FHTC) including other allied works of Balitora W/S Scheme at Santuri Block of Raghunathpur Sub-Division under Purulia Division, PHE Dte. at Mouza- Bakuliashota, Habitation-Bakulia (16 Nos.), Mouza- Santuri, Habitation- Uppardih (46 Nos.) Mouza- Ektira, Habitation- Berakural-(1), Ektira (48 Nos.) Mouza-Kastagora Habitation- Chapabera Chak-(1) (Tender No.342/EE/PD of 2020-21) |  |  | VCH/000385/2021-2022 | BP-2021-22-131 | 11/10/2021 | 11/10/2021 | MS MITRA SENGUPTA ENTERPRISES | 4.63 | 0 | 0 | 0
9 | PURULIA |  | Purulia Division | Retrofitting of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/07564 | Retrofitting | Functional Household Tap Connection (FHTC) including other allied works of Balitora W/S Scheme at Santuri Block of Raghunathpur Sub-Division under Purulia Division, PHE Dte. at Mouza- Bakuliashota, Habitation-Bakulia (112 Nos.) (Tender No.276/EE/PD of 2020-21) |  |  | VCH/000386/2021-2022 | BP-2021-22-132 | 11/10/2021 | 11/10/2021 | DEB SHANKAR LAYEK | 4.54 | 0 | 0 | 0
10 | PURULIA |  | Purulia Division | Retrofitting of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/07564 | Retrofitting | Functional Household Tap Connection (FHTC) including other allied works of Baltora W/S Scheme at Santuri Block of Raghunathpur Sub- Division PHE Dte. at Mouza- Deuli, Habitation- Deuli (70 Nos.) Mouza- Sunuri, Habitaion- Sunuri (42 Nos.) (Tender No:- 348/EE/PD of 2020-21) |  |  | VCH/000216/2021-2022 | BP-2021-22-95 | 23/08/2021 | 23/08/2021 | SK ABBAS | 3.61 | 0 | 0 | 0
11 | PURULIA |  | Purulia Division | Retrofitting of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/07564 | Retrofitting | Functional Household Tap Connection (FHTC) including other allied works of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. at Mouza- Madhukunda Alias Mokura, Habitation- Madhukunda Alias Mokura (86 Nos.) Mouza-Saspur, Habitation-Saspur (26 Nos.) (Tender No.302/EE/PD of 2020-21) |  |  | VCH/000185/2021-2022 | BP-2021-22-87 | 23/08/2021 | 23/08/2021 | SUBRATA SINGHADEO | 4.53 | 0 | 0 | 0
12 | PURULIA |  | Purulia Division | Retrofitting of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/07564 | Retrofitting | Functional Household Tap Connection (FHTC) including other allied works of Balitora W/s Scheme at Santuri Block within Raghunathpur Sub-Division under Purulia Division PHE Dte. Mouza- Santuri, Habitation-Santuri (112 Nos.) (Tender No. 295/EE/PD of 2020-21) |  |  | VCH/000809/2020-2021 | 11/844325/2 | 12/04/2021 | 12/04/2021 | M/S SAYAK BHATTACHARYA | 4.66 | 0 | 0 | 0
13 | PURULIA |  | Purulia Division | Retrofitting of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/07564 | Retrofitting | Functional Household Tap Connection (FHTC) including other allied works of Baltora W/s Scheme at Santuri Block of Raghunathpur Sub-Division at Mouza- Baltora, Habitation- Baltora (51 Nos), Mouza- Santuri, Habitation- Santuri (61 Nos), (Tender No:- 299/EE/PD of 2020-21) |  |  | VCH/000332/2021-2022 | BP-2021-22-118 | 11/10/2021 | 11/10/2021 | SUBRATA SINGHADEO | 3.55 | 0 | 0 | 0
14 | PURULIA |  | Purulia Division | Retrofitting of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/07564 | Retrofitting | Functional Household Tap Connection (FHTC) including other allied works of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. at (Balitora, Habitation- Balitora). (112 Nos.) (Tender No.305/EE/PD of 2020-21) |  |  | VCH/000173/2021-2022 | BP-2021-22-67 | 12/08/2021 | 12/08/2021 | TUMPA GORAIN | 4.52 | 0 | 0 | 0
15 | PURULIA |  | Purulia Division | Retrofitting of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/07564 | Retrofitting | Functional Household Tap Connection (FHTC) including other allied works of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. at Mouza-Dandahit, Habitation- Dandahit). (112 Nos.) (Tender No.279/EE/PD of 2021-22) |  |  | VCH/000178/2021-2022 | BP-2021-22-68 | 12/08/2021 | 12/08/2021 | SIKHA ENTERPRISES | 4.77 | 0 | 0 | 0
16 | PURULIA |  | Purulia Division | Retrofitting of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/07564 | Retrofitting | Functional house hold tap connection (FHTC) including other allied works of under Balotora W/s Scheme of Santuri Block of mouza Monpur (88 Nos). (Tender No. 281/EE/PD of 2020-21) |  |  | VCH/000069/2021-2022 | 17/844362/2 | 21/04/2021 | 21/04/2021 | SUDHANSHU OJHA | 4.4 | 0 | 0 | 0
17 | PURULIA |  | Purulia Division | Retrofitting of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/07564 | Retrofitting | Functional Household Tap Connection (FHTC) including other allied works of Baltora W/s Scheme at Santuri Block of Raghunathpur Sub-Division at Mouza- Kashatagora, Habitation- Kashatagora (112 Nos) (Tender No:- 271/EE/PD of 2020-21) |  |  | VCH/000331/2021-2022 | BP-2021-22-116 | 11/10/2021 | 11/10/2021 | KHITISH CHANDRA PATHAK | 4.43 | 0 | 0 | 0
18 | PURULIA |  | Purulia Division | Retrofitting of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/07564 | Retrofitting | Functional Household Tap Connection (FHTC) including other allied works of Balitora W/S Scheme at Santuri Block at Mouza- Jagannathdi, Habitation-Jagannathdi (09 Nos.), Mouza- Kshatagora Habitation - Kshatagora (11 nos), Mouza- Manpur, Habitation- Manpur (46 Nos.), Siyal Danga (39) (Tender No:- 283/EE/PD of 2020-21) |  |  | VCH/000120/2021-2022 | BP-2021-22-51 | 20/07/2021 | 20/07/2021 | SANDIP KUMAR DUBEY | 4.68 | 0 | 0 | 0
19 | PURULIA |  | Purulia Division | Retrofitting of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/07564 | Retrofitting | Functional Household Tap Connection (FHTC) including other allied works of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. at Balitora, Habitation- Mathorgoria (30 Nos.) (82 Nos.) (Tender No.337/EE/PD of 2020-21) |  |  | VCH/000175/2021-2022 | BP-2021-22-66 | 12/08/2021 | 12/08/2021 | KANAILAL PAL | 4.5 | 0 | 0 | 0
20 | PURULIA |  | Purulia Division | Retrofitting of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/07564 | Retrofitting | Functional Household Tap Connection (FHTC) including other allied works of Baltora W/S Scheme at Santuri Block of Raghunathpur Sub- Division PHE Dte. at Mouza- Madhukunda Alias Mokura, Habitation- Madhukunda Alias Mokura (112) Nos. (Tender No:- 362/EE/PD of 2020-21) |  |  | VCH/000213/2021-2022 | BP-2021-22-82 | 23/08/2021 | 23/08/2021 | SUBHAS CHANDRA MAHATO | 4.58 | 0 | 0 | 0
21 | PURULIA |  | Purulia Division | Retrofitting of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/07564 | Retrofitting | DZSGZDG |  |  | VCH/000624/2021-2022 |  | 30/11/2021 | 30/11/2021 | KABERI DUTTA | 1 | 0 | 0 | 0
22 | PURULIA |  | Purulia Division | Retrofitting of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/07564 | Retrofitting | Functional house hold tap connection (FHTC) including other allied works of Balitora W/s Scheme of Santuri Block. (Tender No. 303/EE/PD of 2020-21) |  |  | VCH/000081/2021-2022 | 11/844325/1 | 12/04/2021 | 12/04/2021 | ROY CONSTRUCTION | 4.54 | 0 | 0 | 0
23 | PURULIA |  | Purulia Division | Retrofitting of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/07564 | Retrofitting | Functional Household Tap Connection (FHTC) including other allied works of Balitora W/s Scheme at Santuri Block within Raghunathpur Sub-Division under Purulia Division PHE Dte. Mouza- Santuri, Habitation-Upardih- (63 Nos.) (49 Nos.) (Tender No. 296/EE/PD of 2020-21) |  |  | VCH/000810/2020-2021 | 11/844325/3 | 12/04/2021 | 12/04/2021 | UTTAM KUMAR DUTTA | 4.77 | 0 | 0 | 0
24 | PURULIA |  | Purulia Division | Retrofitting of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/07564 | Retrofitting | Functional Household Tap Connection (FHTC) including other allied works of Baltora W/S Scheme at Santuri Block of Raghunathpur Sub- Division PHE Dte. at Mouza- Sunuri, Habitation- Kapasdanga (35) Sunuri (77) Nos. (Tender No:- 318/EE/PD of 2020-21) |  |  | VCH/000218/2021-2022 | BP-2021-22-84 | 23/08/2021 | 23/08/2021 | KAMAKHYA ENTERPRISE | 4.58 | 0 | 0 | 0
25 | PURULIA |  | Purulia Division | Retrofitting of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/07564 | Retrofitting | Functional Household Tap Connection (FHTC) including other allied works of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. at Mouza- Sashpur, Habitation-Sashpur (112 Nos.) (Tender No.293/EE/PD of 2020-21) |  |  | VCH/000451/2021-2022 | BP-2021-22-174 | 22/11/2021 | 22/11/2021 | PRATIK SAHA | 4.48 | 0 | 0 | 0
26 | PURULIA |  | Purulia Division | Retrofitting of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/07564 | Retrofitting | Functional Household Tap Connection (FHTC) including other allied works of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. at Mouza -Baltora, Habitation -Balitora (51 Nos.), Mouza- Shunuri, Habitation - Sunuri (61 Nos.) | Assistant Engineer |  | ORD/000208/2020-2021 | 25/RNP | 11/01/2021 | 26/01/2021 | SUBRATA SINGHADEO | 4.73 | 0.98 | 20.74 | 100
27 | PURULIA |  | Purulia Division | Retrofitting of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/07564 | Retrofitting | Probable estimate for sifting of ground HDPE & DI pipe line including supplying & DI pipe of Distribution line with allied works from Kapasdanga Village end to Mokra Pry. School through Jagannathdih & Saluni Village under Zone-II of Balitora W/s Scheme. (Tender No.937/EE/PD of 2021-22) |  |  | VCH/001161/2021-2022 | BP-2021-22-363 | 28/03/2022 | 28/03/2022 | KHITISH CHANDRA PATHAK | 16.39 | 0 | 0 | 0
28 | PURULIA |  | Purulia Division | Retrofitting of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/07564 | Retrofitting | Additional work for Functional Household Tap Connection (FHTC) including other allied works of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. at Mouza - Jagannathdi , Habitation - Jagannathdi (9 Nos.), Mouza - Kshatagora , Habitation - Kshatagora (11 Nos.), Mouza -Manpur , Habitation -Manpur (46 Nos.),Siyal Danga(39). (Tender No.812/EE/PD of 2021-22) |  |  | VCH/000810/2021-2022 | BP-2021-22-225 | 03/02/2022 | 03/02/2022 | AMIT PATHAK | 1.6 | 0 | 0 | 0
29 | PURULIA |  | Purulia Division | Retrofitting of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/07564 | Retrofitting | Additional work for Functional Household Tap Connection (FHTC) including other allied works of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. at Mouza -Manpur, Habitation - Manpur (112 Nos.) (Tender No.-824/EE/PD of 2021-22) |  |  | VCH/000809/2021-2022 | BP-2021-22-226 | 03/02/2022 | 03/02/2022 | CHAIL CONSTRUCTION | 1.36 | 0 | 0 | 0
30 | PURULIA |  | Purulia Division | Retrofitting of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/07564 | Retrofitting | Functional Household Tap Connection (FHTC) including other allied works of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. at Mouza - Balitora , Habitation -Salani (36 Nos.), Balitora (72 Nos.) | Assistant Engineer | Junior Engineer | ORD/000176/2020-2021 | 17/RNP | 11/01/2021 | 26/01/2021 | MADHU SUDAN RAKSHIT | 4.62 | 0 | 0 | 0
31 | PURULIA |  | Purulia Division | Retrofitting of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/07564 | Retrofitting | Functional Household Tap Connection (FHTC) including other allied works of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. at Mouza - Dandahit , Habitation - Dandahit (108 Nos.) | Assistant Engineer | Junior Engineer | ORD/000177/2020-2021 | 18/RNP | 11/01/2021 | 26/01/2021 | ASHOK KUMAR CHATTERJEE | 4.83 | 0 | 0 | 0
32 | PURULIA |  | Purulia Division | Retrofitting of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/07564 | Retrofitting | Functional Household Tap Connection (FHTC) including other allied works of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. at Mouza - Jagannathdi , Habitation - Jagannathdi (9 Nos.), Mouza - Kshatagora , Habitation - Kshatagora (11 Nos.), Mouza -Manpur , Habitation -Manpur (46 Nos.),Siyal Danga(39). | Assistant Engineer | Junior Engineer | ORD/000178/2020-2021 | 19/RNP | 11/01/2021 | 26/01/2021 | SANDIP KUMAR DUBEY | 4.81 | 0 | 0 | 0
33 | PURULIA |  | Purulia Division | Retrofitting of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/07564 | Retrofitting | Functional Household Tap Connection (FHTC) including other allied works of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. at Mouza -Bakuliashota, Habitation -Bakulia (16 Nos.), Mouza- Shunuri, Habitation - Uppardi (46 Nos.), Mouza- Ektira, Habitation -Berakural-(1),Ektira (48 Nos.), Mouza- Kashtagora Habitation -Chapabera Chak-(1) | Assistant Engineer | Junior Engineer | ORD/000179/2020-2021 | 20/RNP | 11/01/2021 | 26/01/2021 | MS MITRA SENGUPTA ENTERPRISES | 4.78 | 0 | 0 | 0
34 | PURULIA |  | Purulia Division | Retrofitting of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/07564 | Retrofitting | Functional Household Tap Connection (FHTC) including other allied works of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. at Mouza -Sunuri, Habitation -Uppardi -(63Nos)Sunuri(49Nos.) | Assistant Engineer | Junior Engineer | ORD/000180/2020-2021 | 38/RNP | 11/01/2021 | 26/01/2021 | UTTAM KUMAR DUTTA | 4.78 | 0 | 0 | 0
35 | PURULIA |  | Purulia Division | Retrofitting of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/07564 | Retrofitting | Functional Household Tap Connection (FHTC) including other allied works of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. at Mouza - Bakuliasota , Habitation - Bakulia (112 Nos.) | Assistant Engineer | Junior Engineer | ORD/000190/2020-2021 | 21/RNP | 11/01/2021 | 26/01/2021 | DEB SHANKAR LAYEK | 4.78 | 0 | 0 | 0
36 | PURULIA |  | Purulia Division | Retrofitting of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/07564 | Retrofitting | Supplying & laying different dia HDPE pipe line at Shunuri village of Balitora W/S Scheme of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte.(Part-II) | Assistant Engineer |  | ORD/000141/2021-2022 | 529/RNP | 27/08/2021 | 26/09/2021 | RAHIBUDDIN MONDAL | 4.84 | 4.16 | 85.8 | 100
37 | PURULIA |  | Purulia Division | Retrofitting of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/07564 | Retrofitting | Supplying & laying different dia HDPE pipe line at Shunuri village of Balitora W/S Scheme of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte.(Part-I) | Assistant Engineer |  | ORD/000136/2021-2022 | 530/RNP | 27/08/2021 | 26/09/2021 | SABIR ALI KHAN | 4.84 | 4.08 | 84.32 | 100
38 | PURULIA |  | Purulia Division | Retrofitting of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/07564 | Retrofitting | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (Santuri Water Supply Scheme, Block- Santuri ) to be Augmented / Retrofitting under Purulia Division P.H.E. Dte. | Assistant Engineer |  | ORD/000847/2022-2023 | 1750/PD | 22/11/2022 | 22/12/2022 | M/S. DESTINY CONSTRUCTION | 2.3 | 0 | 0 | 100
Total | [13 empty] | 169.03 | 13.84 | 8.19