## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURULIA |  | Purulia Division | Retrofitting of Sutabai Water Supply Scheme at Kashipur Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/07565 | Retrofitting | Functional Household Tap Connection (FHTC) including other allied works of Sutabai W/s Scheme at Kashipur Block within Raghunathpur Sub-Division under Purulia Division PHE Dte. (3331 Nos.) (Tender No. 35/SE/PMU of 2020-21) |  |  | VCH/000872/2020-2021 | BP-2021-22-39 | 19/07/2021 | 19/07/2021 | SANTANU BANERJEE | 66.81 | 0 | 0 | 0
2 | PURULIA |  | Purulia Division | Retrofitting of Sutabai Water Supply Scheme at Kashipur Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/07565 | Retrofitting | Functional Household Tap Connection (FHTC) including other allied works of Sutaboi Water Supply Scheme at Kashipur Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. (3331 Nos.) | Assistant Engineer | Junior Engineer | ORD/000332/2020-2021 | 242/PD | 10/02/2021 | 11/04/2021 | SANTANU BANERJEE | 154.04 | 87.21 | 56.62 | 0
Total | [13 empty] | 220.85 | 87.21 | 39.49