## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURULIA |  | Purulia Division | Retrofitting of Kalabani Water Supply Scheme at Hura Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/07566 | Retrofitting | Functional Household Tap Connection (FHTC) including other allied works of Kalaboni W/s Scheme at Hura Block. (Zone-I) (1591 Nos) (Tender No. 345/EE/PD of 2020-21) |  |  | VCH/000016/2021-2022 | BP-2021-22-40 | 19/07/2021 | 19/07/2021 | KOUSHIK CHATTERJEE | 4.69 | 0 | 0 | 0
2 | PURULIA |  | Purulia Division | Retrofitting of Kalabani Water Supply Scheme at Hura Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/07566 | Retrofitting | Changing of HDPE Pipe line due to damaged pipe near Rangadih Pry. School near Srishtidhar Mahato House & Kharpara main line to Ranjit Mahato house under kalaboni W/S Scheme (Zone-III) (Part- II) (Tender No. 386/20-21 of EE/PD) |  |  | VCH/000029/2021-2022 | BP-2021-22-45 | 19/07/2021 | 19/07/2021 | BASANTA KUMAR SINGHADEO | 4.04 | 0 | 0 | 0
3 | PURULIA |  | Purulia Division | Retrofitting of Kalabani Water Supply Scheme at Hura Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/07566 | Retrofitting | Functional Household Tap Connection (FHTC) including other allied works of Kalaboni Water Supply Scheme at Hura Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. at Zone -II (1182 Nos.) (Tender No.384/EE/PD of 2020-21) |  |  | VCH/000325/2021-2022 | BP-2021-22-102 | 13/09/2021 | 13/09/2021 | BASANTA KUMAR SINGHADEO | 34.04 | 0 | 0 | 0
4 | PURULIA |  | Purulia Division | Retrofitting of Kalabani Water Supply Scheme at Hura Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/07566 | Retrofitting | Changing of HDPE Pipe line due to damaged pipe near Rangadih Pry. School near Srishtidhar Mahato House & Kharpara main line to Ranjit Mahato house under kalaboni W/S Scheme (Zone-III) (Part- I) (Tender No. 387/20-21 of EE/PD) |  |  | VCH/000030/2021-2022 | BP-2021-22-46 | 19/07/2021 | 19/07/2021 | BASANTA KUMAR SINGHADEO | 4.32 | 0 | 0 | 0
5 | PURULIA |  | Purulia Division | Retrofitting of Kalabani Water Supply Scheme at Hura Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/07566 | Retrofitting | Functional Household Tap Connection (FHTC) including other allied works of Kalaboni W/S Scheme at Hura Block of Raghunathpur Sub- Division PHE Dte. at Zone- III (970 Nos.) (Tender No:- 336/EE/PD of 2020-21) |  |  | VCH/000214/2021-2022 | BP-2021-22-89 | 23/08/2021 | 23/08/2021 | PRIYATOSH MUKHERJEE | 27.81 | 0 | 0 | 0
6 | PURULIA |  | Purulia Division | Retrofitting of Kalabani Water Supply Scheme at Hura Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/07566 | Retrofitting | Functional Household Tap Connection (FHTC) including other allied works of Kalaboni W/S Scheme at Hura Block of Raghunathpur Sub- Division PHE Dte. at Zone- IV (1016 Nos.) (Tender No:- 313/EE/PD of 2020-21) |  |  | VCH/000217/2021-2022 | BP-2021-22-90 | 23/08/2021 | 23/08/2021 | RABIN CHANDRA CHAIL | 9.69 | 0 | 0 | 0
7 | PURULIA |  | Purulia Division | Retrofitting of Kalabani Water Supply Scheme at Hura Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/07566 | Retrofitting | Functional Household Tap Connection (FHTC) including other allied works of Kalaboni W/s Scheme at Hura Block of Raghunathpur Sub-Division under Purulia Division PHE Dte. at Zone-IV (1016 Nos.) (Tender No. 313/EE/PD of 2020-21) |  |  | VCH/000808/2020-2021 | 10/844326/1 | 12/04/2021 | 12/04/2021 | RABIN CHANDRA CHAIL | 7.95 | 0 | 0 | 0
8 | PURULIA |  | Purulia Division | Retrofitting of Kalabani Water Supply Scheme at Hura Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/07566 | Retrofitting | Temporary water supply arrangement through extension of Distribution Main by supplying & laying 63mm dia HDPE pipe line from Deshra More to Deshra Village (loop line) and to Bathandih Bero Bandh with allied works at Zone-III (Deshra OHR) under Kalabani W/s Scheme (Zone-III) of Raghunathpur Sub-Division PHE Dte. under Purulia Division PHE Dte. (Tender No. 388/EE/PD of 2020-21) |  |  | VCH/000382/2021-2022 | BP-2021-22-124 | 11/10/2021 | 11/10/2021 | BASANTA KUMAR SINGHADEO | 2.96 | 0 | 0 | 0
9 | PURULIA |  | Purulia Division | Retrofitting of Kalabani Water Supply Scheme at Hura Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/07566 | Retrofitting | Functional Household Tap Connection (FHTC) including other allied works of Kalabani Water Supply Scheme at Hura Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. (Zone- I) (120 Nos.) (Tender No.898/EE/PD of 2021-22) |  |  | VCH/000966/2021-2022 | BP-2021-22-268 | 28/02/2022 | 28/02/2022 | CHAIL CONSTRUCTION | 6.2 | 0 | 0 | 0
10 | PURULIA |  | Purulia Division | Retrofitting of Kalabani Water Supply Scheme at Hura Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/07566 | Retrofitting | Functional Household Tap Connection (FHTC) including other allied works of Kalaboni Water Supply Scheme at Hura Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. at Zone - I (1591 Nos.) (Tender No.345/EE/PD of 2020-21) |  |  | VCH/000868/2021-2022 | BP-2021-22-244 | 16/02/2022 | 16/02/2022 | KOUSHIK CHATTERJEE | 4.73 | 0 | 0 | 0
11 | PURULIA |  | Purulia Division | Retrofitting of Kalabani Water Supply Scheme at Hura Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/07566 | Retrofitting | Functional household Tap connection (FHTC) in connection with other allied works of Kalaboni W/S Scheme at Hura Block of Raghunathpur (Zone-II) (Tender No- 905/2021-22 of EE/PD) |  |  | VCH/001190/2021-2022 | BP-2021-22-318 | 22/03/2022 | 22/03/2022 | RAHIBUDDIN MONDAL | 12.46 | 0 | 0 | 0
12 | PURULIA |  | Purulia Division | Retrofitting of Kalabani Water Supply Scheme at Hura Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/07566 | Retrofitting | Additional work for FHTC including other allied works of Kalabani W/s Scheme. (Tender No.887/EE/PD of 2021-22) |  |  | VCH/001012/2021-2022 | BP-2021-22-257 | 25/02/2022 | 25/02/2022 | BASANTA KUMAR SINGHADEO | 7.91 | 0 | 0 | 0
13 | PURULIA |  | Purulia Division | Retrofitting of Kalabani Water Supply Scheme at Hura Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/07566 | Retrofitting | Additional work for Functional Household tap Connection (FHTC) including other allied works of kalaboni W/S Scheme at Hura block of Raghunathpur Sub- Division Zone-III (Tender No- 942/2021-22 of EE/PD) |  |  | VCH/001189/2021-2022 | BP-2021-22-316 | 22/03/2022 | 22/03/2022 | PRIYATOSH MUKHERJEE | 8.11 | 0 | 0 | 0
14 | PURULIA |  | Purulia Division | Retrofitting of Kalabani Water Supply Scheme at Hura Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/07566 | Retrofitting | Additional work for functional Household Tap Connection (FHTC) including other allied works of Kalabani Water Supply Scheme at Hura Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. (Zone-IV) (Tender No.856/EE/PD of 2021-22) |  |  | VCH/000808/2021-2022 | BP-2021-22-233 | 03/02/2022 | 03/02/2022 | RABIN CHANDRA CHAIL | 3.76 | 0 | 0 | 0
15 | PURULIA |  | Purulia Division | Retrofitting of Kalabani Water Supply Scheme at Hura Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/07566 | Retrofitting | Supplying, laying and aligning of HDPE pipe line and othar allied works at Kalabani Water Supply Scheme (Zone-II) of Raghunathpur Sub Division under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000636/2022-2023 | 1404/PD | 01/09/2022 | 16/10/2022 | NANIGOPAL DEY | 19.42 | 0 | 0 | 0
16 | PURULIA |  | Purulia Division | Retrofitting of Kalabani Water Supply Scheme at Hura Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/07566 | Retrofitting | Functional Household Tap Connection (FHTC) including other allied works of Kalaboni Water Supply Scheme at Hura Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. at Zone -IV(1016 Nos.) | Assistant Engineer | Junior Engineer | ORD/000285/2020-2021 | 164/PD | 01/02/2021 | 18/03/2021 | RABIN CHANDRA CHAIL | 45.51 | 22.73 | 49.95 | 0
17 | PURULIA |  | Purulia Division | Retrofitting of Kalabani Water Supply Scheme at Hura Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/07566 | Retrofitting | Functional Household Tap Connection (FHTC) including other allied works of Kalaboni Water Supply Scheme at Hura Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. at Zone -II (1182 Nos.) | Assistant Engineer | Junior Engineer | ORD/000282/2020-2021 | 162/PD | 01/02/2021 | 18/03/2021 | BASANTA KUMAR SINGHADEO | 52.62 | 19.16 | 36.41 | 0
18 | PURULIA |  | Purulia Division | Retrofitting of Kalabani Water Supply Scheme at Hura Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/07566 | Retrofitting | Bypass arrangement with allied works in between of over flow line to distribution main Kolaboni Zone-I OHR site under Kolaboni W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. |  | Junior Engineer-4 | ORD/000649/2024-2025 | 468/RNP | 26/09/2024 | 16/10/2024 | RABIN CHANDRA CHAIL | 0.95 | 0 | 0 | 100
Total | [13 empty] | 257.17 | 41.89 | 16.29