## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURULIA | Bagmundi | Purulia Division | Piped Water Supply Scheme from Marble Lake to adjoining areas. | SM/07764 | New | Sail investigation work for identification of sub sail profile for proposed intake WTP & OHR site Marbel Lake its adjoining mouzas area w/s scheme (Tender No. 359/PD of 2020-21) |  |  | VCH/000127/2021-2022 | 58/844322 | 08/06/2021 | 08/06/2021 | MOYTEC | 1.35 | 0 | 0 | 0
2 | PURULIA | Bagmundi | Purulia Division | Piped Water Supply Scheme from Marble Lake to adjoining areas. | SM/07764 | New | Construction of 30 Cu.m/hr capacity WTP , installation of MS structural intake jetty, supplying and laying 150 mm dia MS ERW raw water pipe line from source to WTP , construction of pump house , boundary wall, drain, inside WTP PCC road etc. for Marble Lake Water Supply Scheme. (Tender No-42/SE/PMU of 20-21) |  |  | VCH/000183/2022-2023 | BP-2022-23-62 | 24/05/2022 | 24/05/2022 | EFFLUENT & WATER TRETMENT ENGINEERS PVT LTD | 23.1 | 0 | 0 | 0
3 | PURULIA | Bagmundi | Purulia Division | Piped Water Supply Scheme from Marble Lake to adjoining areas. | SM/07764 | New | Laying in new alignment of different dia DI and HDPE pipe line for clear water rising main and distribution system & construction of RCC elevated reservoir capacity 100 cum (Torch type) staging height 20 metre at Bhuinghora mouza for marble Lake & adjoining area W/S Scheme of Purulia Sadar Sub- Division (Tender No- 10/2020-21 of SE/PMU/WBPWSP) |  |  | VCH/001191/2021-2022 | BP-2021-22-324 | 22/03/2022 | 22/03/2022 | ANUP KUMAR SAHA | 89.2 | 0 | 0 | 0
4 | PURULIA | Bagmundi | Purulia Division | Piped Water Supply Scheme from Marble Lake to adjoining areas. | SM/07764 | New | Construction of 30 Cu.m/hr capacity WTP , installation of MS structural intake jetty , supplying and laying 150 mm dia MS ERW raw water pipe line from source to WTP , construction of pump house , boundary wall, drain, inside WTP PCC road etc. for Marble Lake Water Supply Scheme. (Tender No.42/SE/PMU of 2020-21) |  |  | VCH/001017/2021-2022 | BP-2021-22-253 | 25/02/2022 | 25/02/2022 | EFFLUENT & WATER TRETMENT ENGINEERS PVT LTD | 58.72 | 0 | 0 | 0
5 | PURULIA | Bagmundi | Purulia Mechanical | Piped Water Supply Scheme from Marble Lake to adjoining areas. | SM/07764 | New | SUPPLY DELIVERY AND INSTALLATION OF ELECTRO MECHANICAL EQUIPMENTS SUBMERSIBLE PUMP MOTOR SETS FOR RAW WATER PUMP HOUSE , CENTRIFUGAL PUMP MOTOR SETS FOR CLEAR WATER PUMP HOUSE AT MARBLE LAKE PIPED WATER SUPPLY SCHEME (TR.NO 179 OF 21-22) |  |  | VCH/000562/2021-2022 | C022228319640 | 09/02/2022 | 09/02/2022 | COMBINE ENTERPRISE | 37.42 | 0 | 0 | 0
6 | PURULIA | Bagmundi | Purulia Division | Piped Water Supply Scheme from Marble Lake to adjoining areas. | SM/07764 | New | Supply delivery & installation of submersible pumping machinery for Marble lake W/S scheme of Baghmundi block (Tender No- 372/2021-22 of EE/PMD) |  |  | VCH/000153/2022-2023 | BP-2022-23-23 | 07/04/2022 | 07/04/2022 | COMBINE ENTERPRISES | 1.82 | 0 | 0 | 0
7 | PURULIA | Bagmundi | Purulia Division | Piped Water Supply Scheme from Marble Lake to adjoining areas. | SM/07764 | New | Laying in new alignment of different dia DI and HDPE pipe line for clear water rising main and distribution system and Construction of R.C.C. Elevated Reservoir, Capcaity 100 cum (Torch Type), Staging height 20 metre at Bhuinghora mouza for Marble Lake & its adjoing area W/S Scheme of Purulia Sadar Sub-Division, under Purulia Division,P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000160/2020-2021 | 1416/PD | 29/12/2020 | 10/01/2021 | ANUP KUMAR SAHA | 178.29 | 145.63 | 81.68 | 0
8 | PURULIA | Bagmundi | Purulia Division | Piped Water Supply Scheme from Marble Lake to adjoining areas. | SM/07764 | New | Construction of 30 Cu.m/hr capacity WTP , installation of MS structural intake jetty , supplying and laying 150 mm dia MS ERW raw water pipe line from source to WTP , construction of pump house , boundary wall, drain, inside WTP PCC road etc. for Marble Lake Water Supply Scheme | Assistant Engineer |  | ORD/000363/2020-2021 | 353/PD | 25/02/2021 | 22/11/2021 | EFFLUENT & WATER TRETMENT ENGINEERS PVT LTD | 205.74 | 170.59 | 82.91 | 100
9 | PURULIA | Bagmundi | Purulia Division | Piped Water Supply Scheme from Marble Lake to adjoining areas. | SM/07764 | New | Construction of RCC Back Wash Reservoir of capacity 57.00 Cum at AT WTP Campus site of Marbel Lake W/S Scheme at Ajodhya Hill W/S Scheme of Purulia Sadar Sub-Division, Under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000199/2021-2022 | 640/PSD | 21/09/2021 | 05/11/2021 | EFFLUENT & WATER TRETMENT ENGINEERS PVT LTD | 4.82 | 4.48 | 92.85 | 85
10 | PURULIA | Bagmundi | Purulia Division | Piped Water Supply Scheme from Marble Lake to adjoining areas. | SM/07764 | New | Construction of Fencing on The Entry of Marble Lake under Marble Lake W/S Scheme Under Purulia Sadar Sub-Division, Purulia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000610/2022-2023 | 507/PSD | 12/08/2022 | 06/09/2022 | ANUP KUMAR SAHA | 1 | 0.94 | 94.13 | 100
11 | PURULIA | Bagmundi | Purulia Division | Piped Water Supply Scheme from Marble Lake to adjoining areas. | SM/07764 | New | Laying Remaining Portion of distribution pipe Line due to shifting of OHR Location Of Marble lake & Its Adjoing area W/S Scheme At Ajodhya Hill Baghmundi Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte | Assistant Engineer |  | ORD/000617/2022-2023 | 514/PSD | 12/08/2022 | 26/09/2022 | ANUP KUMAR SAHA | 4.62 | 4.4 | 95.16 | 100
12 | PURULIA | Bagmundi | Purulia Division | Piped Water Supply Scheme from Marble Lake to adjoining areas. | SM/07764 | New | Extension Of Distribution Line Near marble Lake road to Dulgubera and Laying of GI Pipe over Hatinada Khal Of Marble lake & Its Adjoing area W/S Scheme At Ajodhya Hill Baghmundi Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte | Assistant Engineer |  | ORD/000612/2022-2023 | 509/PSD | 12/08/2022 | 26/09/2022 | ANUP KUMAR SAHA | 4.75 | 4.26 | 89.72 | 100
13 | PURULIA | Bagmundi | Purulia Division | Piped Water Supply Scheme from Marble Lake to adjoining areas. | SM/07764 | New | Sinking of 200 mm dia average 180 mtr deep Reverse Rotary/DTH Rigbored tubewell and necessary VES test at Bhuinghora OHR campurs as Additional Source of water for Marble Lake W/S Scheme to mitigate water crisis in draught like situation under Purulia Sadar Sub-Division, PHE Dte.(TubeWell No-1) | Assistant Engineer |  | ORD/000786/2022-2023 | 1633/PD | 28/10/2022 | 27/11/2022 | ANUP KUMAR SAHA | 4.25 | 2.59 | 60.79 | 75
14 | PURULIA | Bagmundi | Purulia Division | Piped Water Supply Scheme from Marble Lake to adjoining areas. | SM/07764 | New | Sinking of 200 mm dia average 180 mtr deep Reverse Rotary/DTH Rigbored tubewell and necessary VES test at Bhuinghora OHR campurs as Additional Source of water for Marble Lake W/S Scheme to mitigate water crisis in draught like situation under Purulia Sadar Sub-Division, PHE Dte.(TubeWell No-2) | Assistant Engineer |  | ORD/000787/2022-2023 | 1634/PD | 28/10/2022 | 27/11/2022 | ANUP KUMAR SAHA | 4.25 | 4.05 | 95.23 | 100
15 | PURULIA | Bagmundi | Purulia Mechanical | Piped Water Supply Scheme from Marble Lake to adjoining areas. | SM/07764 | New | Supply delivery and installation of electro mechanical equipments submersible pump motor sets of Raw water pump house , centrifugal pump motor sets for Clear water pump house at Marble Lake piped water supply scheme , Block : Baghmundi under Purulia Mechanical Division PHE Dte. Dist : Purulia | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000173/2021-2022 | 471/PMD | 28/07/2021 | 25/12/2021 | COMBINE ENTERPRISES | 43.7 | 5.84 | 13.37 | 100
16 | PURULIA | Bagmundi | Purulia Mechanical | Piped Water Supply Scheme from Marble Lake to adjoining areas. | SM/07764 | New | Supply delivery and installation of Voltage stabilizer ,valves, external illumination arrangement with allied works at Marble lake PWSS Under Purulia Mechanical Division PHE Dte Dist-Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000467/2022-2023 | 307/PMD | 16/03/2023 | 15/04/2023 | COMBINE ENTERPRISES | 13.17 | 12.71 | 96.54 | 60
17 | PURULIA | Bagmundi | Purulia Division | Piped Water Supply Scheme from Marble Lake to adjoining areas. | SM/07764 | New | Allied Work of Construction of roof, slab, plaster etc. of New Constructed Ajodhya Camp Office under Marble Lake & Its Adjoing Area W/S Scheme of Purulia Sadar Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000185/2023-2024 | 4675/PSD | 27/07/2023 | 11/08/2023 | BOSE CONSTRUCTION | 0.88 | 0.83 | 94.33 | 100
18 | PURULIA | Bagmundi | Purulia Division | Piped Water Supply Scheme from Marble Lake to adjoining areas. | SM/07764 | New | Construction of Parapet Wall of New Constructed Ajodhya Camp Office under Marble Lake & Its Adjoing Area W/S Scheme of Purulia Sadar Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000186/2023-2024 | 4676/PSD | 27/07/2023 | 11/08/2023 | BOSE CONSTRUCTION | 0.95 | 0.95 | 100 | 100
19 | PURULIA | Bagmundi | Purulia Division | Piped Water Supply Scheme from Marble Lake to adjoining areas. | SM/07764 | New | Material Requisition To Resource Division |  |  | RTOR000006/2020-2021 | 47/PD | 15/01/2021 | 15/01/2021 | Resource Division | 51.57 | 0 | 0 | 0
20 | PURULIA | Bagmundi | Purulia Division | Piped Water Supply Scheme from Marble Lake to adjoining areas. | SM/07764 | New | Laying of Loop Line for the distribution System at different command area of Patuara, Ramjibanpur, Bhomorbera,Lawadih etc of Satra under Marble Lake W/S Scheme Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-4 | ORD/000479/2024-2025 | 1500/PD | 27/08/2024 | 01/09/2025 | SUBODH PRAMANIK | 27.42 | 20.75 | 75.68 | 80
21 | PURULIA | Bagmundi | Purulia Mechanical | Piped Water Supply Scheme from Marble Lake to adjoining areas. | SM/07764 | New | Supply and installation of PLC panel, Level transmitter with other allied work at Marble Lake water supply scheme under Purulia Mechanical Division PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000645/2024-2025 | 1577/PMD | 14/11/2024 | 12/02/2025 | SUBRATA DUTTA | 14.57 | 0 | 0 | 0
22 | PURULIA | Bagmundi | Purulia Division | Piped Water Supply Scheme from Marble Lake to adjoining areas. | SM/07764 | New | Construction of boundary wall for OHR campus at Bhuinghora mouza of Marbel Lake W/S Scheme at Ajodhya Hill under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000121/2020-2021 | 1280/PD | 07/12/2020 | 06/01/2021 | SHAYED NADEEM AHAMAD | 9.05 | 16.64 | 183.88 | 0
23 | PURULIA | Bagmundi | Purulia Division | Piped Water Supply Scheme from Marble Lake to adjoining areas. | SM/07764 | New | Construction of Office Cum Godown at Ist Floor of Ajodhya Camp Office under Marble Lake & Its Adjoing Area W/S Scheme of Purulia Sadar Sub-Division, PHE Dte. | Assistant Engineer(HQ) | Junior Engineer | ORD/000002/2022-2023 | 538/PD | 01/04/2022 | 10/07/2022 | BOSE CONSTRUCTION | 20.61 | 20.35 | 98.75 | 98
24 | PURULIA | Bagmundi | Purulia Division | Piped Water Supply Scheme from Marble Lake to adjoining areas. | SM/07764 | New | Continuation work order for O & M of Marble Lake and Its Adjoining Area W/S Scheme (Except Electro Mechanical component) Of rising main & all distribution system, sluice valve, street stand post etc. under Purulia Division, P.H.E. Dte. [w.e.f 21.02.23 to 20.05.23] | Assistant Engineer | Junior Engineer | ORD/001293/2022-2023 | 245/PD | 20/02/2023 | 21/05/2023 | ANUP KUMAR SAHA | 1.68 | 1.56 | 92.85 | 100
25 | PURULIA | Bagmundi | Purulia Division | Piped Water Supply Scheme from Marble Lake to adjoining areas. | SM/07764 | New | Continuation work order for O & M of Marble Lake and Its Adjoining Area W/S Scheme (Except Electro Mechanical component) Of rising main & all distribution system, sluice valve, street stand post etc. under Purulia Division, P.H.E. Dte. [w.e.f 29.08.23 to 26.11.23] | Assistant Engineer | Junior Engineer | ORD/000808/2023-2024 | 1169/PD | 28/08/2023 | 26/11/2023 | ANUP KUMAR SAHA | 1.68 | 1.59 | 94.92 | 100
26 | PURULIA | Bagmundi | Purulia Division | Piped Water Supply Scheme from Marble Lake to adjoining areas. | SM/07764 | New | Continuation work order for O & M of Marble Lake and Its Adjoining Area W/S Scheme (Except Electro Mechanical component) Of rising main & all distribution system, sluice valve, street stand post etc. under Purulia Division, P.H.E. Dte. [w.e.f 21.05.23 to 28.08.23] | Assistant Engineer | Junior Engineer | ORD/000807/2023-2024 | 678/PD | 17/05/2023 | 15/08/2023 | ANUP KUMAR SAHA | 1.68 | 1.63 | 96.72 | 100
27 | PURULIA | Bagmundi | Purulia Mechanical | Piped Water Supply Scheme from Marble Lake to adjoining areas. | SM/07764 | New | Arrangement of Pandel & other Miscellaneous works for infield training at Pump operator & valve operator of different water supply scheme under Purulia Mechanical Division, PHE Dte. | DRILLER-IN-CHARGE IN THE RANK OF ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000567/2023-2024 | 23/PMSD(Drilling) | 16/02/2024 | 02/03/2024 | AMIT PATHAK | 0.54 | 0.54 | 100 | 100
28 | PURULIA | Bagmundi | Purulia Division | Piped Water Supply Scheme from Marble Lake to adjoining areas. | SM/07764 | New | Allied works for construction of office cum Godown at Ajodhya under Marble Lake W/S Scheme Purulia Division, PHE Dte. (JJM) | Assistant Engineer(HQ) | Junior Engineer-1 | ORD/000480/2024-2025 | 1516/PD | 27/08/2024 | 11/10/2024 | BOSE CONSTRUCTION | 11.59 | 0 | 0 | 100
29 | PURULIA | Bagmundi | Purulia Division | Piped Water Supply Scheme from Marble Lake to adjoining areas. | SM/07764 | New | Laying HDPE distribution pipeline to cover the left out habitation of Ajodhya, Bagandih & Chatni mouza at Ajodhya Under Marble Lake W/S Scheme under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer-2 | ORD/000448/2024-2025 | 1510/PD | 27/08/2024 | 11/10/2024 | TUMPA GORAIN | 23.18 | 22.42 | 96.72 | 100
30 | PURULIA | Bagmundi | Purulia Mechanical | Piped Water Supply Scheme from Marble Lake to adjoining areas. | SM/07764 | New | Arrangement of refreshment for infield training of pump operator & valve operator of different water supply scheme under Purulia Mechanical Division, PHE Dte. | DRILLER-IN-CHARGE IN THE RANK OF ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000568/2023-2024 | 24/PMSD(Drilling) | 16/02/2024 | 02/03/2024 | AMIT PATHAK | 0.43 | 0.43 | 100 | 100
31 | PURULIA | Bagmundi | Purulia Division | Piped Water Supply Scheme from Marble Lake to adjoining areas. | SM/07764 | New | Construction of shed and other works at Manbhum Paridarshan Abas Campus under Marble Lake W/S Scheme Purulia Division, PHE Dte. | Assistant Engineer(HQ) | Junior Engineer-1 | ORD/000478/2024-2025 | 1499/PD | 27/08/2024 | 11/10/2024 | MAHARSHI BANERJEE | 5.61 | 5.41 | 96.58 | 100
32 | PURULIA | Bagmundi | Purulia Division | Piped Water Supply Scheme from Marble Lake to adjoining areas. | SM/07764 | New | Construction of main drain at Baghmundi WTP Site under Piped Water Supply Scheme from Marble Lake under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000124/2024-2025 | 892/PD | 07/05/2024 | 21/06/2024 | ROY CONSTRUCTION | 2.32 | 2.03 | 87.76 | 100
33 | PURULIA | Bagmundi | Purulia Division | Piped Water Supply Scheme from Marble Lake to adjoining areas. | SM/07764 | New | Continuation order for the work of O & M of Marble Lake and Its Adjoining Area W/S Scheme (Except Electro Mechanical component) Of rising main & all distribution system, sluice valve, street stand post etc. under Purulia Division, P.H.E. Dte [For the period of 90 days] (w.e.f 20/05/2025-17/08/2025) | Assistant Engineer | Junior Engineer-2 | ORD/000543/2025-2026 | 894/PD | 19/05/2025 | 17/08/2025 | ANUP KUMAR SAHA | 1.68 | 0 | 0 | 100
Total | [13 empty] | 851.65 | 450.63 | 52.91