## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURULIA |  | Purulia Division | Retrofitting of Bathanbari Water Supply Scheme at Neturia Block of Raghunathpur Sub Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/07836 | Retrofitting | Functional Household Tap Connection (FHTC) including other allied works of Bathanbari Water Supply Scheme at Neturia Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. Part-B (Mouza- Ghatkul, Gobindapur Alis , Amaidi, Hariraidi ALIS, Birbaldi, Kalipathar, Kharbana, Kulbana, Malancha, Shalchura, Taltly under Gunyarae G.P). (590 Nos.) | Assistant Engineer |  | ORD/000242/2020-2021 | 63/PD | 15/01/2021 | 01/03/2021 | KHITISH CHANDRA PATHAK | 29.98 | 67.12 | 223.84 | 100
2 | PURULIA |  | Purulia Division | Retrofitting of Bathanbari Water Supply Scheme at Neturia Block of Raghunathpur Sub Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/07836 | Retrofitting | Prviding Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL Sapna) at Satra village of Hensla G.P under command area of Satra W/s Scheme at Arsha Block. (Part-D) (Tender No. 264/EE/PD of 2020-21) |  |  | VCH/000015/2021-2022 | BP-2021-22-43 | 19/07/2021 | 19/07/2021 | DEBAKI RANJAN SARKAR | 27.12 | 0 | 0 | 0
3 | PURULIA |  | Purulia Division | Retrofitting of Bathanbari Water Supply Scheme at Neturia Block of Raghunathpur Sub Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/07836 | Retrofitting | Construction of Boundary wall, RCC Pillar gate, Barbed wire, and other allied work at Bathanbari Head Work Site under Bathanbari W/s Schemeunder Raghunathpur Sub-Division PHE Dte. (Total length of Boundary Wall 42.00 mtr.) (Tender No.235/EE/PD of 2020-21) |  |  | VCH/000174/2021-2022 | BP-2021-22-65 | 12/08/2021 | 12/08/2021 | KHITISH CHANDRA PATHAK | 2.76 | 0 | 0 | 0
4 | PURULIA |  | Purulia Division | Retrofitting of Bathanbari Water Supply Scheme at Neturia Block of Raghunathpur Sub Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/07836 | Retrofitting | Repairing of Pressure filtre,Plumbing work of toilet,Clearing of OHR Campus and other allied works under Bathanbari W/S Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000317/2020-2021 | 113/RNP | 08/02/2021 | 23/02/2021 | KHITISH CHANDRA PATHAK | 1.47 | 1.29 | 87.49 | 90
5 | PURULIA |  | Purulia Division | Retrofitting of Bathanbari Water Supply Scheme at Neturia Block of Raghunathpur Sub Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/07836 | Retrofitting | Additional work for FHTC Bathanbari Water supply Scheme [Ad- Interim payment] [Tender No- 935/2021-22 of EE/PD) |  |  | VCH/001149/2021-2022 | BP-2021-22-298 | 09/03/2022 | 09/03/2022 | KHITISH CHANDRA PATHAK | 5 | 0 | 0 | 0
6 | PURULIA |  | Purulia Division | Retrofitting of Bathanbari Water Supply Scheme at Neturia Block of Raghunathpur Sub Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/07836 | Retrofitting | Additional work for functional Household Tap Connection (FHTC) including other allied works of Bathanbari Water Supply Scheme at Neturia Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. (Tender No.935/EE/PD of 2021-22) |  |  | VCH/001144/2021-2022 | BP-2021-22-300 | 09/03/2022 | 09/03/2022 | KHITISH CHANDRA PATHAK | 33.31 | 0 | 0 | 0
Total | [13 empty] | 99.64 | 68.4 | 68.65