## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURULIA |  | Purulia Division | Retrofitting of Bhamuria Water Supply Scheme at Neturia Block of Raghunathpur Sub Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/07837 | Retrofitting | Functional Household Tap Connection (FHTC) including other allied works of Bhamuria Water Supply Scheme at Neturia Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. Part-C (Mouza- Bhamuria, Habitation-Sarkardih Tola under Bhamuria G.P). (655 Nos.) | Assistant Engineer |  | ORD/000240/2020-2021 | 61/PD | 15/01/2021 | 01/03/2021 | LEO CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 32.49 | 0 | 0 | 100
2 | PURULIA |  | Purulia Division | Retrofitting of Bhamuria Water Supply Scheme at Neturia Block of Raghunathpur Sub Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/07837 | Retrofitting | Functional Household Tap Connection (FHTC) including other allied works of Bhamuria Water Supply Scheme at Neturia Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. Part-A (Mouza-Alkusha, Asanbani, Baruipara under Bhamuria G.P). (586 Nos.) | Assistant Engineer |  | ORD/000236/2020-2021 | 57/PD | 15/01/2021 | 01/03/2021 | ANUP KUMAR SAHA | 29.11 | 0 | 0 | 100
3 | PURULIA |  | Purulia Division | Retrofitting of Bhamuria Water Supply Scheme at Neturia Block of Raghunathpur Sub Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/07837 | Retrofitting | Functional Household Tap Connection (FHTC) including other allied works of Bhamuria Water Supply Scheme at Neturia Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. Part-D (Mouza-Bonra under Bhamuria GP ).( 889 Nos.) (Tender No.333/EE/PD of 2020-21) |  |  | VCH/001171/2021-2022 | BP-2021-22-365 | 28/03/2022 | 28/03/2022 | BABA LOKENATH LABOUR CONSTRUCTION CO-OP SOCIETY LTD. | 40.33 | 0 | 0 | 0
4 | PURULIA |  | Purulia Division | Retrofitting of Bhamuria Water Supply Scheme at Neturia Block of Raghunathpur Sub Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/07837 | Retrofitting | Rejuvenation work for supplying & laying of HDPE piped distribution main with all allied works from old OHR site at Bhamuria & adjacent habitation under Bhamuria W/S Scheme (Tender No- 547/2021-22 of EE/PD) |  |  | VCH/001136/2021-2022 | BP-2021-22-334 | 23/03/2022 | 23/03/2022 | ANUP KUMAR SAHA | 10.5 | 0 | 0 | 0
5 | PURULIA |  | Purulia Division | Retrofitting of Bhamuria Water Supply Scheme at Neturia Block of Raghunathpur Sub Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/07837 | Retrofitting | New Sinking of 1(one) No 200 mm dia river bed vertical tube well (T/W No. 2) along with necessary 100 mm dia GI collecting line from riverbed tube well to manifold chamber at river bank (Damodar River) at Manikeswar ghat at Hirakund under Bhamuria Improvement W/S Scheme under Raghunathpur Sub-Division, PHE Dte. (Tube well No - 2) | Assistant Engineer | Junior Engineer | ORD/000477/2020-2021 | 404/PD | 15/01/2021 | 14/02/2021 | ANUP KUMAR SAHA | 7.38 | 0 | 0 | 0
6 | PURULIA |  | Purulia Division | Retrofitting of Bhamuria Water Supply Scheme at Neturia Block of Raghunathpur Sub Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/07837 | Retrofitting | Additional work by providing Functional Household Tap Connection (FHTC) and other allied works of Bhamuria Water Supply Scheme at Neturia Block of Raghunathpur Sub Division under Purulia Division, PHE Dte.(Part -A) | Assistant Engineer |  | ORD/000543/2022-2023 | 459/RNP | 12/07/2022 | 01/08/2022 | ANUP KUMAR SAHA | 4.79 | 0 | 0 | 100
7 | PURULIA |  | Purulia Division | Retrofitting of Bhamuria Water Supply Scheme at Neturia Block of Raghunathpur Sub Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/07837 | Retrofitting | Additional work by providing Functional Household Tap Connection (FHTC) and other allied works of Bhamuria Water Supply Scheme at Neturia Block of Raghunathpur Sub Division under Purulia Division, PHE Dte.(Part -B) | Assistant Engineer |  | ORD/000544/2022-2023 | 460/RNP | 12/07/2022 | 01/08/2022 | ANUP KUMAR SAHA | 4.85 | 0 | 0 | 100
8 | PURULIA |  | Purulia Division | Retrofitting of Bhamuria Water Supply Scheme at Neturia Block of Raghunathpur Sub Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/07837 | Retrofitting | Additional work by providing Functional Household Tap Connection (FHTC) including Interconnection between Over flow and Distribution Main and other allied works of Bhamuria Water Supply Scheme at Neturia Block of Raghunathpur Sub Division under Purulia Division, PHE Dte.(Part -C) | Assistant Engineer |  | ORD/000545/2022-2023 | 461/RNP | 12/07/2022 | 01/08/2022 | ANUP KUMAR SAHA | 4.21 | 0 | 0 | 100
9 | PURULIA |  | Purulia Division | Retrofitting of Bhamuria Water Supply Scheme at Neturia Block of Raghunathpur Sub Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/07837 | Retrofitting | Sinking of 2 (Two) No 200 mm dia river bed vertical tubewell (T/W No.3 & 4) alongwith necessary 100 mm dia GI collecting line to common manifold chamber Cleaning of chowkage of distribution line and other allied work under Bhamuria W/S Scheme under Raghunathpur Sub Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000050/2023-2024 | 674/PD | 17/05/2023 | 01/07/2023 | ANUP KUMAR SAHA | 11.84 | 0 | 0 | 100
10 | PURULIA |  | Purulia Division | Retrofitting of Bhamuria Water Supply Scheme at Neturia Block of Raghunathpur Sub Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/07837 | Retrofitting | Re-sinking of 01 (One) No. 200 mm dia river bed vertical tube well T/W no- 4 along with necessary 100 mm dia GI collecting under Bhamuria W/S Scheme (Tender No- 110/2022-23 of EE/PD) |  |  | VCH/000906/2022-2023 | BP-2022-23-95 | 07/07/2022 | 07/07/2022 | ANUP KUMAR SAHA | 4.38 | 0 | 0 | 0
11 | PURULIA |  | Purulia Division | Retrofitting of Bhamuria Water Supply Scheme at Neturia Block of Raghunathpur Sub Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/07837 | Retrofitting | New sinking of 02 (Two) No. 200 mm dia river bed vertical tube well T/W no- 3&4 along with necessary 100 mm dia GI collecting line 250 mm dia clear water rising main in connection with FHTC from river bed tube well to common manifold chamber at river bank (Damodar river) of Manikeswar Ghat at Hirakund under Bhamuria Water Supply Scheme under Raghunathpur Sub- Division, PHE dte.(Tender No- 24/2020-21 of EE/PD) |  |  | VCH/000907/2022-2023 | BP-2022-23-94 | 07/07/2022 | 07/07/2022 | ANUP KUMAR SAHA | 16.61 | 0 | 0 | 0
12 | PURULIA |  | Purulia Division | Retrofitting of Bhamuria Water Supply Scheme at Neturia Block of Raghunathpur Sub Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/07837 | Retrofitting | New sinking of 01 (One) No. 200 mm dia river bed vertical tube well T/W no- 2 along with necessary 100 mm dia GI collecting line from river bed tube well to manifold chamber at river bank (Damodar river) of Manikeswar Ghat under Bhamuria Water Supply Scheme (Tender No- 14/2020-21 of EE/PD) |  |  | VCH/000883/2022-2023 | BP-2022-23-68 | 01/07/2022 | 01/07/2022 | ANUP KUMAR SAHA | 7.14 | 0 | 0 | 0
Total | [13 empty] | 173.6 | 0 | 0