## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURULIA |  | Purulia Division | Retrofitting of Sonathali Water Supply Scheme at Kashipur Block of Raghunathpur Sub Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/07838 | Retrofitting | Functional Household Tap Connection (FHTC) including other allied works of Sonathali Water Supply Scheme at Kashipur Block of Raghunathpur Sub Division under Purulia Division, PHE Dte at (Mouza:-Kalapathar, ,Kendtanr, Kultore , Kumardih, ushjuri Sonathol). (1309 Nos.) (Tender No. 373/EE/PD of 2020-21) (Ad-interim) |  |  | VCH/000224/2021-2022 | 89/8443101 | 15/07/2021 | 15/07/2021 | KHAN ENTERPRISE | 7.11 | 0 | 0 | 0
2 | PURULIA |  | Purulia Division | Retrofitting of Sonathali Water Supply Scheme at Kashipur Block of Raghunathpur Sub Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/07838 | Retrofitting | Functional Household Tap Connection (FHTC) including other allied works of Sonathali W/S Scheme at Kashipur Block of Raghunathpur Sub- Division PHE Dte. at Mouza- Kalapathar, Kendtanr, kultore, kumardih, Ushjuri Sonathol (1309) Nos. (Tender No:- 373/EE/PD of 2020-21) |  |  | VCH/000220/2021-2022 |  | 09/08/2021 | 09/08/2021 | KHAN ENTERPRISE | 14.38 | 0 | 0 | 0
3 | PURULIA |  | Purulia Division | Retrofitting of Sonathali Water Supply Scheme at Kashipur Block of Raghunathpur Sub Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/07838 | Retrofitting | Functional House Hold Connection (FHTC) including other allied works of Sonatholi Water Supply Scheme at Kashipur Block of Raghunathpur Sub-Division PHE Dte. (Mouza- Kashipur, Kendtanr, Kultore, Kumardih, Ushjuri Sonatholi) (1309 nos.) (Tender No. 373/EE/PD of 2020-21) |  |  | VCH/000870/2020-2021 |  | 22/03/2021 | 22/03/2021 | KHAN ENTERPRISE | 28.02 | 0 | 0 | 0
4 | PURULIA |  | Purulia Division | Retrofitting of Sonathali Water Supply Scheme at Kashipur Block of Raghunathpur Sub Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/07838 | Retrofitting | Additional work for functional Household Tap Connection (FHTC) including other allied works of augmentation of Sonathali Water Supply Scheme at Kashipur Block. (Tender No.17/SE/PMU of 2021-22) |  |  | VCH/000179/2022-2023 | BP-2022-23-46 | 02/05/2022 | 02/05/2022 | S AND P CONSTRUCTION | 16.37 | 0 | 0 | 0
5 | PURULIA |  | Purulia Division | Retrofitting of Sonathali Water Supply Scheme at Kashipur Block of Raghunathpur Sub Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/07838 | Retrofitting | Construction of Boundary wall, RCC pillar, barbed wire & other allied works under Sonathali W/S Scheme (Tender No-930/2021-22 of EE/PD) |  |  | VCH/000190/2022-2023 | BP-2022-23-57 | 20/05/2022 | 20/05/2022 | TOTAL INFRA | 3.35 | 0 | 0 | 0
6 | PURULIA |  | Purulia Division | Retrofitting of Sonathali Water Supply Scheme at Kashipur Block of Raghunathpur Sub Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/07838 | Retrofitting | Construction of G.I. Shed at 1st Floor of Raghunathpur Sub-Divisional office buiding under Aug. of Sonathol W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | Assistant Engineer |  | ORD/000844/2022-2023 | 1747/PD | 22/11/2022 | 06/01/2023 | MANATOSH SINGH | 4.3 | 0 | 0 | 0
7 | PURULIA |  | Purulia Division | Retrofitting of Sonathali Water Supply Scheme at Kashipur Block of Raghunathpur Sub Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/07838 | Retrofitting | Functional Household Tap Connection (FHTC) including other allied works of Sonathali Water Supply Scheme at Kashipur Block of Raghunathpur Sub Division under Purulia Division, PHE Dte at (Muza:-Kalapathar, ,Kendtanr, Kultore , Kumardih, ushjuri Sonathol). (1309 Nos.) | Assistant Engineer | Junior Engineer | ORD/000288/2020-2021 | 213/PD | 08/02/2021 | 25/03/2021 | KHAN ENTERPRISE | 70.34 | 60.28 | 85.69 | 0
Total | [13 empty] | 143.87 | 60.28 | 41.9