## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURULIA |  | Purulia Division | Retrofitting of Manguria-Lalpur Water Supply Scheme at Hura Block of Raghunathpur Sub Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/07839 | Retrofitting | Functional Household Tap Connection (FHTC) including other allied works of Maguria-Lalpur Water Supply Scheme at Hura Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. Part-B Mouza-Daldali, Bhagabandh under Daldali G.P.(1139 Nos.) | Assistant Engineer |  | ORD/000272/2020-2021 | 157/PD | 01/02/2021 | 18/03/2021 | GOUTAM CHAKRABORTY | 56.95 | 34.58 | 60.72 | 85
2 | PURULIA |  | Purulia Division | Retrofitting of Manguria-Lalpur Water Supply Scheme at Hura Block of Raghunathpur Sub Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/07839 | Retrofitting | Functional Household Tap Connection (FHTC) including other allied works of Maguria-Lalpur Water Supply Scheme at Hura Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. Part-C (Mouza-Maguria-Lalpur under Maguria-Lalpurr G.P). 1218 Nos.) (Tender No.307/EE/PD OF 2020-21) |  |  | VCH/000444/2021-2022 | BP-2021-22-106 | 14/09/2021 | 14/09/2021 | SWAPAN MANDAL | 46.14 | 0 | 0 | 0
3 | PURULIA |  | Purulia Division | Retrofitting of Manguria-Lalpur Water Supply Scheme at Hura Block of Raghunathpur Sub Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/07839 | Retrofitting | Functional Household Tap Connection (FHTC) including other allied works of Manguria-Lalpur W/s Scheme at Hura Block of Raghunathpur Sub-DivisionPHE Dte. (Tender No. 409/EE/PD of 2020-21) |  |  | VCH/000249/2021-2022 | BP-2021-22-98 | 23/08/2021 | 23/08/2021 | ALOK KUMAR CHAKRABORTY | 28.51 | 0 | 0 | 0
4 | PURULIA |  | Purulia Division | Retrofitting of Manguria-Lalpur Water Supply Scheme at Hura Block of Raghunathpur Sub Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/07839 | Retrofitting | Artificial recharging of existing river bed tubewells along with all others related items of works to combat extreme drought like situation under Manguria-Lalpur W/s Scheme of Raghunathpur Sub-Division PHE Dte. under Purulia Division PHE Dte. (Tender No. 376/EE/PD of 2021-22) |  |  | VCH/000383/2021-2022 | BP-2021-22-125 | 11/10/2021 | 11/10/2021 | ALOK KUMAR CHAKRABORTY | 4.78 | 0 | 0 | 0
5 | PURULIA |  | Purulia Division | Retrofitting of Manguria-Lalpur Water Supply Scheme at Hura Block of Raghunathpur Sub Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/07839 | Retrofitting | Functional Household Tap Connection (FHTC) including other allied works of Manguria-Lalpur W/s Scheme at Hura Block of Raghunathpur Sub-Division under Purulia Division PHE Dte. at Part-B Mouza- Daldali, Bhagabandh under Daldali G.P (1139 Nos.) (Tender No. 309/EE/PD of 2020-21) |  |  | VCH/000871/2020-2021 | 9/844324/2 | 12/04/2021 | 12/04/2021 | GOUTAM CHAKRABORTY | 13.28 | 0 | 0 | 0
6 | PURULIA |  | Purulia Division | Retrofitting of Manguria-Lalpur Water Supply Scheme at Hura Block of Raghunathpur Sub Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/07839 | Retrofitting | Additional work for functional Household Tap Connection (FHTC) including other allied works of Manguria-Lalpur Water Supply Scheme at Hura Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. (Part-B) Mouza-Daldali, Bhagabandh under Daldali (1139 Nos.) Part-II. (Tender No.826/EE/PD of 2021-22) |  |  | VCH/000815/2021-2022 | BP-2021-22-231 | 03/02/2022 | 03/02/2022 | GOUTAM CHAKRABORTY | 4.8 | 0 | 0 | 0
7 | PURULIA |  | Purulia Division | Retrofitting of Manguria-Lalpur Water Supply Scheme at Hura Block of Raghunathpur Sub Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/07839 | Retrofitting | Additional work for functional Household Tap Connection (FHTC) including other allied works of Manguria-Lalpur Water Supply Scheme at Hura Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. (Part-B) Mouza-Daldali, Bhagabandh under Daldali G.P Part-III. (Tender No.827/EE/PD of 2021-22) |  |  | VCH/000812/2021-2022 | BP-2021-22-228 | 03/02/2022 | 03/02/2022 | GOUTAM CHAKRABORTY | 4.82 | 0 | 0 | 0
8 | PURULIA |  | Purulia Division | Retrofitting of Manguria-Lalpur Water Supply Scheme at Hura Block of Raghunathpur Sub Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/07839 | Retrofitting | Distribution Main by supplying & laying of different dia HDPE pipe line and Functional Household Tap Connection (FHTC) including other allied works of Manguria-Lalpur Water Supply Scheme at Hura Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. (Tender No.959/EE/PD of 2021-22) |  |  | VCH/001137/2021-2022 | BP-2021-22-292 | 09/03/2022 | 09/03/2022 | PREMNATH MITRA | 53.06 | 0 | 0 | 0
9 | PURULIA |  | Purulia Division | Retrofitting of Manguria-Lalpur Water Supply Scheme at Hura Block of Raghunathpur Sub Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/07839 | Retrofitting | Additional work for functional Household Tap Connection (FHTC) including other allied works of Manguria-Lalpur Water Supply Scheme at Hura Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. (Part-B) Mouza-Daldali, Bhagabandh under Daldali G.P Part-IV. (Tender No.830/EE/PD of 2021-22) |  |  | VCH/000813/2021-2022 | BP-2021-22-229 | 03/02/2022 | 03/02/2022 | GOUTAM CHAKRABORTY | 4.15 | 0 | 0 | 0
10 | PURULIA |  | Purulia Division | Retrofitting of Manguria-Lalpur Water Supply Scheme at Hura Block of Raghunathpur Sub Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/07839 | Retrofitting | Additional work for functional Household Tap Connection (FHTC) including other allied works of Manguria-Lalpur Water Supply Scheme at Hura Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. (Part-B) Mouza-Daldali, Bhagabandh under Daldali (1139 Nos.) Part-I. (Tender No.833/EE/PD of 2021-22) |  |  | VCH/000814/2021-2022 | BP-2021-22-230 | 03/02/2022 | 03/02/2022 | GOUTAM CHAKRABORTY | 4.77 | 0 | 0 | 0
11 | PURULIA |  | Purulia Division | Retrofitting of Manguria-Lalpur Water Supply Scheme at Hura Block of Raghunathpur Sub Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/07839 | Retrofitting | Additional work for functional Household Tap Connection (FHTC) and other allied works of Manguria-Lalpur Water Supply Scheme at Hura Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. (Part-A) (Chatumadar G.P.) | Assistant Engineer | Junior Engineer | ORD/000660/2023-2024 | 1353/PD | 13/09/2023 | 28/10/2023 | ALOK KUMAR CHAKRABORTY | 2.02 | 0 | 0 | 100
12 | PURULIA |  | Purulia Division | Retrofitting of Manguria-Lalpur Water Supply Scheme at Hura Block of Raghunathpur Sub Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/07839 | Retrofitting | Repairing and renovation op pipe line at Lalpur & Hijuli village under Lalpur-Manguria Water supply Scheme. (Tender No.533/EE/PD of 2022-23) |  |  | VCH/001309/2022-2023 | 181/844340 | 06/12/2022 | 06/12/2022 | ALOK KUMAR CHAKRABORTY | 0.86 | 0 | 0 | 0
Total | [13 empty] | 224.13 | 34.58 | 15.43