## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURULIA |  | Purulia Division | Retrofitting of Paharpur Water Supply Scheme at Kashipur Block of Raghunathpur Sub Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/07840 | Retrofitting | Laying of distribution pipe line ( 90 & 75 mm dia HDPE pipe ) for Kargali and Jamua villege of Raghunathpur-II Development Block under Raghunathpur Sub-Divn, P.H.E. Dte. (In connection with Paray Samadhan) | Assistant Engineer | Junior Engineer | ORD/000014/2021-2022 | 743/PD | 06/07/2021 | 05/08/2021 | KHITISH CHANDRA PATHAK | 11.96 | 1.08 | 9 | 80
2 | PURULIA |  | Purulia Division | Retrofitting of Paharpur Water Supply Scheme at Kashipur Block of Raghunathpur Sub Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme | SM/07840 | Retrofitting | Functional Household Tap Connection (FHTC) including other allied works of Paharpur Water Supply Scheme at Kashipur Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. (176 Nos.) | Assistant Engineer | Junior Engineer | ORD/000241/2020-2021 | 62/PD | 15/01/2021 | 01/03/2021 | SHYAMAL KUMAR DEY | 9.88 | 16.25 | 164.49 | 0
Total | [13 empty] | 21.84 | 17.33 | 79.36